## Sheet1
ID | SERIAL_NUMBER | ACTIVITY_ID | ACTIVITY_NAME | TASK_RANK | PARENT_ID | PROJECT_ID | INSTRUCTION | FORMAT_INSTRUCTION | SRC_AGENT | TARGET_AGENT | START_DATE | END_DATE | ACTUAL_START_DATE | ACTUAL_END_DATE | STATUS | PROCESS | PRINCIPAL | PRINCIPAL_COMPANY | SCENARIO | CREATED_BY | CREATION_DATE | LAST_UPDATE_BY | LAST_UPDATE_DATE | group_id | RAW_EQUIPMENT_LIST | TASK_COMMENT | TODO_ID | MANAGEMENT_UNIT | OWNER | MANUAL_PROCESS | REAL_MANAGEMENT_UNIT
1670562 | 00069a13a10a4c1173108359be7a9677 | 9.1 | 计算管理系统对接 | 2 | d79e747ac029013e8f356c2cd17602f0 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 79 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD18 |  |  | 303-POD18
1670752 | 00e4f3758ca903ff196f26ef6dbf1b44 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | dd9464ecec8bdea6a13f134a3ad565e4 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:57 | 104 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD23 |  |  | 304-POD23
1670206 | 02b5f0170cde65079f531aca74bc960a | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 65f90532d7fb93b4b2e1da26e63823b6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 33 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD12 |  |  | 204-POD12
1670469 | 02d0ff79432df68fdf35c63a91b94ab0 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 62832bb134c8624ef9c070316b881967 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 67 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670052 | 03a2482dbef9fb79c6588bc482ce2915 | 8.12 | 计算子系统验证-智算服务器 | 2 | f6554bcb6c45099802bd0f92dca5750a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:57 | 13 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD27 |  |  | 201-POD27
1670761 | 03dbb366886e837f6be3df6c38f25ac5 | 8.13 | 计算子系统验证-灵衢网络 | 2 | dd9464ecec8bdea6a13f134a3ad565e4 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:57 | 105 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD23 |  |  | 304-POD23
1670327 | 0445816358b4542006ac7f17adc30c22 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 03ac3374406c6fe0e56bd97ed7c4daab | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 49 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD26 |  |  | 201-POD26
1670653 | 04471409296a004077d74704592e83e1 | 8.12 | 计算子系统验证-智算服务器 | 2 | 9865de96ab6bde557d2d2c58109fcc5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 91 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD24 |  |  | 304-POD24
1670205 | 048eda29ab0e70af8b1874dd3fe30bac | 8.6 | 智算硬件压测 | 2 | 65f90532d7fb93b4b2e1da26e63823b6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 33 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD12 |  |  | 204-POD12
1670730 | 06e567210e09d65c0249d525bdb59b1e | 8.12 | 计算子系统验证-智算服务器 | 2 | 103ca18ba6bf0c3ba090a402745158f5 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:57 | 101 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD22 |  |  | 304-POD22
1670260 | 07070ba5e25ef4b053a5975e498a6325 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 3b2c2588b3d1e76c61bb8a9291dd4870 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 40 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD4 |  |  | 202-POD4
1670130 | 07be1e130cce284ef173a0bb7a09f548 | 8.13 | 计算子系统验证-灵衢网络 | 2 | f55d7830292083df19382d92eb48d9d1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 23 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670829 | 0822386add5a1180d0292ed26df43dbb | 8.8 | 计算子系统部署调测-智算服务器 | 2 | a018577ea7ff9ff374d57cc088d2fc37 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:57 | 114 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD36 |  |  | 401-POD36
1670204 | 08271810ebec5454b21428a4922b1089 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 65f90532d7fb93b4b2e1da26e63823b6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 33 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD12 |  |  | 204-POD12
1670185 | 092a455ad65084d9aaff776b4a7a23f2 | 9.1 | 计算管理系统对接 | 2 | f24d9c06378477e8290961e6fe6908ff | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 30 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD7 |  |  | 203-POD7
1670207 | 093d2acadc59c25a531649845a807922 | 8.12 | 计算子系统验证-智算服务器 | 2 | 65f90532d7fb93b4b2e1da26e63823b6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 33 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD12 |  |  | 204-POD12
1670827 | 0985a57b9ba24fb4e15488a3415cb0c2 | 8.2 | 设备硬装初始化-智算服务器 | 2 | a018577ea7ff9ff374d57cc088d2fc37 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:57 | 114 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD36 |  |  | 401-POD36
1670854 | 0a318444456b1bd51a504e66e2f976b4 | 9.1 | 计算管理系统对接 | 2 | 42a8d912d3b0fd14c277186e18c6825f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:57 | 117 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD35 |  |  | 401-POD35
1670477 | 0a63b4bc62617b0f4b9e639bfb1f635f | 9.2 | 网络管理系统对接 | 2 | d4df1db7384345c0bac27b731dd16501 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-14至2026-06-15进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-14 | 2026-06-15 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 68 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670404 | 0a70e5fe17079c5d4cf6dd4dc5237dff | 8.2 | 设备硬装初始化-智算服务器 | 2 | a020d5cdac05db8c30edc29d4ca7bf54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 59 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670037 | 0aca2e14ae59bda4d20dc80d60caa1b7 | 9.2 | 网络管理系统对接 | 2 | 416dc13968efa0c84d3861b54118cecc | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-11至2026-06-12进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-11 | 2026-06-12 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:57 | 11 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670860 | 0b5d3b033b3ed3a6ce2126a2793f2496 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | ddf5a0337be203189f6d5c2d8a497dd6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:57 | 118 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD35 |  |  | 401-POD35
1670049 | 0b70a4aaaff712edf018206c5c74cfb0 | 8.2 | 设备硬装初始化-智算服务器 | 2 | f6554bcb6c45099802bd0f92dca5750a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:57 | 13 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD27 |  |  | 201-POD27
1670359 | 0bea3a75ebacf129ed9270faef26a352 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | db2049f830177d2afeb9c4eeb4815b0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 53 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD11 |  |  | 204-POD11
1670535 | 0cbdbae9187c77ade988aa7b0834e7c5 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 18a4041ec1b2f6ab8822aa3a68e26789 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 76 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD32 |  |  | 301-POD32
1670192 | 0d471e5fd80681eb0ce22bc45c35106f | 8.13 | 计算子系统验证-灵衢网络 | 2 | d39b2ce315888c23aa46daedfdb03e98 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 31 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD7 |  |  | 203-POD7
1670459 | 0d49c93191e38083f4f8f197d8f3bb62 | 8.6 | 智算硬件压测 | 2 | 62832bb134c8624ef9c070316b881967 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 66 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670414 | 0df99476196b37cb0533f2ff08204851 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | a020d5cdac05db8c30edc29d4ca7bf54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 60 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670500 | 0f1fb4ebbf92dc29abef13ea679fffb6 | 8.13 | 计算子系统验证-灵衢网络 | 2 | c826c8feae238ad2bf303073abdfbb25 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 71 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD14 |  |  | 302-POD14
1670514 | 0f9e1f4499f5842fb8984e568c29f94f | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 24e3cdd2d57d17b0a366e2f5ead2d61e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 73 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD16 |  |  | 302-POD16
1670169 | 102126a1fa7b11ecfc58a3d13656a2ca | 9.2 | 网络管理系统对接 | 2 | c502d6697cb2b2b4b57de0b1a9a2f308 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-15至2026-06-16进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-15 | 2026-06-16 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 28 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670838 | 104d4cc936aafa17886ce18a3bb5778b | 8.13 | 计算子系统验证-灵衢网络 | 2 | a018577ea7ff9ff374d57cc088d2fc37 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:57 | 115 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD36 |  |  | 401-POD36
1670253 | 126aff2d7bcdce3b9c5c5ffede376f72 | 8.12 | 计算子系统验证-智算服务器 | 2 | 3b2c2588b3d1e76c61bb8a9291dd4870 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 39 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD4 |  |  | 202-POD4
1669981 | 15221f6703128398069ba03711874240 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 61792c7944ed3393ae8abb6c3a4e1dd7 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:57 | 4 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD10 |  |  | 204-POD10
1670151 | 15abdc2d338b118a72353e3da0c287eb | 8.6 | 智算硬件压测 | 2 | f07be6ccb5484bc38067669a6864270c | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 26 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670607 | 1608d8bd691331e8dfc3b72edf190ac1 | 8.12 | 计算子系统验证-智算服务器 | 2 | ca6bf767c2cb6de8211c420fc93e157e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 85 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD15 |  |  | 302-POD15
1670304 | 16eabf676bf9bacd4c86653ec530070b | 8.2 | 设备硬装初始化-智算服务器 | 2 | d87b31ab43bb926bd4a93efe50d8e464 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 46 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD28 |  |  | 201-POD28
1670783 | 18840710487fa98e6426ad5b8a061c16 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 7e393e340b11a9213d7cde8165a81259 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:57 | 108 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670852 | 197a016aebbd3a2d1bbb3628513f038b | 8.8 | 计算子系统部署调测-智算服务器 | 2 | ddf5a0337be203189f6d5c2d8a497dd6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:57 | 117 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD35 |  |  | 401-POD35
1670336 | 199bbdc58fd3a2b5502e9fa9cb7e1d0f | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 03ac3374406c6fe0e56bd97ed7c4daab | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 50 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD26 |  |  | 201-POD26
1670361 | 1bf990433cfb4a3c29c920fc8e74f3ab | 8.13 | 计算子系统验证-灵衢网络 | 2 | db2049f830177d2afeb9c4eeb4815b0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 53 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD11 |  |  | 204-POD11
1670637 | 1c67de4b527e910eb970061bda676e1b | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | b426a0ce7dc8ae6f732421d0e26e6a5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 89 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD20 |  |  | 303-POD20
1670415 | 1ceabd7e75c8f106c07d718db1c7adbd | 8.13 | 计算子系统验证-灵衢网络 | 2 | a020d5cdac05db8c30edc29d4ca7bf54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 60 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670029 | 1f5e02fe5293f63ee09fb7f9b4711a8a | 8.13 | 计算子系统验证-灵衢网络 | 2 | 4943d29f93667ff572e188c2ac2b7fc8 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:57 | 10 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670135 | 1f9c3fcdce5222cbe40e3ac47c92733a | 8.1 | 基础网络配置 | 2 | f55d7830292083df19382d92eb48d9d1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-06至2026-06-07进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-06 | 2026-06-07 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 24 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670421 | 2000132e346d20f0b1f4e338ae7f7d28 | 8.7 | 网络子系统部署调测 | 2 | a020d5cdac05db8c30edc29d4ca7bf54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-09至2026-06-13进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-09 | 2026-06-13 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 61 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670036 | 2128d6c5d1f62175deb5e64339deab6b | 8.15 | 网络子系统验证 | 2 | 4943d29f93667ff572e188c2ac2b7fc8 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-11至2026-06-13进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-11 | 2026-06-13 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:57 | 11 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670423 | 21874de7031b481a4eb90ac6a01acb92 | 9.2 | 网络管理系统对接 | 2 | 9aaf1fb8521f3bd14a8493c72ed04ff1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-14至2026-06-15进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-14 | 2026-06-15 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 61 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670184 | 21c3b45366d6a8599a22e13eb9f7a6fc | 8.12 | 计算子系统验证-智算服务器 | 2 | d39b2ce315888c23aa46daedfdb03e98 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 30 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD7 |  |  | 203-POD7
1670583 | 21cdd67791cee19bc628c6be4154f058 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 05c3fff9227a16057f256f6f4453949e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 82 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD31 |  |  | 301-POD31
1670072 | 22e6b791acba45f71aac73f0cbcea39a | 8.2 | 设备硬装初始化-智算服务器 | 2 | 2a5d2b339c9e5d555058e266671d1f5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 16 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD3 |  |  | 202-POD3
1670119 | 232affadaa0bdfb89e786ec37e0d4b27 | 8.2 | 设备硬装初始化-智算服务器 | 2 | f55d7830292083df19382d92eb48d9d1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 22 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670444 | 24de1105e2d221e1cfbde72692628d95 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | dee03de40e6fb41ce5b05d7994205898 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:57 | 64 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD30 |  |  | 301-POD30
1670314 | 26606a5ce7c473cc14d35eb4d26dab48 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | d87b31ab43bb926bd4a93efe50d8e464 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:57 | 47 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD28 |  |  | 201-POD28
1670374 | 267a1ffd81a845183ffd4fe4da5c7b28 | 8.6 | 智算硬件压测 | 2 | a6a1e1a79c725060a83506cfdd0623ce | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 55 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670831 | 26fddec3d7b0e688b19107497782ea59 | 9.1 | 计算管理系统对接 | 2 | 32615e4caf4263763e674924ac7e22aa | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 114 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD36 |  |  | 401-POD36
1670261 | 27410e2a7f92377a768dba03166fd018 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 3b2c2588b3d1e76c61bb8a9291dd4870 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 40 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD4 |  |  | 202-POD4
1670213 | 27ec2eeed547544c104f0964a5ae9aae | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 65f90532d7fb93b4b2e1da26e63823b6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 34 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD12 |  |  | 204-POD12
1669983 | 2892adb9917ab09aa0cd5e9cfb2f50e3 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 61792c7944ed3393ae8abb6c3a4e1dd7 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 4 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD10 |  |  | 204-POD10
1670851 | 28b17020871795551d7bb3ac1532277b | 8.6 | 智算硬件压测 | 2 | ddf5a0337be203189f6d5c2d8a497dd6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 117 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD35 |  |  | 401-POD35
1670405 | 2c190e6c96680a6aa3c08c0a86f386e2 | 8.6 | 智算硬件压测 | 2 | a020d5cdac05db8c30edc29d4ca7bf54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 59 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670515 | 2c4eff4d8a6fd9f9caf4451d4ff6e4ab | 8.12 | 计算子系统验证-智算服务器 | 2 | 24e3cdd2d57d17b0a366e2f5ead2d61e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 73 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD16 |  |  | 302-POD16
1669995 | 2c70c759c45a24d1a4b447421719826a | 8.2 | 设备硬装初始化-智算服务器 | 2 | 2d2940d893d47b77b5ff6898b6a042c3 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 6 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD2 |  |  | 202-POD2
1670027 | 300c656d3f6a3163f82e1fccddfb2287 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 4943d29f93667ff572e188c2ac2b7fc8 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 10 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670191 | 307a0505c3719565698bf00213ab1715 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | d39b2ce315888c23aa46daedfdb03e98 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 31 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD7 |  |  | 203-POD7
1670462 | 31448874910cff67fc8622fcb6ff19fe | 9.1 | 计算管理系统对接 | 2 | d4df1db7384345c0bac27b731dd16501 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 66 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670075 | 321d23efa5edbf44d7b6a2064752882b | 8.12 | 计算子系统验证-智算服务器 | 2 | 2a5d2b339c9e5d555058e266671d1f5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 16 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD3 |  |  | 202-POD3
1670760 | 32eec8d5c95cc3a104a525cda26244f9 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | dd9464ecec8bdea6a13f134a3ad565e4 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 105 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD23 |  |  | 304-POD23
1670682 | 33b4eb236b3ab6310053dfd99e016217 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 251feb99813e3a248e5095c3f4955f56 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 95 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD19 |  |  | 303-POD19
1670292 | 33e4cc37b8accfb72ed36a0dc7710c34 | 9.2 | 网络管理系统对接 | 2 | 56b24380af50623a9af24dd5fd905643 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-14至2026-06-15进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-14 | 2026-06-15 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 44 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670468 | 358db08e20f0b4dfdf58affa26e0b75c | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 62832bb134c8624ef9c070316b881967 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 67 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670867 | 370fc98fdb711b4324dab13ccfbb8285 | 9.5 | 综合布线整改 | 2 | e29f1d8756ba3935d4d6a08313e40743 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-30至2026-07-03进行综合布线整改活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-06-30 | 2026-07-03 |  |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 |  | { "device_list": [] } |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36 |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36
1670181 | 376711f1a6376cf594c562119eb2b964 | 8.2 | 设备硬装初始化-智算服务器 | 2 | d39b2ce315888c23aa46daedfdb03e98 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 30 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD7 |  |  | 203-POD7
1670498 | 37c358da2daa35ff23cfd5908d684f57 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | c826c8feae238ad2bf303073abdfbb25 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 71 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD14 |  |  | 302-POD14
1670675 | 37f8e25bdd38acb292cbe867f2d7374d | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 251feb99813e3a248e5095c3f4955f56 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 94 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD19 |  |  | 303-POD19
1670096 | 3829e444b7e6fa33a4f90c08bd4e9850 | 8.6 | 智算硬件压测 | 2 | c897a07909985ce10d9a5b747aee076a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD6 |  |  | 203-POD6
1670095 | 38598bf30cfc819ce105cd7b48229432 | 8.2 | 设备硬装初始化-智算服务器 | 2 | c897a07909985ce10d9a5b747aee076a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD6 |  |  | 203-POD6
1670238 | 395082f6c3e1e635fcd444f6484e3a84 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 4b665118faff7bce4565ba27e63e51a2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 37 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD8 |  |  | 203-POD8
1670214 | 3a051a235f1a0d34629e6ebe162c0280 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 65f90532d7fb93b4b2e1da26e63823b6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 34 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD12 |  |  | 204-POD12
1670813 | 3c4361b1d75eff70d6e81ae8254a505b | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 553f764385d381145313cd0285178e0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 112 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD34 |  |  | 401-POD34
1670859 | 3c515e3e383cb0dd68a083e445fb8ca4 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | ddf5a0337be203189f6d5c2d8a497dd6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 118 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD35 |  |  | 401-POD35
1670337 | 3d13acf1e213a53ae2baae1093622d38 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 03ac3374406c6fe0e56bd97ed7c4daab | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:45 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 50 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD26 |  |  | 201-POD26
1670058 | 3e15cc8107e07289163752e0204fcbbe | 8.5 | 设备硬装初始化-灵衢网络 | 2 | f6554bcb6c45099802bd0f92dca5750a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 14 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD27 |  |  | 201-POD27
1670406 | 3ef05d7aa606ec80594c273177661b77 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | a020d5cdac05db8c30edc29d4ca7bf54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 59 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670567 | 3f120a25b55959a28f14d25d9156a545 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 9546c58cc8fbce8dfa4c3446148e3386 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 80 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD18 |  |  | 303-POD18
1670420 | 3f526a603a311ad76454f97d66b6b6ce | 8.1 | 基础网络配置 | 2 | a020d5cdac05db8c30edc29d4ca7bf54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-07至2026-06-08进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-07 | 2026-06-08 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 61 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670123 | 40ad810e2d0122dbfda7295c13540c23 | 9.1 | 计算管理系统对接 | 2 | 6f24d4f15bf5bb804fb2b7ae87b632e2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 22 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670866 | 40c554fc43bc59b5ebdfca4c01901009 | 9.4 | 线序及光链路质量排查 | 2 | e29f1d8756ba3935d4d6a08313e40743 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行线序及光链路质量排查活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 |  |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 |  | { "device_list": [] } |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36 |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36
1670389 | 41774c9b4b184ef4f27572acd73cda55 | 8.1 | 基础网络配置 | 2 | a6a1e1a79c725060a83506cfdd0623ce | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-08至2026-06-09进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-08 | 2026-06-09 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 57 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670237 | 41b6a65f550a621cb4bffc697d092466 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 4b665118faff7bce4565ba27e63e51a2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 37 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD8 |  |  | 203-POD8
1670775 | 42a52839f9499deda027f3f2327748dc | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 7e393e340b11a9213d7cde8165a81259 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 107 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670467 | 42ef05d0a771cc885bf67efbf30fef4d | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 62832bb134c8624ef9c070316b881967 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 67 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670446 | 4427764450d82766479a9ebb3572b4db | 8.13 | 计算子系统验证-灵衢网络 | 2 | dee03de40e6fb41ce5b05d7994205898 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 64 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD30 |  |  | 301-POD30
1670407 | 448ebcafadbf8c4e1b9a0965a7323d09 | 8.12 | 计算子系统验证-智算服务器 | 2 | a020d5cdac05db8c30edc29d4ca7bf54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 59 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670154 | 46111b4ca0e22b5817db9ba1ce6fcb14 | 9.1 | 计算管理系统对接 | 2 | c502d6697cb2b2b4b57de0b1a9a2f308 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 26 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670837 | 465ced90c161a9f1560dc1842e555750 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | a018577ea7ff9ff374d57cc088d2fc37 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 115 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD36 |  |  | 401-POD36
1670352 | 4738b9039e7c28e8842a6eb9c598c4bf | 8.8 | 计算子系统部署调测-智算服务器 | 2 | db2049f830177d2afeb9c4eeb4815b0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 52 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD11 |  |  | 204-POD11
1670784 | 49d939c1aab070f5fb1fc30aac6514cb | 8.13 | 计算子系统验证-灵衢网络 | 2 | 7e393e340b11a9213d7cde8165a81259 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 108 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1669972 | 4b0af3d9290ecb856c7ab5adb1254e2c | 8.2 | 设备硬装初始化-智算服务器 | 2 | 61792c7944ed3393ae8abb6c3a4e1dd7 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD10 |  |  | 204-POD10
1670676 | 4b795d7a2a2124dac85f835f0851e628 | 8.12 | 计算子系统验证-智算服务器 | 2 | 251feb99813e3a248e5095c3f4955f56 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 94 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD19 |  |  | 303-POD19
1670005 | 4c313fa736c9c5b7c0e5f8f573de4d67 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 2d2940d893d47b77b5ff6898b6a042c3 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 7 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD2 |  |  | 202-POD2
1670651 | 4c640e91c2719252c16507270f537b60 | 8.6 | 智算硬件压测 | 2 | 9865de96ab6bde557d2d2c58109fcc5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 91 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD24 |  |  | 304-POD24
1670438 | 4e5dbf2a9f4dd9ec5bd4bc55e1a435c7 | 8.12 | 计算子系统验证-智算服务器 | 2 | dee03de40e6fb41ce5b05d7994205898 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 63 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD30 |  |  | 301-POD30
1670083 | 4f5ade0017e545f253a8ac8add0b006e | 8.13 | 计算子系统验证-灵衢网络 | 2 | 2a5d2b339c9e5d555058e266671d1f5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 17 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD3 |  |  | 202-POD3
1670605 | 4f691a2520e2503e588e48623049ef5d | 8.6 | 智算硬件压测 | 2 | ca6bf767c2cb6de8211c420fc93e157e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 85 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD15 |  |  | 302-POD15
1670152 | 4f774d093aebd68856bc3f20033e1884 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | f07be6ccb5484bc38067669a6864270c | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 26 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670307 | 51a8f34fb9a548d9eb475900f9991f35 | 8.12 | 计算子系统验证-智算服务器 | 2 | d87b31ab43bb926bd4a93efe50d8e464 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 46 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD28 |  |  | 201-POD28
1670559 | 5364fffbbf26e4aa44bdde1dcdd46141 | 8.6 | 智算硬件压测 | 2 | 9546c58cc8fbce8dfa4c3446148e3386 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 79 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD18 |  |  | 303-POD18
1670499 | 54479cb9ffa9c0fb7e2ddcca4ae4ba48 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | c826c8feae238ad2bf303073abdfbb25 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 71 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD14 |  |  | 302-POD14
1670283 | 55551ae5f7c829ea5853e17f1f8e3248 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 18ca86273180d7644d99757367c6797d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 43 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670236 | 571b0b573bfa8eef440a07fbda7809d7 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 4b665118faff7bce4565ba27e63e51a2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 37 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD8 |  |  | 203-POD8
1670591 | 58435e92fdd519da5104333d5b9f564f | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 05c3fff9227a16057f256f6f4453949e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 83 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD31 |  |  | 301-POD31
1670776 | 58d03ccc101cc030d07ced9b48666a63 | 8.12 | 计算子系统验证-智算服务器 | 2 | 7e393e340b11a9213d7cde8165a81259 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 107 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670215 | 5926ce6a7a718c00b8d1a4c70a8601a2 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 65f90532d7fb93b4b2e1da26e63823b6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 34 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD12 |  |  | 204-POD12
1670650 | 5af99a06e6aedf3a361e0626c7569f75 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 9865de96ab6bde557d2d2c58109fcc5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 91 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD24 |  |  | 304-POD24
1670750 | 5b4f0d4febdbbe85fc0e9ce8ab4e676c | 8.2 | 设备硬装初始化-智算服务器 | 2 | dd9464ecec8bdea6a13f134a3ad565e4 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 104 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD23 |  |  | 304-POD23
1669998 | 5baac4105c321615e0459f3e7b429314 | 8.12 | 计算子系统验证-智算服务器 | 2 | 2d2940d893d47b77b5ff6898b6a042c3 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 6 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD2 |  |  | 202-POD2
1670630 | 5c519f4c5bf5d36670d93db228c603bb | 8.12 | 计算子系统验证-智算服务器 | 2 | b426a0ce7dc8ae6f732421d0e26e6a5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 88 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD20 |  |  | 303-POD20
1670638 | 5d4dbfcf2ce3597eaa45b1428c261c92 | 8.13 | 计算子系统验证-灵衢网络 | 2 | b426a0ce7dc8ae6f732421d0e26e6a5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 89 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD20 |  |  | 303-POD20
1670138 | 5eb132e0ee49df33b94a477cd285be8d | 9.2 | 网络管理系统对接 | 2 | 6f24d4f15bf5bb804fb2b7ae87b632e2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-13至2026-06-14进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-13 | 2026-06-14 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 24 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670160 | 5eb308c033dd33352093806f2eeb5db7 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | f07be6ccb5484bc38067669a6864270c | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 27 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670006 | 5ebcc3499eb09a763a6214ffa388c9c2 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 2d2940d893d47b77b5ff6898b6a042c3 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 7 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD2 |  |  | 202-POD2
1670490 | 5ed690d53696695156384c640b06820b | 8.6 | 智算硬件压测 | 2 | c826c8feae238ad2bf303073abdfbb25 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 70 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD14 |  |  | 302-POD14
1670828 | 5f1e7237751dd24fcd5ca80a945b02bc | 8.6 | 智算硬件压测 | 2 | a018577ea7ff9ff374d57cc088d2fc37 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 114 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD36 |  |  | 401-POD36
1670284 | 5f54280f6add27d2a3a8cc28574292f9 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 18ca86273180d7644d99757367c6797d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 43 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670422 | 5fa14bf78a49512cda52331a1efa36b8 | 8.15 | 网络子系统验证 | 2 | a020d5cdac05db8c30edc29d4ca7bf54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-14至2026-06-16进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-14 | 2026-06-16 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 61 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670475 | 5fe7935f021ccdbc0c9631f7138af4be | 8.7 | 网络子系统部署调测 | 2 | 62832bb134c8624ef9c070316b881967 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-09至2026-06-13进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-09 | 2026-06-13 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 68 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670631 | 6063f89ac4eec404f759de9b2ffb4370 | 9.1 | 计算管理系统对接 | 2 | dc37a5c3041db67d631c3da82467d899 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 88 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD20 |  |  | 303-POD20
1670699 | 6520a39d1a2fdf94ed0d55c7df8f6580 | 8.12 | 计算子系统验证-智算服务器 | 2 | fd49155be495025405d25d7b173f6f39 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 97 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670377 | 661047e2db06dfccdf0a5e5f1b1995ba | 9.1 | 计算管理系统对接 | 2 | a0aee0b212766d4ff35ba0eba7e331ec | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 55 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670850 | 667b0fe81c8f962c1386bf1db1e7b419 | 8.2 | 设备硬装初始化-智算服务器 | 2 | ddf5a0337be203189f6d5c2d8a497dd6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 117 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD35 |  |  | 401-POD35
1670581 | 66b4ea14379932fc1d63d5273994b781 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 05c3fff9227a16057f256f6f4453949e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 82 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD31 |  |  | 301-POD31
1670461 | 6726b8b71f45bb9adee2aeaabd52e585 | 8.12 | 计算子系统验证-智算服务器 | 2 | 62832bb134c8624ef9c070316b881967 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 66 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670190 | 679b23a785bb0eac7c7515b3027c0e84 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | d39b2ce315888c23aa46daedfdb03e98 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 31 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD7 |  |  | 203-POD7
1670105 | 687f022c5348b010d948ae53fb751611 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | c897a07909985ce10d9a5b747aee076a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 20 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD6 |  |  | 203-POD6
1670354 | 698dda77a813dab9fef2b18e418e34ad | 9.1 | 计算管理系统对接 | 2 | c068b8666507d7fc6dc3a4744721c0ca | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 52 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD11 |  |  | 204-POD11
1670491 | 69bd12f8db260e86b2068f53234bd77e | 8.8 | 计算子系统部署调测-智算服务器 | 2 | c826c8feae238ad2bf303073abdfbb25 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 70 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD14 |  |  | 302-POD14
1670523 | 6a3cd24d4eac020a9454a6d262d18ad2 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 24e3cdd2d57d17b0a366e2f5ead2d61e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 74 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD16 |  |  | 302-POD16
1670022 | 6aaeb20802c7f5cfb3f53f8ec6af9fef | 9.1 | 计算管理系统对接 | 2 | 416dc13968efa0c84d3861b54118cecc | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 9 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670074 | 6b790c63bf30fe7da65787f01dfbc125 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 2a5d2b339c9e5d555058e266671d1f5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 16 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD3 |  |  | 202-POD3
1670537 | 6c006086d37e380d522c89b73be3ff3c | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 18a4041ec1b2f6ab8822aa3a68e26789 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 76 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD32 |  |  | 301-POD32
1670492 | 6c667ce3995b14dd8e6dba5812bf57d2 | 8.12 | 计算子系统验证-智算服务器 | 2 | c826c8feae238ad2bf303073abdfbb25 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 70 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD14 |  |  | 302-POD14
1670729 | 6dbc912ff1a9818761ed245fcf71793d | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 103ca18ba6bf0c3ba090a402745158f5 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 101 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD22 |  |  | 304-POD22
1670773 | 6e6cb10d355180fe928993ce199238e0 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 7e393e340b11a9213d7cde8165a81259 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 107 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670476 | 6f039e573e6f64265ccb3a28128a743b | 8.15 | 网络子系统验证 | 2 | 62832bb134c8624ef9c070316b881967 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-14至2026-06-16进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-14 | 2026-06-16 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 68 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670166 | 6f30e93891bd2d00d2f6172d09026704 | 8.1 | 基础网络配置 | 2 | f07be6ccb5484bc38067669a6864270c | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-08至2026-06-09进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-08 | 2026-06-09 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 28 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670375 | 6f93d851cdb128342055cdaaeda1330f | 8.8 | 计算子系统部署调测-智算服务器 | 2 | a6a1e1a79c725060a83506cfdd0623ce | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 55 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670153 | 716ec97bcf56c230b6485196705aed85 | 8.12 | 计算子系统验证-智算服务器 | 2 | f07be6ccb5484bc38067669a6864270c | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 26 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670121 | 71dd02d905ef31882721d193a016c724 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | f55d7830292083df19382d92eb48d9d1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 22 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670161 | 720be61db0243400a94782f5dc7cb919 | 8.13 | 计算子系统验证-灵衢网络 | 2 | f07be6ccb5484bc38067669a6864270c | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 27 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670869 | 72243341ea6e6f112c1015f02f530359 | 9.7 | 集群系统集成测试 | 2 | e29f1d8756ba3935d4d6a08313e40743 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-07-06至2026-07-10进行集群系统集成测试活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 432, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-07-06 | 2026-07-10 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 |  | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 1728, "unit": "台" } ] } |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36 |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36
1670437 | 72d31bf7fbea69469b12ed9604e15f90 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | dee03de40e6fb41ce5b05d7994205898 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 63 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD30 |  |  | 301-POD30
1670073 | 7312699602e7672c3304abffea0e14e2 | 8.6 | 智算硬件压测 | 2 | 2a5d2b339c9e5d555058e266671d1f5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 16 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD3 |  |  | 202-POD3
1670106 | 739d0e1968d31c3d91bd9f5d96ac83b1 | 8.13 | 计算子系统验证-灵衢网络 | 2 | c897a07909985ce10d9a5b747aee076a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 20 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD6 |  |  | 203-POD6
1670673 | 73a297811d83f7971ac940877dc6a006 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 251feb99813e3a248e5095c3f4955f56 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 94 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD19 |  |  | 303-POD19
1670789 | 74c23344b6790fc2a41e50463c425491 | 8.1 | 基础网络配置 | 2 | 7e393e340b11a9213d7cde8165a81259 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-06至2026-06-07进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-06 | 2026-06-07 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 109 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670493 | 760fbd6cf57e876f0838301e3750ca0c | 9.1 | 计算管理系统对接 | 2 | 2d878ea74de2fef5433bf50d63524341 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 70 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD14 |  |  | 302-POD14
1670328 | 7654bbe943c963a42cd11c74c8b0dc92 | 8.6 | 智算硬件压测 | 2 | 03ac3374406c6fe0e56bd97ed7c4daab | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 49 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD26 |  |  | 201-POD26
1670104 | 777a783e7312f2eccad062b6e6e81d25 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | c897a07909985ce10d9a5b747aee076a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 20 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD6 |  |  | 203-POD6
1670536 | 7afa30ce94bd39d65b8013af20a15bb3 | 8.6 | 智算硬件压测 | 2 | 18a4041ec1b2f6ab8822aa3a68e26789 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 76 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD32 |  |  | 301-POD32
1670413 | 7b1c392d5d44d2dbca7ec55e082767a4 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | a020d5cdac05db8c30edc29d4ca7bf54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 60 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670585 | 7c72be42884d7c7c3dc08a9f99b1cd74 | 9.1 | 计算管理系统对接 | 2 | 11bc9c94bcfe2123306867de7fe4dfa7 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 82 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD31 |  |  | 301-POD31
1670183 | 7c9994ef9d7b5848179f982f0cfa4f98 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | d39b2ce315888c23aa46daedfdb03e98 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 30 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD7 |  |  | 203-POD7
1670677 | 7d602c72e2353b856469c3b0e46bc722 | 9.1 | 计算管理系统对接 | 2 | adf7996c7b55e2b1f00a885fde4deece | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 94 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD19 |  |  | 303-POD19
1670439 | 7deea6acd4cfb5d9b46e715012f11a38 | 9.1 | 计算管理系统对接 | 2 | c471908fb823a3604f3db7249eabaa98 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 63 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD30 |  |  | 301-POD30
1670019 | 7ee5fbaaf92c2f9ebbd7f018ae11860e | 8.6 | 智算硬件压测 | 2 | 4943d29f93667ff572e188c2ac2b7fc8 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 9 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670659 | 7f84b2626189d7679eabbbd031d41c54 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 9865de96ab6bde557d2d2c58109fcc5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 92 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD24 |  |  | 304-POD24
1670873 | 817577bbb103a51e0837b379f4964bdb | 12.3 | 验收报告沟通 | 2 | 2c2746963b3a0c69e85497f95577de1b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-07-26至2026-07-28进行验收报告沟通活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-07-26 | 2026-07-28 |  |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 |  | { "device_list": [] } |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36 |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36
1669976 | 81a187dad7e7924594e3a8e2a0b0df97 | 9.1 | 计算管理系统对接 | 2 | 5eec74f5e8f31efe94dfbac89113804d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD10 |  |  | 204-POD10
1670705 | 82e0e4f293c99ac311471070445a5df5 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | fd49155be495025405d25d7b173f6f39 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 98 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670738 | 82ea60e007cd8053ca6799c77eb79068 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 103ca18ba6bf0c3ba090a402745158f5 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 102 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD22 |  |  | 304-POD22
1670474 | 82ff008e2bacd5cf66e3a42fe27b1c56 | 8.1 | 基础网络配置 | 2 | 62832bb134c8624ef9c070316b881967 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-07至2026-06-08进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-07 | 2026-06-08 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 68 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670539 | 839a631e5bd12a97d91f7048dce427fb | 9.1 | 计算管理系统对接 | 2 | 648ba884bc6daf636ee1f5a8fbc69c54 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 76 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD32 |  |  | 301-POD32
1670373 | 84941df55157c816b004164be6bdcdaa | 8.2 | 设备硬装初始化-智算服务器 | 2 | a6a1e1a79c725060a83506cfdd0623ce | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 55 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670777 | 861d326c96b9d5cc96732d71ed0a98ca | 9.1 | 计算管理系统对接 | 2 | cd456b489e3ea99ad91599724f007b30 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 107 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670753 | 86db54ba7079467de23f94ce21030f0d | 8.12 | 计算子系统验证-智算服务器 | 2 | dd9464ecec8bdea6a13f134a3ad565e4 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 104 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD23 |  |  | 304-POD23
1670604 | 87477fde6b7f137749219a495d0ed2b0 | 8.2 | 设备硬装初始化-智算服务器 | 2 | ca6bf767c2cb6de8211c420fc93e157e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 85 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD15 |  |  | 302-POD15
1670290 | 87b4641354935c684a73eca39886cbfa | 8.7 | 网络子系统部署调测 | 2 | 18ca86273180d7644d99757367c6797d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-09至2026-06-13进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-09 | 2026-06-13 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 44 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670227 | 87e4d2356bbbaad01631651c9916b830 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 4b665118faff7bce4565ba27e63e51a2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 36 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD8 |  |  | 203-POD8
1670782 | 8831e66ae420a5f80bc543a5a4c2e093 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 7e393e340b11a9213d7cde8165a81259 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 108 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670308 | 893d7618b9ad2d47a16722b4e67af250 | 9.1 | 计算管理系统对接 | 2 | 413bf2d03e7bf4858c0dd3caea8204e4 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 46 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD28 |  |  | 201-POD28
1670592 | 8ab1bcecf975ba298367674a56451b5e | 8.13 | 计算子系统验证-灵衢网络 | 2 | 05c3fff9227a16057f256f6f4453949e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 83 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD31 |  |  | 301-POD31
1670259 | 8b7d770d85ae09e0802df50065c2027a | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 3b2c2588b3d1e76c61bb8a9291dd4870 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 40 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD4 |  |  | 202-POD4
1670569 | 8c2ae0b82eb55fc4fe1e08ba18dbf072 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 9546c58cc8fbce8dfa4c3446148e3386 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 80 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD18 |  |  | 303-POD18
1670122 | 8c847f75ac5c93a1391a76594980c9da | 8.12 | 计算子系统验证-智算服务器 | 2 | f55d7830292083df19382d92eb48d9d1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 22 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670021 | 8e3dc8ab779435d928486c4d2168cdd4 | 8.12 | 计算子系统验证-智算服务器 | 2 | 4943d29f93667ff572e188c2ac2b7fc8 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:46 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 9 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670731 | 8fa66c4326db867116b44532c2c59094 | 9.1 | 计算管理系统对接 | 2 | 78daf0394a04d446405a146a04cd35f2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 101 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD22 |  |  | 304-POD22
1670815 | 924c3be167cb72707c286489332ee13f | 8.13 | 计算子系统验证-灵衢网络 | 2 | 553f764385d381145313cd0285178e0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 112 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD34 |  |  | 401-POD34
1670836 | 9313d941e5126423ec334fdc62b3ea9f | 8.5 | 设备硬装初始化-灵衢网络 | 2 | a018577ea7ff9ff374d57cc088d2fc37 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 115 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD36 |  |  | 401-POD36
1669973 | 9579b8fc13f9f184b5b66fe8da0d8431 | 8.6 | 智算硬件压测 | 2 | 61792c7944ed3393ae8abb6c3a4e1dd7 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD10 |  |  | 204-POD10
1670706 | 957c85e850921536af79a43cc3839620 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | fd49155be495025405d25d7b173f6f39 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 98 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670053 | 95c7f4cf6bdcd803f56b8cae2c7f6091 | 9.1 | 计算管理系统对接 | 2 | 9ffadcc1a7c8c11a968981220a31d1f9 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 13 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD27 |  |  | 201-POD27
1670871 | 97640618c5d6270531f6e866ee7bfbd4 | 12.1 | 客户集群验收 | 2 | 2c2746963b3a0c69e85497f95577de1b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-07-11至2026-07-20进行客户集群验收活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-07-11 | 2026-07-20 |  |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 |  | { "device_list": [] } |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36 |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36
1670167 | 98505e48c9a0b327086c48824eaffc43 | 8.7 | 网络子系统部署调测 | 2 | f07be6ccb5484bc38067669a6864270c | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-10至2026-06-14进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-10 | 2026-06-14 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 28 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670276 | 987e21920b683f239113d4b3c0a91e93 | 8.12 | 计算子系统验证-智算服务器 | 2 | 18ca86273180d7644d99757367c6797d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 42 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670274 | 98bd52cdb1dba332978de55d9f39c4fe | 8.6 | 智算硬件压测 | 2 | 18ca86273180d7644d99757367c6797d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 42 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670521 | 99683d5e7bc71b0254ea769e2964a4a3 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 24e3cdd2d57d17b0a366e2f5ead2d61e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 74 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD16 |  |  | 302-POD16
1670129 | 9973d10b09b13b223edb3417a021b5ca | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | f55d7830292083df19382d92eb48d9d1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 23 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670713 | 99b1d91889911f45a446b8f878499dc3 | 8.7 | 网络子系统部署调测 | 2 | fd49155be495025405d25d7b173f6f39 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-08至2026-06-12进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-08 | 2026-06-12 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 99 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670561 | 9b17ab9266fee0d226b637e042af98a1 | 8.12 | 计算子系统验证-智算服务器 | 2 | 9546c58cc8fbce8dfa4c3446148e3386 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 79 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD18 |  |  | 303-POD18
1670727 | 9b184ff3700cd8b8830dc194ae2312cb | 8.2 | 设备硬装初始化-智算服务器 | 2 | 103ca18ba6bf0c3ba090a402745158f5 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 101 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD22 |  |  | 304-POD22
1670489 | 9b1c52afbb4ae131aae18b8031312cf3 | 8.2 | 设备硬装初始化-智算服务器 | 2 | c826c8feae238ad2bf303073abdfbb25 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 70 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD14 |  |  | 302-POD14
1670436 | 9b1cb51032f1a3235f66b35fa2c83899 | 8.6 | 智算硬件压测 | 2 | dee03de40e6fb41ce5b05d7994205898 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 63 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD30 |  |  | 301-POD30
1670004 | 9b6883d4e0efe6396323b9dfc44d9a35 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 2d2940d893d47b77b5ff6898b6a042c3 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 7 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD2 |  |  | 202-POD2
1670861 | 9b6abcc6a036097b11d2d599b8972102 | 8.13 | 计算子系统验证-灵衢网络 | 2 | ddf5a0337be203189f6d5c2d8a497dd6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 118 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD35 |  |  | 401-POD35
1670754 | 9bcef38bedce824477df007ad1108cb8 | 9.1 | 计算管理系统对接 | 2 | e1d4138c27a0d614c89732665fbeeb11 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 104 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD23 |  |  | 304-POD23
1670383 | 9be4cc2e3df8460ee912c00ad5362da2 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | a6a1e1a79c725060a83506cfdd0623ce | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 56 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670150 | 9d599b82d990e358483fff083849bcc7 | 8.2 | 设备硬装初始化-智算服务器 | 2 | f07be6ccb5484bc38067669a6864270c | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 26 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670392 | 9da6e2a0b69758833190ed852bb9d4bd | 9.2 | 网络管理系统对接 | 2 | a0aee0b212766d4ff35ba0eba7e331ec | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-15至2026-06-16进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-15 | 2026-06-16 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 57 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670660 | 9de75fe5ca7bb05ff3b0d39336489748 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 9865de96ab6bde557d2d2c58109fcc5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 92 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD24 |  |  | 304-POD24
1670814 | 9e102c4afd6d096bef42cfdbb6bf476f | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 553f764385d381145313cd0285178e0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 112 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 401-POD34 |  |  | 401-POD34
1670759 | 9eb7a2e4e3a6e3280ca7e83c148cb259 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | dd9464ecec8bdea6a13f134a3ad565e4 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 105 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD23 |  |  | 304-POD23
1670351 | 9f3890205a4e35396b31f95ecc6648ec | 8.6 | 智算硬件压测 | 2 | db2049f830177d2afeb9c4eeb4815b0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 52 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD11 |  |  | 204-POD11
1670613 | 9f70f66d1dfaf7868ccffd49c7967843 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | ca6bf767c2cb6de8211c420fc93e157e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 86 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD15 |  |  | 302-POD15
1670804 | 9fcc95e6bd4970cec1d53413a1fc13e2 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 553f764385d381145313cd0285178e0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 111 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD34 |  |  | 401-POD34
1670306 | a106eb70934cf3b182bdc9f832fb0b05 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | d87b31ab43bb926bd4a93efe50d8e464 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 46 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD28 |  |  | 201-POD28
1670684 | a12349a6f9e5f6d042061365cd703abd | 8.13 | 计算子系统验证-灵衢网络 | 2 | 251feb99813e3a248e5095c3f4955f56 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 95 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD19 |  |  | 303-POD19
1670512 | a190eca3dcb4076b4b6a234663e0ae78 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 24e3cdd2d57d17b0a366e2f5ead2d61e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 73 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD16 |  |  | 302-POD16
1670791 | a1ac7090b325b6c4df1f2ed8c091ef00 | 8.15 | 网络子系统验证 | 2 | 7e393e340b11a9213d7cde8165a81259 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-13至2026-06-15进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-13 | 2026-06-15 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 109 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670208 | a2ed8fd17bc9cab28094c9d465fb6491 | 9.1 | 计算管理系统对接 | 2 | 412980179649a354b3cbba0f444e37ab | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 33 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD12 |  |  | 204-POD12
1670390 | a3230007a9e04ac6f8cd4b185b72b599 | 8.7 | 网络子系统部署调测 | 2 | a6a1e1a79c725060a83506cfdd0623ce | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-10至2026-06-14进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-10 | 2026-06-14 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 57 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670329 | a408e0058bf75505b053fc078c9e1893 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 03ac3374406c6fe0e56bd97ed7c4daab | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 49 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD26 |  |  | 201-POD26
1670830 | a494ed480807a87cfc6c6a95382b8f23 | 8.12 | 计算子系统验证-智算服务器 | 2 | a018577ea7ff9ff374d57cc088d2fc37 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 114 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD36 |  |  | 401-POD36
1669999 | a4d2362d35632831dd9e658d6fcd8919 | 9.1 | 计算管理系统对接 | 2 | 0bbb767db3cd5ac0295f5b3637f9b733 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 6 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD2 |  |  | 202-POD2
1670273 | a50c45f075c4fd0c78dd19dee96ef805 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 18ca86273180d7644d99757367c6797d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 42 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670808 | a5c59d761b98f05aa50a78df3d8ecc07 | 9.1 | 计算管理系统对接 | 2 | 897fae2bca74f395686d9712ce9f0bf2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 111 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD34 |  |  | 401-POD34
1670805 | a645cf0572699e842ae2a201536e8c87 | 8.6 | 智算硬件压测 | 2 | 553f764385d381145313cd0285178e0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 111 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD34 |  |  | 401-POD34
1670712 | a6770ff807620184ceb3fb3605070e1f | 8.1 | 基础网络配置 | 2 | fd49155be495025405d25d7b173f6f39 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-06至2026-06-07进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-06 | 2026-06-07 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 99 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670159 | a6975dd7ae9b6013864653c434a18998 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | f07be6ccb5484bc38067669a6864270c | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 27 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670076 | a6a7241720e7ac86f1c42c851709ca54 | 9.1 | 计算管理系统对接 | 2 | 7039f51f358152c479ad5ab3ce112663 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 16 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD3 |  |  | 202-POD3
1670291 | a76545a15d9e9fa9356f8cbf76ad4402 | 8.15 | 网络子系统验证 | 2 | 18ca86273180d7644d99757367c6797d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-14至2026-06-16进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-14 | 2026-06-16 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 44 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1669997 | aaa6b8d385cf9b1012ea488b2278cd5d | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 2d2940d893d47b77b5ff6898b6a042c3 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 6 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD2 |  |  | 202-POD2
1670590 | aaaa551295a9c0b42df0ede34fd21933 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 05c3fff9227a16057f256f6f4453949e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 83 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD31 |  |  | 301-POD31
1670853 | ad5edb4727c906bbc8aa96fb01ab2312 | 8.12 | 计算子系统验证-智算服务器 | 2 | ddf5a0337be203189f6d5c2d8a497dd6 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 117 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD35 |  |  | 401-POD35
1670606 | aeb25720c3feda98b14d44d50d25cfa3 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | ca6bf767c2cb6de8211c420fc93e157e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 85 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD15 |  |  | 302-POD15
1670252 | b0320d67ee93c00063530200276c5c64 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 3b2c2588b3d1e76c61bb8a9291dd4870 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 39 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD4 |  |  | 202-POD4
1670636 | b04b6c54d58e94d44fb6eed070ccc10b | 8.5 | 设备硬装初始化-灵衢网络 | 2 | b426a0ce7dc8ae6f732421d0e26e6a5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 89 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD20 |  |  | 303-POD20
1670331 | b0913f9356fc5a48ef6f45de91b44b19 | 9.1 | 计算管理系统对接 | 2 | eaeb843e36a64e9601a439862cefe18e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 49 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD26 |  |  | 201-POD26
1670018 | b31e4c47f9117406b717d9aa93ddeec0 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 4943d29f93667ff572e188c2ac2b7fc8 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 9 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670654 | b4f2ff6ce3311157e9161a9c59d93b41 | 9.1 | 计算管理系统对接 | 2 | 8eeddaeff502435c6d4ed93cad8a2ae7 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 91 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD24 |  |  | 304-POD24
1670513 | b5b9aeafa6507504c2d7814a8995a350 | 8.6 | 智算硬件压测 | 2 | 24e3cdd2d57d17b0a366e2f5ead2d61e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 73 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD16 |  |  | 302-POD16
1670230 | b735572b708717a9c5c452d3dbf98f53 | 8.12 | 计算子系统验证-智算服务器 | 2 | 4b665118faff7bce4565ba27e63e51a2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 36 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD8 |  |  | 203-POD8
1669974 | b7dd9d637ed64cd222409e0ad2260829 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 61792c7944ed3393ae8abb6c3a4e1dd7 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD10 |  |  | 204-POD10
1670614 | b8d30e41b1c4c67daaaf75f8d031278d | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | ca6bf767c2cb6de8211c420fc93e157e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 86 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD15 |  |  | 302-POD15
1670034 | b9ad6c53466444d150b023d5c0ebad7e | 8.1 | 基础网络配置 | 2 | 4943d29f93667ff572e188c2ac2b7fc8 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-04至2026-06-05进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-04 | 2026-06-05 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 11 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1669975 | b9b446f1874618ea70eaccabfde806cb | 8.12 | 计算子系统验证-智算服务器 | 2 | 61792c7944ed3393ae8abb6c3a4e1dd7 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD10 |  |  | 204-POD10
1670582 | ba3a3268359907ea424a4c7107911a41 | 8.6 | 智算硬件压测 | 2 | 05c3fff9227a16057f256f6f4453949e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 82 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD31 |  |  | 301-POD31
1670435 | ba402ca22204d8edb989f377b03cd2d4 | 8.2 | 设备硬装初始化-智算服务器 | 2 | dee03de40e6fb41ce5b05d7994205898 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 63 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD30 |  |  | 301-POD30
1670627 | bbcff6f2f5131da7a2bea55f342c35ac | 8.2 | 设备硬装初始化-智算服务器 | 2 | b426a0ce7dc8ae6f732421d0e26e6a5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 88 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD20 |  |  | 303-POD20
1670774 | bc2528eed4637923b8b9109e2908569d | 8.6 | 智算硬件压测 | 2 | 7e393e340b11a9213d7cde8165a81259 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 107 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670305 | bc929943028efadd0af22fd221612c3b | 8.6 | 智算硬件压测 | 2 | d87b31ab43bb926bd4a93efe50d8e464 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 46 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD28 |  |  | 201-POD28
1670615 | bcb6ad8dac74d70adfae3d1ac1b62056 | 8.13 | 计算子系统验证-灵衢网络 | 2 | ca6bf767c2cb6de8211c420fc93e157e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 86 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD15 |  |  | 302-POD15
1670872 | bdbbd9567444a3b7ea57f1062b908843 | 12.2 | 输出验收报告 | 2 | 2c2746963b3a0c69e85497f95577de1b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-07-21至2026-07-25进行输出验收报告活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-07-21 | 2026-07-25 |  |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 |  | { "device_list": [] } |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36 |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36
1670661 | bddc34de6c248d2ffc3b110ec5371aeb | 8.13 | 计算子系统验证-灵衢网络 | 2 | 9865de96ab6bde557d2d2c58109fcc5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 92 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD24 |  |  | 304-POD24
1670376 | bebf1403022cffc6d80dc2d4c75b6c4b | 8.12 | 计算子系统验证-智算服务器 | 2 | a6a1e1a79c725060a83506cfdd0623ce | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 55 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670737 | bf5547e986372c29b771f4f58041dcec | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 103ca18ba6bf0c3ba090a402745158f5 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 102 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD22 |  |  | 304-POD22
1670229 | c03d6499b6c2ea8e8fbcef4345744c02 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 4b665118faff7bce4565ba27e63e51a2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 36 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD8 |  |  | 203-POD8
1670868 | c1a0bc1bd8621d51d655a98d07ba794f | 9.6 | 集群通信配置测试 | 2 | e29f1d8756ba3935d4d6a08313e40743 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-07-04至2026-07-05进行集群通信配置测试活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 432, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-07-04 | 2026-07-05 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 |  | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 1728, "unit": "台" } ] } |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36 |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36
1670251 | c2e639c8c6cb2cc19d8b4bbb7248d8f4 | 8.6 | 智算硬件压测 | 2 | 3b2c2588b3d1e76c61bb8a9291dd4870 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 39 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD4 |  |  | 202-POD4
1670168 | c370e5d5906ccc6ca2de8c5a28f4e899 | 8.15 | 网络子系统验证 | 2 | f07be6ccb5484bc38067669a6864270c | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-15至2026-06-17进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-15 | 2026-06-17 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 28 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } |  |  | 202-POD1 |  |  | 202-POD1
1670137 | c48e1f6fd6f7d022af57320adb2b43b4 | 8.15 | 网络子系统验证 | 2 | f55d7830292083df19382d92eb48d9d1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-13至2026-06-15进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-13 | 2026-06-15 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 24 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670522 | c4c48ade4d2dc508b2417fe2b2e943ec | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 24e3cdd2d57d17b0a366e2f5ead2d61e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 74 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD16 |  |  | 302-POD16
1670874 | c4c5e46881d8540da684da932771fcfa | 12.4 | 移交 | 2 | 2c2746963b3a0c69e85497f95577de1b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-07-29至2026-07-30进行移交活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-07-29 | 2026-07-30 |  |  | 待接收 | 0% | 秦云鹭 00821049 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 |  | { "device_list": [] } |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36 |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36
1670289 | c4ff47df8a7c2f185331d755b77457a8 | 8.1 | 基础网络配置 | 2 | 18ca86273180d7644d99757367c6797d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-07至2026-06-08进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-07 | 2026-06-08 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 44 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 32, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 2, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670545 | c50873f2066b29387a8c806a0044182c | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 18a4041ec1b2f6ab8822aa3a68e26789 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 77 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD32 |  |  | 301-POD32
1670028 | c593df28408f8319320feb0c8158a7a9 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 4943d29f93667ff572e188c2ac2b7fc8 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 10 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670683 | c598725f2146cf11b6f90c444c0d0deb | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 251feb99813e3a248e5095c3f4955f56 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 95 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD19 |  |  | 303-POD19
1670870 | c5e41d74998977338c0b9aaaa4bf9b15 | 9.8 | 集群性能调优 | 2 | e29f1d8756ba3935d4d6a08313e40743 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-07-11至2026-07-13进行集群性能调优活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-07-11 | 2026-07-13 |  |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 |  | { "device_list": [] } |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36 |  |  | 201-POD25,201-POD26,201-POD27,201-POD28,202-POD1,202-POD2,202-POD3,202-POD4,203-POD5,203-POD6,203-POD7,203-POD8,204-POD9,204-POD10,204-POD11,204-POD12,301-POD29,301-POD30,301-POD31,301-POD32,302-POD13,302-POD14,302-POD15,302-POD16,303-POD17,303-POD18,303-POD19,303-POD20,304-POD21,304-POD22,304-POD23,304-POD24,401-POD33,401-POD34,401-POD35,401-POD36
1670408 | c85e288d61d0fe44884539427bbbbd55 | 9.1 | 计算管理系统对接 | 2 | 9aaf1fb8521f3bd14a8493c72ed04ff1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 59 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD29 |  |  | 301-POD29
1670714 | c87607b2e12e8030aea501f1d8dc9f12 | 8.15 | 网络子系统验证 | 2 | fd49155be495025405d25d7b173f6f39 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-13至2026-06-15进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-13 | 2026-06-15 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 99 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670081 | c9c75be97cae78297a0a037f301c6b74 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 2a5d2b339c9e5d555058e266671d1f5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 17 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD3 |  |  | 202-POD3
1670277 | c9d0a8bb85b114661ea3b4ecb76bee45 | 9.1 | 计算管理系统对接 | 2 | 56b24380af50623a9af24dd5fd905643 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 42 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670538 | ca196b7ac78a42920970c5520c83639a | 8.12 | 计算子系统验证-智算服务器 | 2 | 18a4041ec1b2f6ab8822aa3a68e26789 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 76 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD32 |  |  | 301-POD32
1670051 | cb515960fd4cf5f0dc52965640b13cdb | 8.8 | 计算子系统部署调测-智算服务器 | 2 | f6554bcb6c45099802bd0f92dca5750a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 13 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD27 |  |  | 201-POD27
1670282 | ccf74661f035cd3f3e5d80ccdf79b14f | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 18ca86273180d7644d99757367c6797d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 43 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670697 | cd2bb82bea917e3b8f3ae2013865fb9e | 8.6 | 智算硬件压测 | 2 | fd49155be495025405d25d7b173f6f39 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 97 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670445 | cd2e86c302a9fca6173f844e2a82afd7 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | dee03de40e6fb41ce5b05d7994205898 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 64 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD30 |  |  | 301-POD30
1670698 | cd68c4e4a60a250cb259c38b91f1ef18 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | fd49155be495025405d25d7b173f6f39 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 97 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1669982 | cd71e008ef58de21851255154663ccd1 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 61792c7944ed3393ae8abb6c3a4e1dd7 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 4 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD10 |  |  | 204-POD10
1670792 | cdcb818c74a0bc70e5f2b2c2fb313615 | 9.2 | 网络管理系统对接 | 2 | cd456b489e3ea99ad91599724f007b30 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-13至2026-06-14进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-13 | 2026-06-14 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 109 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670097 | ce8a37284cad8d3e810270e6c64e4f76 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | c897a07909985ce10d9a5b747aee076a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD6 |  |  | 203-POD6
1670806 | d1e9281acc3e50f8a7aaf79b80df5397 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 553f764385d381145313cd0285178e0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 111 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD34 |  |  | 401-POD34
1670254 | d2587cff7e4f20042865a5905626f62b | 9.1 | 计算管理系统对接 | 2 | eefd7e6cc5a2e16a28a3481344f72534 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 39 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD4 |  |  | 202-POD4
1670231 | d3436390c87e6e280d4026127d206016 | 9.1 | 计算管理系统对接 | 2 | 4df8dbf5aef257ba9532463b59c6ce27 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 36 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD8 |  |  | 203-POD8
1670807 | d54a53cf982c9ad379bf7e8a7d70639d | 8.12 | 计算子系统验证-智算服务器 | 2 | 553f764385d381145313cd0285178e0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 111 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 401-POD34 |  |  | 401-POD34
1670516 | d5f80971a1e85db35418964fa87e6591 | 9.1 | 计算管理系统对接 | 2 | b6d6daa55d47cc1f969a1bb769db40b1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 73 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD16 |  |  | 302-POD16
1670353 | d713bcdb5cab052f7ab66385c61e63d2 | 8.12 | 计算子系统验证-智算服务器 | 2 | db2049f830177d2afeb9c4eeb4815b0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 52 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD11 |  |  | 204-POD11
1670382 | d7918f59ff484522729f598bb7419a47 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | a6a1e1a79c725060a83506cfdd0623ce | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 56 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670652 | d7fcf84e35272c8ef1aeb7d0d24dd546 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 9865de96ab6bde557d2d2c58109fcc5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:58 | 91 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD24 |  |  | 304-POD24
1670790 | d9454b8fd166c3ee7e58629811608aae | 8.7 | 网络子系统部署调测 | 2 | 7e393e340b11a9213d7cde8165a81259 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-08至2026-06-12进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-08 | 2026-06-12 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:58 | 109 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 401-POD33 |  |  | 401-POD33
1670099 | d97d9e40ac31cab790dcbc7f948207ef | 9.1 | 计算管理系统对接 | 2 | 70f7ce768b97376414baadfdd137b190 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD6 |  |  | 203-POD6
1670082 | dc8903d43450edb0e69a96853aa24dde | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 2a5d2b339c9e5d555058e266671d1f5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 17 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 202-POD3 |  |  | 202-POD3
1670330 | dcd9f2687c504581a659203cc7643201 | 8.12 | 计算子系统验证-智算服务器 | 2 | 03ac3374406c6fe0e56bd97ed7c4daab | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:47 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 49 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD26 |  |  | 201-POD26
1670060 | dde273d234b14f298f3b44e262e20a7c | 8.13 | 计算子系统验证-灵衢网络 | 2 | f6554bcb6c45099802bd0f92dca5750a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:58 | 14 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD27 |  |  | 201-POD27
1670098 | df170cf6894b5a13cb446548c17e1009 | 8.12 | 计算子系统验证-智算服务器 | 2 | c897a07909985ce10d9a5b747aee076a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:58 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD6 |  |  | 203-POD6
1670608 | e26e9f69432c97b23502596f5a7c5e66 | 9.1 | 计算管理系统对接 | 2 | 53f6b0c6d41144affadb6921f971515e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 85 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 302-POD15 |  |  | 302-POD15
1670751 | e3681f8f50fa946cf768ffcecc34724d | 8.6 | 智算硬件压测 | 2 | dd9464ecec8bdea6a13f134a3ad565e4 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:59 | 104 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD23 |  |  | 304-POD23
1670120 | e41834abd16e1797afe7dffdc3b18527 | 8.6 | 智算硬件压测 | 2 | f55d7830292083df19382d92eb48d9d1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 22 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670458 | e57af3fad460231249f54ea57f1be67c | 8.2 | 设备硬装初始化-智算服务器 | 2 | 62832bb134c8624ef9c070316b881967 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 66 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670384 | e76962a9ef3f4623313b5caabcd16278 | 8.13 | 计算子系统验证-灵衢网络 | 2 | a6a1e1a79c725060a83506cfdd0623ce | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 56 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670736 | e7d907e67a5ae5f22484d2323024e098 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 103ca18ba6bf0c3ba090a402745158f5 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:59 | 102 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD22 |  |  | 304-POD22
1670628 | e84208df3259da9e409f7a12fd9fa261 | 8.6 | 智算硬件压测 | 2 | b426a0ce7dc8ae6f732421d0e26e6a5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 88 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD20 |  |  | 303-POD20
1670228 | e9dab7975ac19dbd54fa97d19fb33e71 | 8.6 | 智算硬件压测 | 2 | 4b665118faff7bce4565ba27e63e51a2 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 36 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD8 |  |  | 203-POD8
1670250 | ea9eddded3d1df29baf6d691748c80e1 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 3b2c2588b3d1e76c61bb8a9291dd4870 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 39 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD4 |  |  | 202-POD4
1669996 | ebaa528be35545939f186d455415f23a | 8.6 | 智算硬件压测 | 2 | 2d2940d893d47b77b5ff6898b6a042c3 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:59 | 6 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 202-POD2 |  |  | 202-POD2
1670460 | ebc94477da058072884b921507b52d4a | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 62832bb134c8624ef9c070316b881967 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 66 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD17 |  |  | 303-POD17
1670182 | ec42586446c77ae1fabac1409fe1444b | 8.6 | 智算硬件压测 | 2 | d39b2ce315888c23aa46daedfdb03e98 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 30 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD7 |  |  | 203-POD7
1670715 | ec5904b0a137b8707a4236c2efcd2ec8 | 9.2 | 网络管理系统对接 | 2 | 9502882d3c10e8f176a29bd2deb5be15 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-13至2026-06-14进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-13 | 2026-06-14 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:59 | 99 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670544 | ec6cb09b486e9ff5b1ab29d3c81c3581 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 18a4041ec1b2f6ab8822aa3a68e26789 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 77 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD32 |  |  | 301-POD32
1670128 | ed5e425333a882a05b551b8a7390f0c8 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | f55d7830292083df19382d92eb48d9d1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 23 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670391 | edde66a4f795d6f32a48704b71a5783d | 8.15 | 网络子系统验证 | 2 | a6a1e1a79c725060a83506cfdd0623ce | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-15至2026-06-17进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-15 | 2026-06-17 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 57 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" }, { "device_model": "CE9855", "quantity": 40, "unit": "台" }, { "device_model": "CE9860", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "CE6857", "quantity": 1, "unit": "台" } ] } |  |  | 302-POD13 |  |  | 302-POD13
1670275 | ef77fd3fd0e3dfd3eb52d58a6b021a2c | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 18ca86273180d7644d99757367c6797d | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 42 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 203-POD5 |  |  | 203-POD5
1670674 | ef81e389d02587b99067880175380aac | 8.6 | 智算硬件压测 | 2 | 251feb99813e3a248e5095c3f4955f56 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:59 | 94 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD19 |  |  | 303-POD19
1670313 | eff0ee6df91fb04b4d771579dd6780c2 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | d87b31ab43bb926bd4a93efe50d8e464 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 47 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD28 |  |  | 201-POD28
1670584 | f091d8241207a3231d4bf1df2f893b08 | 8.12 | 计算子系统验证-智算服务器 | 2 | 05c3fff9227a16057f256f6f4453949e | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 82 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 301-POD31 |  |  | 301-POD31
1670546 | f0e27a79912a6affcfe7099b3375867f | 8.13 | 计算子系统验证-灵衢网络 | 2 | 18a4041ec1b2f6ab8822aa3a68e26789 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 77 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 301-POD32 |  |  | 301-POD32
1670560 | f158c3e752f26d2dca33f1b9087a847a | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 9546c58cc8fbce8dfa4c3446148e3386 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 79 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD18 |  |  | 303-POD18
1670360 | f1c9af33823b18010fc759f3520963da | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | db2049f830177d2afeb9c4eeb4815b0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 53 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 204-POD11 |  |  | 204-POD11
1670558 | f3174c0ab36f6a11ac2d1db2ed24ce11 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 9546c58cc8fbce8dfa4c3446148e3386 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 79 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD18 |  |  | 303-POD18
1670350 | f500cb650ce97fe2573a99ce0e4a13c4 | 8.2 | 设备硬装初始化-智算服务器 | 2 | db2049f830177d2afeb9c4eeb4815b0b | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 52 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD11 |  |  | 204-POD11
1670696 | f5a58af27ffc7e1b8722fb4feaaf1e21 | 8.2 | 设备硬装初始化-智算服务器 | 2 | fd49155be495025405d25d7b173f6f39 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-20至2026-06-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-20 | 2026-06-21 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:59 | 97 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670568 | f6e7f466b838056b44567727448d7364 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 9546c58cc8fbce8dfa4c3446148e3386 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 80 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 303-POD18 |  |  | 303-POD18
1670315 | f7958b40ab91b6fc49ec96d7d00efc0f | 8.13 | 计算子系统验证-灵衢网络 | 2 | d87b31ab43bb926bd4a93efe50d8e464 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 47 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD28 |  |  | 201-POD28
1670707 | f8a973a0f6203963cee7a28e5b940fa7 | 8.13 | 计算子系统验证-灵衢网络 | 2 | fd49155be495025405d25d7b173f6f39 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:59 | 98 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670020 | f8f48cfd34223e58141fe477ad9114a7 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 4943d29f93667ff572e188c2ac2b7fc8 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:59 | 9 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670035 | f9048a43c83e192f867056547325aa47 | 8.7 | 网络子系统部署调测 | 2 | 4943d29f93667ff572e188c2ac2b7fc8 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-06至2026-06-10进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-06 | 2026-06-10 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:59 | 11 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 204-POD9 |  |  | 204-POD9
1670700 | f922ab7e686553472bbeedbecf557df6 | 9.1 | 计算管理系统对接 | 2 | 9502882d3c10e8f176a29bd2deb5be15 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-28 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:59 | 97 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD21 |  |  | 304-POD21
1670629 | fa34e6e0d8ef13bea42bedf976373385 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | b426a0ce7dc8ae6f732421d0e26e6a5f | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:16 | z00933673 | 2026-06-04 10:59 | 88 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 303-POD20 |  |  | 303-POD20
1670050 | fbd7ae28d0f4b2ad47e43ae3e8f35a12 | 8.6 | 智算硬件压测 | 2 | f6554bcb6c45099802bd0f92dca5750a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:59 | 13 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 201-POD27 |  |  | 201-POD27
1670136 | fca51f0a68d751ca428a2be33988be69 | 8.7 | 网络子系统部署调测 | 2 | f55d7830292083df19382d92eb48d9d1 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-08至2026-06-12进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-06-08 | 2026-06-12 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 24 | { "device_list": [ { "device_model": "CE8875", "quantity": 16, "unit": "台" }, { "device_model": "CE16800-X4", "quantity": 24, "unit": "台" }, { "device_model": "S5736", "quantity": 8, "unit": "台" }, { "device_model": "S5736", "quantity": 1, "unit": "台" }, { "device_model": "S5736", "quantity": 2, "unit": "台" }, { "device_model": "S5736", "quantity": 12, "unit": "台" } ] } |  |  | 201-POD25 |  |  | 201-POD25
1670338 | fee0dfe704f22e904f2344b0a502688c | 8.13 | 计算子系统验证-灵衢网络 | 2 | 03ac3374406c6fe0e56bd97ed7c4daab | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-27至2026-06-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-27 | 2026-06-29 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:15 | z00933673 | 2026-06-04 10:59 | 50 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD26 |  |  | 201-POD26
1670728 | fef0bd2a1be5f891fec2397f7b10871e | 8.6 | 智算硬件压测 | 2 | 103ca18ba6bf0c3ba090a402745158f5 | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:17 | z00933673 | 2026-06-04 10:59 | 101 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  |  | 304-POD22 |  |  | 304-POD22
1670059 | ff23f030a7719aae4b366c004f68580c | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | f6554bcb6c45099802bd0f92dca5750a | d468a3659a8243feab7bb51af7e584f6 | 项目编码 ，项目名称 F1项目 for skill，请从2026-06-22至2026-06-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-06-22 | 2026-06-26 | 2026-05-14 11:48 |  | 待接收 | 0% | 胡德华 00643479 | 华为 |  | z00933673 | 2026-05-14 11:14 | z00933673 | 2026-06-04 10:59 | 14 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  |  | 201-POD27 |  |  | 201-POD27