## sheet0
ID | TODO_ID | SERIAL_NUMBER | ACTIVITY_ID | ACTIVITY_NAME | TASK_RANK | PARENT_ID | PROJECT_ID | INSTRUCTION | FORMAT_INSTRUCTION | SRC_AGENT | TARGET_AGENT | START_DATE | END_DATE | ACTUAL_START_DATE | ACTUAL_END_DATE | STATUS | PROCESS | PRINCIPAL | PRINCIPAL_COMPANY | SCENARIO | CREATED_BY | CREATION_DATE | LAST_UPDATE_BY | LAST_UPDATE_DATE | group_id | RAW_EQUIPMENT_LIST | TASK_COMMENT | MANAGEMENT_UNIT | OWNER | MANUAL_PROCESS | REAL_MANAGEMENT_UNIT
49767 |  | 00213f32bd359e146829c8b6e81e054d | 8.0 | 单机调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-29进行单机调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-14 00:00:00 | 2026-01-29 00:00:00 | 2026-01-18 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 09:52:29 |  | { "device_list": [] } |  | B2DH401-POD03 |  | 100%
49664 |  | 02d6bda93e6686fa5474414cf691e4d9 | 6.9 | 网络到货（含开箱验货） | 2 | 15225ba7ad316e6a0f70b2424fcabe1c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行网络到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-07 00:00:00 | 2026-03-07 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-10 10:10:11 | 17 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49632 |  | 02f387b30a7c79190bff5ddac18bf559 | 8.13 | 计算子系统验证-灵衢网络 | 2 | b5f402b29414deadb16f17861def8194 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 2026-01-30 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:35:17 | 12 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49764 |  | 02fa9b1f273b66ab83ce827eb6b3d9ec | 9.2 | 网络管理系统对接 | 2 | b54bba420a74d18a9f17858c109c828e | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-22进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-21 00:00:00 | 2026-01-25 00:00:00 | 2026-01-25 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 09:52:40 | 29 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49776 |  | 038574401cdf742976565a3310a36281 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 7a21404db97a2a7184547a95c4f4a28c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-10进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 2026-03-22 00:00:00 | 2026-03-23 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-22 23:51:54 | 31 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49619 |  | 04aedc7f8b9830d1225e5562ed85b435 | 7.20 | 液冷计算柜设备上电 | 2 | 39f755adca700a886f962ce3bac181bc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-19进行液冷计算柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-21 00:00:00 | 2026-01-23 00:00:00 | 2026-01-24 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-01-27 00:00:00 | 11 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49645 |  | 062746fa7309305dee7e8a82a1c814be | 6.5 | 灵衢线缆到货（含开箱验货） | 2 | 15225ba7ad316e6a0f70b2424fcabe1c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-05进行灵衢线缆到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-05 00:00:00 | 2026-01-08 00:00:00 | 2026-01-08 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 10:10:11 | 14 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH402-POD06 |  | 100%
49722 |  | 06c2be3574a153b0f2fda59f9521649d | 7.24 | 总线设备柜验收 | 2 | 5711bf7d585084aa21011f8708cc8f26 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-15进行总线设备柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-18 00:00:00 | 2026-03-24 00:00:00 | 2026-03-23 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-15 20:46:19 | 24 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49803 |  | 0898a3efc35da9b45561c14e2d67c220 | 6.11 | 转运与设备静置 | 2 | 4f1622107208a82e5379e84235c8076b | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-19至2026-01-19进行转运与设备静置活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-19 00:00:00 | 2026-01-19 00:00:00 | 2026-01-21 00:00:00 | 2026-01-21 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-01-21 00:00:00 | 35 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49822 |  | 08dccb6cce7f1fea1ffa92cf489a08b1 | 7.15 | 网络设备硬件验收 | 2 | 668de380b2c306cc4b6644ee75fe4ef9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-22进行网络设备硬件验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-22 00:00:00 | 2026-01-22 00:00:00 | 2026-01-24 00:00:00 | 2026-01-24 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:41:18 | 37 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49644 |  | 097cb011d565cd09f42c3de80111c703 | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-28进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-27 00:00:00 | 2026-01-24 00:00:00 | 2026-01-30 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:35:47 |  | { "device_list": [] } |  | B2DH401-POD02
49673 |  | 0a42ee3f371d80abc73b66a46d67254f | 7.0 | 工程安装 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-02至2026-03-15进行工程安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2025-12-02 00:00:00 | 2026-03-24 00:00:00 | 2025-12-05 00:00:00 | 2026-03-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-15 20:44:49 |  | { "device_list": [] } |  | B2DH402-POD06 |  | 100%
49726 |  | 0abd82fab748ca23976474787cc37b61 | 6.9 | 网络到货（含开箱验货） | 2 | 974f1dbc336d0a548d8c0446ef1588c7 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行网络到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-09 00:00:00 | 2026-03-09 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-10 09:57:19 | 25 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49569 |  | 0abe8ecf1253bd8aaba6bd09e8e23a3e | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | d67315c919da4515dcd27f7f8cee0fd4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-26 00:00:00 | 2026-01-26 00:00:00 | 2026-01-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 08:31:34 | 4 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49599 |  | 0aeecdd49d5f72db3c8a6789f864aedb | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 2026-01-27 00:00:00 | 2026-01-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:53:32 | 8 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49797 |  | 0d2365c84de5c6fbd95cb5b915b11daf | 7.0 | 工程安装 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-02至2026-03-15进行工程安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2025-12-02 00:00:00 | 2026-03-24 00:00:00 | 2025-12-06 00:00:00 | 2026-03-28 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-15 20:45:39 |  | { "device_list": [] } |  | B2DH402-POD07
49545 |  | 0d6fa684666ea5480291b142a9e7233d | 5.6 | 集群验收方案设计 | 2 | 9d902ce7baa85aa0b3573c7dc4634011 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-28至2026-01-01进行集群验收方案设计活动，确保低阶设计顺利进行。 | { "device_list": [] } | manage_agent | design_agent | 2025-12-28 00:00:00 | 2026-01-01 00:00:00 | 2025-12-30 00:00:00 | 2026-01-03 00:00:00 | 已完成 | 100% | 张杨 00543862 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:46:36 |  | { "device_list": [] } |  |  |  | 100%
49583 |  | 0de0adb1bd5b68a3fa61e00f733b825a | 6.5 | 灵衢线缆到货（含开箱验货） | 2 | b42abb2c92f1b1889620005fbc34448d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-05进行灵衢线缆到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-05 00:00:00 | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:52:49 | 6 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH401-POD04 |  | 100%
49595 |  | 0f2ab39d2842b45f17df496f6d12b4a5 | 6.3 | 总线设备柜到货（含开箱验货） | 2 | b42abb2c92f1b1889620005fbc34448d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行总线设备柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-15 00:00:00 | 2026-01-15 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:52:53 | 8 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49705 |  | 0f8cc620095af38d62109166a5af7bc4 | 8.0 | 单机调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-18进行单机调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-08 00:00:00 | 2026-03-27 00:00:00 | 2026-03-10 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-04-02 19:12:44 |  | { "device_list": [] } |  | B2DH402-POD05 |  | 100%
49862 |  | 101a6de57d32e63d5bb5c737a2136aa5 | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-04-01进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-04-01 00:00:00 | 2026-03-30 00:00:00 | 2026-04-06 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-02 19:16:45 |  | { "device_list": [] } |  | B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08 |  | 100%
49591 |  | 11a35234efef4d39f2cdb71d419ae29e | 8.6 | 智算硬件压测 | 2 | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-28 00:00:00 | 2026-01-29 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:53:48 | 7 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49670 |  | 1289c48aea06274b694f93de96e1c808 | 8.15 | 网络子系统验证 | 2 | fe360f4b58153382f33ce7e61e7e0db5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-17进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-17 00:00:00 | 2026-03-18 00:00:00 | 2026-03-20 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-22 23:54:34 | 17 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49618 |  | 12b7aa298287f6fe24baef2611762fc0 | 7.19 | 液冷计算柜安装 | 2 | 39f755adca700a886f962ce3bac181bc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-12进行液冷计算柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 2026-01-15 00:00:00 | 2026-01-15 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 08:34:37 | 11 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49704 |  | 130bd396a173514f6052d60408189852 | 7.0 | 工程安装 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-02至2026-03-15进行工程安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2025-12-02 00:00:00 | 2026-03-24 00:00:00 | 2025-12-04 00:00:00 | 2026-03-26 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-15 20:43:41 |  | { "device_list": [] } |  | B2DH402-POD05
49707 |  | 1339837740fcd87711710f7beb763d82 | 6.5 | 灵衢线缆到货（含开箱验货） | 2 | 974f1dbc336d0a548d8c0446ef1588c7 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-05进行灵衢线缆到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-05 00:00:00 | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-10 09:56:55 | 22 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH402-POD08 |  | 100%
49671 |  | 13474beeb9d085d904f7d260d1c146c4 | 9.2 | 网络管理系统对接 | 2 | 30007f6ecaa7d88df89066d8ba4b0173 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-16进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-16 00:00:00 | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-04-02 19:13:47 | 17 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49538 |  | 13e77ff566a327d6581954b8b4d63306 | 4.2 | 建模仿真设计 | 2 | 2866389ea55269ba184f0b54b2386005 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-21至2025-12-25进行建模仿真设计活动，确保建模仿真顺利进行。 | { "device_list": [] } | manage_agent | simulation_agent | 2025-12-21 00:00:00 | 2025-12-25 00:00:00 | 2025-12-23 00:00:00 | 2025-12-27 00:00:00 | 已完成 | 100% | 李佳蒴 60094644 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:46:21 |  | { "device_list": [] } |  |  |  | 100%
49736 |  | 150290f605b7b9c11fb814eb2fa4cb3f | 8.0 | 单机调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-18进行单机调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-08 00:00:00 | 2026-03-27 00:00:00 | 2026-03-13 00:00:00 | 2026-04-01 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-04-02 19:15:13 |  | { "device_list": [] } |  | B2DH402-POD08 |  | 100%
49672 |  | 15225ba7ad316e6a0f70b2424fcabe1c | 6.0 | 到货 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-03-05进行到货活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-03-05 00:00:00 | 2026-01-08 00:00:00 | 2026-03-08 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-10 10:10:11 |  | { "device_list": [] } |  | B2DH402-POD06 |  | 100%
49563 |  | 15cb5300cd0d4f7c073f316b5b4a1a3e | 9.1 | 计算管理系统对接 | 2 | c7f11a1dd31dbdf48ee2751e8335e861 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 2026-01-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 08:33:28 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49843 |  | 15fd2ca2679ffd92354ccb6af5b21351 | 9.5 | 综合布线整改 | 2 | f9ac2503e56fa2240efefcc3aba5828a | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-02至2026-02-05进行综合布线整改活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-01-28 00:00:00 | 2026-01-28 00:00:00 | 2026-01-30 00:00:00 | 2026-01-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 09:59:29 |  | { "device_list": [] } |  | B2DH403-POD09 |  | 100%
49750 |  | 169501cbb620f4b1644305bdc4b11444 | 6.3 | 总线设备柜到货（含开箱验货） | 2 | e4ce39e2aff0d3dd2cfa93d47331d18e | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行总线设备柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 08:36:01 | 28 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49834 |  | 18991d59341d404cb256469de416be50 | 9.7 | 集群系统集成测试 | 2 | f502cd626d2334d82791f460952855ff | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-05至2026-02-09进行集群系统集成测试活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 48, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-31 00:00:00 | 2026-01-31 00:00:00 | 2026-02-05 00:00:00 | 2026-02-05 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 10:08:24 |  | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 192, "unit": "台" } ] } |  | B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04 |  | 100%
49790 |  | 19fc2cd5eb3f69f167371f44313bb964 | 7.14 | 网络设备上电 | 2 | 0d2365c84de5c6fbd95cb5b915b11daf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-07进行网络设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-07 00:00:00 | 2026-03-10 00:00:00 | 2026-03-11 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-22 00:00:00 | 33 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49866 |  | 1a5f9192fb74861bc06e54102c144d9f-B2DH401-POD02 | 9.8-B2DH401-POD02 | 集群性能调优 | 2 | f502cd626d2334d82791f460952855ff | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-10至2026-02-12进行集群性能调优活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-01 00:00:00 | 2026-02-01 00:00:00 | 2026-02-04 00:00:00 | 2026-02-04 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-02-05 00:00:00 |  | { "device_list": [] } |  | B2DH401-POD02 |  | 100%
49867 |  | 1a5f9192fb74861bc06e54102c144d9f-B2DH401-POD03 | 9.8-B2DH401-POD03 | 集群性能调优 | 2 | f502cd626d2334d82791f460952855ff | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-10至2026-02-12进行集群性能调优活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-01 00:00:00 | 2026-02-01 00:00:00 | 2026-02-05 00:00:00 | 2026-02-05 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-02-06 00:00:00 |  | { "device_list": [] } |  | B2DH401-POD03 |  | 100%
49868 |  | 1a5f9192fb74861bc06e54102c144d9f-B2DH401-POD04 | 9.8-B2DH401-POD04 | 集群性能调优 | 2 | f502cd626d2334d82791f460952855ff | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-10至2026-02-12进行集群性能调优活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-01 00:00:00 | 2026-02-01 00:00:00 | 2026-02-06 00:00:00 | 2026-02-06 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-02-07 00:00:00 |  | { "device_list": [] } |  | B2DH401-POD04 |  | 100%
49799 |  | 1a7cd43a16f5a52df8b8948fed1de43b | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-17进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-26 00:00:00 | 2026-03-19 00:00:00 | 2026-03-30 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-04-02 19:14:40 |  | { "device_list": [] } |  | B2DH402-POD07
49533 |  | 1b565bcc58e2c34c945556da01b5f0a9 | 3.1 | 现场勘测 | 2 | a5509dbfc0ddd88c2b793fbec3a55cbe | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-17至2025-12-19进行现场勘测活动，确保工程勘测顺利进行。 | { "device_list": [] } | manage_agent | survey_agent | 2025-12-17 00:00:00 | 2025-12-19 00:00:00 | 2025-12-19 00:00:00 | 2025-12-21 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:45:21 |  | { "device_list": [] } |  |  |  | 100%
49585 |  | 1b81b09b28c5445543f41ba3a94ae95b | 6.2 | 计算柜到货（含开箱验货） | 2 | b42abb2c92f1b1889620005fbc34448d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行计算柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-15 00:00:00 | 2026-01-15 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:52:58 | 7 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49564 |  | 1ce576afb892faeee4e0e4e6f9a32e96 | 6.3 | 总线设备柜到货（含开箱验货） | 2 | f52853c9677b1938411df3cedf812acc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行总线设备柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:47:07 | 4 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49681 |  | 1d1f69dc313fbb3fae083d98f25e89db | 7.20 | 液冷计算柜设备上电 | 2 | 130bd396a173514f6052d60408189852 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-07至2026-03-08进行液冷计算柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-16 00:00:00 | 2026-03-17 00:00:00 | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-20 00:00:00 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49719 |  | 1db3a2d112d1b5d25285c9f42cc97b40 | 6.3 | 总线设备柜到货（含开箱验货） | 2 | 974f1dbc336d0a548d8c0446ef1588c7 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行总线设备柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-09 00:00:00 | 2026-03-09 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-10 09:57:02 | 24 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49587 |  | 1e8d520f7a22e55333d633efd3afbdbc | 7.19 | 液冷计算柜安装 | 2 | 92d8f9e053e5c6293b513d9bfef0b492 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-12进行液冷计算柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 2026-01-17 00:00:00 | 2026-01-17 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:42:43 | 7 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49578 |  | 1ef878decc89977c8527d4037b5a02b2 | 9.2 | 网络管理系统对接 | 2 | c7f11a1dd31dbdf48ee2751e8335e861 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-22进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-21 00:00:00 | 2026-01-23 00:00:00 | 2026-01-23 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 08:33:23 | 5 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49691 |  | 1f985c94171262b6d52ea961a5e92533 | 7.24 | 总线设备柜验收 | 2 | 130bd396a173514f6052d60408189852 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-15进行总线设备柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-18 00:00:00 | 2026-03-24 00:00:00 | 2026-03-20 00:00:00 | 2026-03-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-15 20:43:20 | 20 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49714 |  | 210f7136841ce4440d11f83af2eb8359 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 150290f605b7b9c11fb814eb2fa4cb3f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-10进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 2026-03-23 00:00:00 | 2026-03-24 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-22 23:51:58 | 23 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49727 |  | 219ea64fc2ea2f4370ae1f0e7202a64e | 7.13 | 网络设备安装 | 2 | 5711bf7d585084aa21011f8708cc8f26 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-05至2026-03-05进行网络设备安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-05 00:00:00 | 2026-03-05 00:00:00 | 2026-03-10 00:00:00 | 2026-03-10 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-10 09:57:30 | 25 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49817 |  | 2410a8f0f57de8209ac946a81df8e439 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | dc4fd9bf53efce590628780fd29f44a8 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-25至2026-01-29进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-25 00:00:00 | 2026-01-25 00:00:00 | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:42:40 | 36 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49777 |  | 2468116ecf655067c9eff34238299fd2 | 8.6 | 智算硬件压测 | 2 | 7a21404db97a2a7184547a95c4f4a28c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-24 00:00:00 | 2026-03-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-22 23:50:29 | 31 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49784 |  | 24a9ae7269db8fda5d0eb5b63853c830 | 7.24 | 总线设备柜验收 | 2 | 0d2365c84de5c6fbd95cb5b915b11daf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-15进行总线设备柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-18 00:00:00 | 2026-03-24 00:00:00 | 2026-03-22 00:00:00 | 2026-03-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-15 20:45:19 | 32 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49649 |  | 25531f26a39c7aa468f4b6d3126b7dfd | 7.19 | 液冷计算柜安装 | 2 | 0a42ee3f371d80abc73b66a46d67254f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-06进行液冷计算柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 2026-03-09 00:00:00 | 2026-03-09 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 09:55:58 | 15 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49717 |  | 25c4e687e6c7bc86da82f22f63ee6e6d | 8.12 | 计算子系统验证-智算服务器 | 2 | 150290f605b7b9c11fb814eb2fa4cb3f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-18进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-27 00:00:00 | 2026-03-30 00:00:00 | 2026-04-01 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-04-02 19:15:13 | 23 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49795 |  | 26d77234337e7df699daae2bdfbe3a7f | 9.2 | 网络管理系统对接 | 2 | 1a7cd43a16f5a52df8b8948fed1de43b | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-16进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-16 00:00:00 | 2026-03-19 00:00:00 | 2026-03-20 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-04-02 19:14:31 | 33 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49637 |  | 27d9bb27ecbd519a00575ebf6b48ede9 | 8.1 | 基础网络配置 | 2 | b5f402b29414deadb16f17861def8194 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-15进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-14 00:00:00 | 2026-01-15 00:00:00 | 2026-01-17 00:00:00 | 2026-01-18 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:34:51 | 13 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49549 |  | 2866389ea55269ba184f0b54b2386005 | 4.0 | 建模仿真 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-20至2025-12-27进行建模仿真活动，确保建模仿真顺利进行。 | { "device_list": [] } | manage_agent | simulation_agent | 2025-12-20 00:00:00 | 2025-12-27 00:00:00 | 2025-12-22 00:00:00 | 2025-12-29 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:46:30 |  | { "device_list": [] }
49856 |  | 288898b97b4db7fb9e7e9f2afa2c1701 | 9.7 | 集群系统集成测试 | 2 | 101a6de57d32e63d5bb5c737a2136aa5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-25至2026-03-29进行集群系统集成测试活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 48, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-31 00:00:00 | 2026-03-31 00:00:00 | 2026-04-05 00:00:00 | 2026-04-05 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-02 19:16:26 |  | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 192, "unit": "台" } ] } |  | B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08 |  | 100%
49755 |  | 288b293c6daa0cee7dcf3591015ad2aa | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 00213f32bd359e146829c8b6e81e054d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-26 00:00:00 | 2026-01-28 00:00:00 | 2026-01-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 09:52:08 | 28 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49539 |  | 2940d04aa19ba3976559fe3ee3ee9c0d | 4.3 | 建模仿真初稿评审 | 2 | 2866389ea55269ba184f0b54b2386005 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-26至2025-12-26进行建模仿真初稿评审活动，确保建模仿真顺利进行。 | { "device_list": [] } | manage_agent | simulation_agent | 2025-12-26 00:00:00 | 2025-12-26 00:00:00 | 2025-12-28 00:00:00 | 2025-12-28 00:00:00 | 已完成 | 100% | 李佳蒴 60094644 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:46:26 |  | { "device_list": [] } |  |  |  | 100%
49700 |  | 2bcc251246e09dcd8f8c0038b5881a12 | 8.7 | 网络子系统部署调测 | 2 | 0f8cc620095af38d62109166a5af7bc4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-10至2026-03-14进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-10 00:00:00 | 2026-03-14 00:00:00 | 2026-03-12 00:00:00 | 2026-03-16 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-22 23:56:15 | 21 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49709 |  | 2db7bf17f2630ac45a6b599cd9b3986e | 6.2 | 计算柜到货（含开箱验货） | 2 | 974f1dbc336d0a548d8c0446ef1588c7 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行计算柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-09 00:00:00 | 2026-03-09 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-10 09:57:10 | 23 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49679 |  | 2de28aa17bee5455bd8767f5ed135f95 | 6.11 | 转运与设备静置 | 2 | 49933100b7bbf12f6eafe81922f0875d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-05至2026-03-05进行转运与设备静置活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-05 00:00:00 | 2026-03-05 00:00:00 | 2026-03-07 00:00:00 | 2026-03-07 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-07 00:00:00 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49571 |  | 2e6d7234296ddcb74e2099b7710c2783 | 6.9 | 网络到货（含开箱验货） | 2 | f52853c9677b1938411df3cedf812acc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行网络到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:47:19 | 5 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49675 |  | 30007f6ecaa7d88df89066d8ba4b0173 | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-17进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-26 00:00:00 | 2026-03-18 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-04-02 19:13:51 |  | { "device_list": [] } |  | B2DH402-POD06
49824 |  | 3013554dc7f63ea323c0559f431438ce | 8.7 | 网络子系统部署调测 | 2 | dc4fd9bf53efce590628780fd29f44a8 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-24至2026-01-28进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-24 00:00:00 | 2026-01-26 00:00:00 | 2026-01-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:42:23 | 37 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49791 |  | 333ca8fd2da43968cf3404b295068dc5 | 7.15 | 网络设备硬件验收 | 2 | 0d2365c84de5c6fbd95cb5b915b11daf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-08进行网络设备硬件验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 2026-03-12 00:00:00 | 2026-03-12 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-15 20:45:08 | 33 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49788 |  | 34879ab7f92ef4c12ba41e114fb4f462 | 6.9 | 网络到货（含开箱验货） | 2 | 7b49cc45f3121c22f06324dce60e6c64 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行网络到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 10:10:55 | 33 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49558 |  | 35cf669e8261a06dc60e05ce305824f8 | 7.21 | 液冷计算柜验收 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-26进行液冷计算柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-22 00:00:00 | 2026-01-28 00:00:00 | 2026-01-24 00:00:00 | 2026-01-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:48:02 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49775 |  | 3670e44ad20f0256cf7255613b1537c2 | 7.21 | 液冷计算柜验收 | 2 | 0d2365c84de5c6fbd95cb5b915b11daf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-15进行液冷计算柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-18 00:00:00 | 2026-03-24 00:00:00 | 2026-03-22 00:00:00 | 2026-03-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-15 20:45:39 | 31 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49615 |  | 37bea7e1676e5556db38c42698b9e8c0 | 7.3 | 综合布线与成端-灵衢线缆 | 2 | 39f755adca700a886f962ce3bac181bc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-06至2026-01-17进行综合布线与成端-灵衢线缆活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2026-01-06 00:00:00 | 2026-01-19 00:00:00 | 2026-01-09 00:00:00 | 2026-01-22 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-01-23 00:00:00 | 10 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH401-POD02 |  | 100%
49801 |  | 38886f5903d5e42f19cb4b0c3dc682a1 | 7.3 | 综合布线与成端-灵衢线缆 | 2 | 668de380b2c306cc4b6644ee75fe4ef9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-06至2026-01-20进行综合布线与成端-灵衢线缆活动，确保在设备到货后完成里程碑。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2026-01-06 00:00:00 | 2026-01-20 00:00:00 | 2026-01-08 00:00:00 | 2026-01-22 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-01-24 00:00:00 | 34 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH403-POD09 |  | 100%
49612 |  | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 8.0 | 单机调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-29进行单机调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-14 00:00:00 | 2026-01-29 00:00:00 | 2026-01-19 00:00:00 | 2026-02-03 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:54:07 |  | { "device_list": [] } |  | B2DH401-POD04 |  | 100%
49793 |  | 39d4662edfaca2ae187f7ba2fa2b5408 | 8.7 | 网络子系统部署调测 | 2 | 7a21404db97a2a7184547a95c4f4a28c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-10至2026-03-14进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-10 00:00:00 | 2026-03-14 00:00:00 | 2026-03-14 00:00:00 | 2026-03-18 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-22 23:56:27 | 33 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49642 |  | 39f755adca700a886f962ce3bac181bc | 7.0 | 工程安装 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-02至2026-01-26进行工程安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2025-12-02 00:00:00 | 2026-01-28 00:00:00 | 2025-12-05 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:34:45 |  | { "device_list": [] } |  | B2DH401-POD02
49623 |  | 3b7133585ebe7213c7ecac5a4a451b12 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | b5f402b29414deadb16f17861def8194 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-26 00:00:00 | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 08:35:25 | 11 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49661 |  | 3d3c6a58aea538db368d435e6cc45c2b | 8.5 | 设备硬装初始化-灵衢网络 | 2 | fe360f4b58153382f33ce7e61e7e0db5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-10进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 2026-03-21 00:00:00 | 2026-03-22 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-22 23:51:16 | 16 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49739 |  | 3e7f3f99745195e4cfe63a595a4cc077 | 7.3 | 综合布线与成端-灵衢线缆 | 2 | d6c4fa9c7e400667870077b23e88f967 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-06至2026-01-17进行综合布线与成端-灵衢线缆活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2026-01-06 00:00:00 | 2026-01-19 00:00:00 | 2026-01-10 00:00:00 | 2026-01-23 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-01-24 00:00:00 | 26 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH401-POD03 |  | 100%
49809 |  | 3f696f421702b221cd2e197e3e1a3082 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | dc4fd9bf53efce590628780fd29f44a8 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-25至2026-01-29进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-26 00:00:00 | 2026-01-26 00:00:00 | 2026-01-28 00:00:00 | 2026-01-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 09:58:04 | 35 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49589 |  | 40c9857eea817f2e03d8ab1ad46a45f8 | 7.21 | 液冷计算柜验收 | 2 | 92d8f9e053e5c6293b513d9bfef0b492 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-26进行液冷计算柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-22 00:00:00 | 2026-01-28 00:00:00 | 2026-01-27 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:42:43 | 7 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49738 |  | 4108637ef43011b589742437c30ca267 | 6.5 | 灵衢线缆到货（含开箱验货） | 2 | e4ce39e2aff0d3dd2cfa93d47331d18e | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-05进行灵衢线缆到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-05 00:00:00 | 2026-01-09 00:00:00 | 2026-01-09 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 08:35:55 | 26 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH401-POD03 |  | 100%
49689 |  | 418816c0fa50032499fcf540f63f8251 | 7.22 | 总线设备柜安装 | 2 | 130bd396a173514f6052d60408189852 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-06进行总线设备柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-10 09:54:55 | 20 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49821 |  | 41f4ab542edf033b828d3ba22559c337 | 7.14 | 网络设备上电 | 2 | 668de380b2c306cc4b6644ee75fe4ef9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-21进行网络设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-21 00:00:00 | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-01-28 00:00:00 | 37 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49561 |  | 437b34effcfe5ba1acdbfd3cab2cb780 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | d67315c919da4515dcd27f7f8cee0fd4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-26 00:00:00 | 2026-01-26 00:00:00 | 2026-01-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 08:33:07 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49647 |  | 438c770b02ec7ea3c96557af3e5fa4ec | 6.2 | 计算柜到货（含开箱验货） | 2 | 15225ba7ad316e6a0f70b2424fcabe1c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行计算柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-07 00:00:00 | 2026-03-07 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 10:10:11 | 15 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49658 |  | 43b2817df3240a223fb2a653f839fb01 | 7.22 | 总线设备柜安装 | 2 | 0a42ee3f371d80abc73b66a46d67254f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-06进行总线设备柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 2026-03-09 00:00:00 | 2026-03-09 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-10 09:55:46 | 16 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49811 |  | 447cfc8f8becbd2f3e0ecc2326f0792c | 9.1 | 计算管理系统对接 | 2 | f9ac2503e56fa2240efefcc3aba5828a | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-30至2026-01-31进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 2026-01-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 08:40:10 | 35 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49731 |  | 44a832bb452f084ddbadb68f3109fdc2 | 8.7 | 网络子系统部署调测 | 2 | 150290f605b7b9c11fb814eb2fa4cb3f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-10至2026-03-14进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-10 00:00:00 | 2026-03-14 00:00:00 | 2026-03-15 00:00:00 | 2026-03-19 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-22 23:56:31 | 25 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49814 |  | 453a9b7e410122b2a783082b8e5083f5 | 7.23 | 总线设备柜设备上电 | 2 | 668de380b2c306cc4b6644ee75fe4ef9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-22进行总线设备柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-21 00:00:00 | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 2026-01-24 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-01-28 00:00:00 | 36 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49594 |  | 45ada2d3876be5ea44d0edfe32fcf42e | 9.1 | 计算管理系统对接 | 2 | e0f5b7502c728cdf7af677ef58bdf1d0 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-02-01 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:54:11 | 7 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49815 |  | 464eda7e572731f6267f4291e50e2329 | 7.24 | 总线设备柜验收 | 2 | 668de380b2c306cc4b6644ee75fe4ef9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-23至2026-01-29进行总线设备柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-23 00:00:00 | 2026-01-25 00:00:00 | 2026-01-25 00:00:00 | 2026-01-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:41:35 | 36 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49663 |  | 4705b31849a267488be51551e38d730d | 8.13 | 计算子系统验证-灵衢网络 | 2 | fe360f4b58153382f33ce7e61e7e0db5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-18进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-27 00:00:00 | 2026-03-28 00:00:00 | 2026-03-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-04-02 19:13:20 | 16 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49701 |  | 48a9419fa0438eef1d7d35382c7ab85e | 8.15 | 网络子系统验证 | 2 | 0f8cc620095af38d62109166a5af7bc4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-17进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-17 00:00:00 | 2026-03-17 00:00:00 | 2026-03-19 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-22 23:54:30 | 21 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49833 |  | 48e463c3cc57887bccec4698759bb321 | 9.6 | 集群通信配置测试 | 2 | f502cd626d2334d82791f460952855ff | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-03至2026-02-04进行集群通信配置测试活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 48, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-30 00:00:00 | 2026-01-30 00:00:00 | 2026-02-04 00:00:00 | 2026-02-04 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 10:08:24 |  | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 192, "unit": "台" } ] } |  | B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04 |  | 100%
49703 |  | 49933100b7bbf12f6eafe81922f0875d | 6.0 | 到货 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-03-05进行到货活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-03-05 00:00:00 | 2026-01-07 00:00:00 | 2026-03-07 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-10 09:43:50 |  | { "device_list": [] } |  | B2DH402-POD05 |  | 100%
49720 |  | 49ba339e4d0732575b368690a94cc15a | 7.22 | 总线设备柜安装 | 2 | 5711bf7d585084aa21011f8708cc8f26 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-06进行总线设备柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 2026-03-11 00:00:00 | 2026-03-11 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-10 09:57:37 | 24 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49699 |  | 4a6a4703cb9b82a7afa17a2d18621ed7 | 8.1 | 基础网络配置 | 2 | 0f8cc620095af38d62109166a5af7bc4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-09进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-08 00:00:00 | 2026-03-09 00:00:00 | 2026-03-10 00:00:00 | 2026-03-11 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-19 18:40:58 | 21 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49859 |  | 4aabf7a60fe6ff1a2f0e6ffcc1ace474 | 12.2 | 输出验收报告 | 2 | 9f85b7d5cb45132378d790a0cf6120cf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-04-09至2026-04-13进行输出验收报告活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-02 00:00:00 | 2026-04-02 00:00:00 | 2026-04-07 00:00:00 | 2026-04-07 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-07 08:27:51 |  | { "device_list": [] } |  | B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08 |  | 100%
49598 |  | 4b3c39806062d73a3ac7168c7a817b7a | 7.24 | 总线设备柜验收 | 2 | 92d8f9e053e5c6293b513d9bfef0b492 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-26进行总线设备柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-22 00:00:00 | 2026-01-28 00:00:00 | 2026-01-27 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:42:43 | 8 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49759 |  | 4bae3eadface9dc849b05e60ab515e97 | 7.14 | 网络设备上电 | 2 | d6c4fa9c7e400667870077b23e88f967 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-13进行网络设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-13 00:00:00 | 2026-01-16 00:00:00 | 2026-01-17 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-01-28 00:00:00 | 29 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49715 |  | 4d3d7ce4add405be7da847041a65bbb1 | 8.6 | 智算硬件压测 | 2 | 150290f605b7b9c11fb814eb2fa4cb3f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-25 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-22 23:50:35 | 23 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49812 |  | 4e9e35fca46b7d5dff1ccb28fa5c2b29 | 6.3 | 总线设备柜到货（含开箱验货） | 2 | 4f1622107208a82e5379e84235c8076b | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-18进行总线设备柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-18 00:00:00 | 2026-01-18 00:00:00 | 2026-01-20 00:00:00 | 2026-01-20 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 08:40:27 | 36 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49772 |  | 4ee579a908da44f51dc17886cacc60fa | 6.11 | 转运与设备静置 | 2 | 7b49cc45f3121c22f06324dce60e6c64 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-05至2026-03-05进行转运与设备静置活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-05 00:00:00 | 2026-03-05 00:00:00 | 2026-03-09 00:00:00 | 2026-03-09 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-09 00:00:00 | 31 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49827 |  | 4f1622107208a82e5379e84235c8076b | 6.0 | 到货 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-19进行到货活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-19 00:00:00 | 2026-01-07 00:00:00 | 2026-01-21 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:40:44 |  | { "device_list": [] } |  | B2DH403-POD09
49805 |  | 4f49551c4da7c58a4020c4bc39d3b3b4 | 7.20 | 液冷计算柜设备上电 | 2 | 668de380b2c306cc4b6644ee75fe4ef9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-22进行液冷计算柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-23 00:00:00 | 2026-01-24 00:00:00 | 2026-01-25 00:00:00 | 2026-01-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-01-28 00:00:00 | 35 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49534 |  | 4f552ebe5d12766d71fc42302ee24d61 | 3.2 | 远程视频辅助 | 2 | a5509dbfc0ddd88c2b793fbec3a55cbe | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-18至2025-12-19进行远程视频辅助活动，确保工程勘测顺利进行。 | { "device_list": [] } | manage_agent | survey_agent | 2025-12-18 00:00:00 | 2025-12-19 00:00:00 | 2025-12-20 00:00:00 | 2025-12-21 00:00:00 | 已完成 | 100% | 侯克照 00578443 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:45:26 |  | { "device_list": [] } |  |  |  | 100%
49588 |  | 4f6fd384981c9669f6872af46ec0e217 | 7.20 | 液冷计算柜设备上电 | 2 | 92d8f9e053e5c6293b513d9bfef0b492 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-19进行液冷计算柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-21 00:00:00 | 2026-01-25 00:00:00 | 2026-01-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-01-29 00:00:00 | 7 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49668 |  | 50cd65e7ea42bdd0e90d2321a2911466 | 8.1 | 基础网络配置 | 2 | fe360f4b58153382f33ce7e61e7e0db5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-09进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-08 00:00:00 | 2026-03-09 00:00:00 | 2026-03-11 00:00:00 | 2026-03-12 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-19 18:41:02 | 17 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49584 |  | 516e11c9ebc34fa6d41b5ecac544fcd6 | 7.3 | 综合布线与成端-灵衢线缆 | 2 | 92d8f9e053e5c6293b513d9bfef0b492 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-06至2026-01-17进行综合布线与成端-灵衢线缆活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2026-01-06 00:00:00 | 2026-01-19 00:00:00 | 2026-01-11 00:00:00 | 2026-01-24 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-01-25 00:00:00 | 6 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH401-POD04 |  | 100%
49568 |  | 527dac3aaca77abb7a104ea0d0166b7b | 8.5 | 设备硬装初始化-灵衢网络 | 2 | d67315c919da4515dcd27f7f8cee0fd4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 2026-01-24 00:00:00 | 2026-01-25 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 08:31:26 | 4 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49786 |  | 52dab477bbf805a43b4e37d8acc42f3d | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 7a21404db97a2a7184547a95c4f4a28c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-24 00:00:00 | 2026-03-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-04-02 19:14:01 | 32 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49565 |  | 534affe29149b297b4d268e148ef2579 | 7.22 | 总线设备柜安装 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-12进行总线设备柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:47:43 | 4 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49542 |  | 5460cc7a87b5d9808bb1b37a11ce4aca | 5.2 | 计算子系统LLD设计 | 2 | 9d902ce7baa85aa0b3573c7dc4634011 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-28至2026-01-01进行计算子系统LLD设计活动，确保低阶设计顺利进行。 | { "device_list": [] } | manage_agent | design_agent | 2025-12-28 00:00:00 | 2026-01-01 00:00:00 | 2025-12-30 00:00:00 | 2026-01-03 00:00:00 | 已完成 | 100% | 张杨 00543862 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:46:40 |  | { "device_list": [] } |  |  |  | 100%
49660 |  | 54d9bfd55b40d9f230bae34c9613b20b | 7.24 | 总线设备柜验收 | 2 | 0a42ee3f371d80abc73b66a46d67254f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-15进行总线设备柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-18 00:00:00 | 2026-03-24 00:00:00 | 2026-03-21 00:00:00 | 2026-03-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-15 20:44:21 | 16 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49847 |  | 5541705f58eb522fb81331baf6a88cd5 | 12.1 | 客户集群验收 | 2 | dd183b97366f3e6338d7bcdc1464d2ea | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-13至2026-02-22进行客户集群验收活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-01-31 00:00:00 | 2026-01-31 00:00:00 | 2026-02-02 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-03-10 09:59:54 |  | { "device_list": [] } |  | B2DH403-POD09 |  | 100%
49810 |  | 56489928f11ef83f1d7d4546c272f178 | 8.12 | 计算子系统验证-智算服务器 | 2 | dc4fd9bf53efce590628780fd29f44a8 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-30至2026-02-01进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 2026-01-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 09:58:12 | 35 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49735 |  | 5711bf7d585084aa21011f8708cc8f26 | 7.0 | 工程安装 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-02至2026-03-15进行工程安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2025-12-02 00:00:00 | 2026-03-24 00:00:00 | 2025-12-07 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-15 20:46:35 |  | { "device_list": [] } |  | B2DH402-POD08
49752 |  | 575571837b3fee7d679346a3b9cfd52f | 7.23 | 总线设备柜设备上电 | 2 | d6c4fa9c7e400667870077b23e88f967 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-19进行总线设备柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-21 00:00:00 | 2026-01-24 00:00:00 | 2026-01-25 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-01-28 00:00:00 | 28 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49848 |  | 58c63822458755a5ac18d27c7479aa8e | 12.2 | 输出验收报告 | 2 | dd183b97366f3e6338d7bcdc1464d2ea | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-23至2026-02-27进行输出验收报告活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-01 00:00:00 | 2026-02-01 00:00:00 | 2026-02-03 00:00:00 | 2026-02-03 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-03-10 09:59:58 |  | { "device_list": [] } |  | B2DH403-POD09 |  | 100%
49778 |  | 58e74b9663b375e0756178db1f4fe272 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 7a21404db97a2a7184547a95c4f4a28c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-24 00:00:00 | 2026-03-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-04-02 19:14:17 | 31 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49818 |  | 5919a6bb318d96eddcbad33f04993fea | 8.13 | 计算子系统验证-灵衢网络 | 2 | dc4fd9bf53efce590628780fd29f44a8 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-30至2026-02-01进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-26 00:00:00 | 2026-01-26 00:00:00 | 2026-01-28 00:00:00 | 2026-01-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:42:47 | 36 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49654 |  | 5978f0d5e61a8cc8282af86188b8f821 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | fe360f4b58153382f33ce7e61e7e0db5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-23 00:00:00 | 2026-03-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-04-02 19:13:30 | 15 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49566 |  | 59f29d6ef22146166387062b76060df1 | 7.23 | 总线设备柜设备上电 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-19进行总线设备柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-21 00:00:00 | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-01-25 00:00:00 | 4 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49826 |  | 5c02eb5b018943449e03b2a0794c09c2 | 9.2 | 网络管理系统对接 | 2 | f9ac2503e56fa2240efefcc3aba5828a | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-29至2026-01-30进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-25 00:00:00 | 2026-01-25 00:00:00 | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:40:03 | 37 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49837 |  | 5ffddab184ef77e66850bb0a157c52a0 | 12.2 | 输出验收报告 | 2 | fae29171999e359cf40c83e23c9da541 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-20至2026-02-24进行输出验收报告活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-02 00:00:00 | 2026-02-02 00:00:00 | 2026-02-07 00:00:00 | 2026-02-07 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 09:58:56 |  | { "device_list": [] } |  | B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04 |  | 100%
49680 |  | 60327408bc2f95ffdf492a626ef1ecc3 | 7.19 | 液冷计算柜安装 | 2 | 130bd396a173514f6052d60408189852 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-06进行液冷计算柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-11 08:53:04 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49816 |  | 60fbbd19e725239eea6578e12f7e163f | 8.5 | 设备硬装初始化-灵衢网络 | 2 | dc4fd9bf53efce590628780fd29f44a8 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-23至2026-01-24进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-23 00:00:00 | 2026-01-24 00:00:00 | 2026-01-25 00:00:00 | 2026-01-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:42:35 | 36 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49782 |  | 622063aa7a1612b78b8f68654e361234 | 7.22 | 总线设备柜安装 | 2 | 0d2365c84de5c6fbd95cb5b915b11daf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-06进行总线设备柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 2026-03-10 00:00:00 | 2026-03-10 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 09:56:34 | 32 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49860 |  | 62c47cc804f82258dbefa4ab314a81fb | 12.3 | 验收报告沟通 | 2 | 9f85b7d5cb45132378d790a0cf6120cf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-04-14至2026-04-16进行验收报告沟通活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-03 00:00:00 | 2026-04-03 00:00:00 | 2026-04-08 00:00:00 | 2026-04-08 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-07 08:27:59 |  | { "device_list": [] } |  | B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08 |  | 100%
49546 |  | 63305541398bb71eeb95488c93d1f122 | 5.7 | 低阶设计评审 | 2 | 9d902ce7baa85aa0b3573c7dc4634011 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-02至2026-01-04进行低阶设计评审活动，确保低阶设计顺利进行。 | { "device_list": [] } | manage_agent | design_agent | 2026-01-02 00:00:00 | 2026-01-04 00:00:00 | 2026-01-04 00:00:00 | 2026-01-06 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:46:59 |  | { "device_list": [] } |  |  |  | 100%
49785 |  | 633a7231f3a17559daf01450d8f695f5 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 7a21404db97a2a7184547a95c4f4a28c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-10进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 2026-03-22 00:00:00 | 2026-03-23 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-22 23:51:21 | 32 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49597 |  | 641079afd6d221a3685cba2023d72882 | 7.23 | 总线设备柜设备上电 | 2 | 92d8f9e053e5c6293b513d9bfef0b492 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-19进行总线设备柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-21 00:00:00 | 2026-01-25 00:00:00 | 2026-01-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-01-29 00:00:00 | 8 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49650 |  | 64ba19e1d3e257168b6493f4827db9f8 | 7.20 | 液冷计算柜设备上电 | 2 | 0a42ee3f371d80abc73b66a46d67254f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-07至2026-03-08进行液冷计算柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-16 00:00:00 | 2026-03-17 00:00:00 |  |  | 未开始 | 0% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-21 00:00:00 | 15 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49635 |  | 64e21625169a67678e45dada59010f57 | 7.14 | 网络设备上电 | 2 | 39f755adca700a886f962ce3bac181bc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-13进行网络设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-13 00:00:00 | 2026-01-15 00:00:00 | 2026-01-16 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-01-27 00:00:00 | 13 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49828 |  | 668de380b2c306cc4b6644ee75fe4ef9 | 7.0 | 工程安装 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-02至2026-01-29进行工程安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2025-12-02 00:00:00 | 2026-01-31 00:00:00 | 2025-12-04 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:41:57 |  | { "device_list": [] } |  | B2DH403-POD09
49806 |  | 6750521fe9c2f36c1b8e4bde3da28fef | 7.21 | 液冷计算柜验收 | 2 | 668de380b2c306cc4b6644ee75fe4ef9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-23至2026-01-29进行液冷计算柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-25 00:00:00 | 2026-01-31 00:00:00 | 2026-01-27 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 08:41:57 | 35 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49609 |  | 6844135905e0ec1fd45c9ae3e0b93853 | 9.2 | 网络管理系统对接 | 2 | e0f5b7502c728cdf7af677ef58bdf1d0 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-22进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-21 00:00:00 | 2026-01-26 00:00:00 | 2026-01-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:54:15 | 9 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49756 |  | 69fb4ea1282152d8c48406e7b283ef8c | 8.13 | 计算子系统验证-灵衢网络 | 2 | 00213f32bd359e146829c8b6e81e054d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 2026-01-31 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 09:52:13 | 28 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49601 |  | 6a6aeb1d1ec35191fd10d4fcea4af3e7 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 2026-02-01 00:00:00 | 2026-02-03 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:53:40 | 8 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49849 |  | 6aed03dd123c8eb51915b27c55ad1c1e | 12.3 | 验收报告沟通 | 2 | dd183b97366f3e6338d7bcdc1464d2ea | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-28至2026-03-02进行验收报告沟通活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-02 00:00:00 | 2026-02-02 00:00:00 | 2026-02-04 00:00:00 | 2026-02-04 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-03-10 10:00:02 |  | { "device_list": [] } |  | B2DH403-POD09 |  | 100%
49779 |  | 6d64791199038b93af43bac4474eb4a5 | 8.12 | 计算子系统验证-智算服务器 | 2 | 7a21404db97a2a7184547a95c4f4a28c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-18进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-27 00:00:00 | 2026-03-29 00:00:00 | 2026-03-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-04-02 19:14:23 | 31 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49712 |  | 6e1eaf1c77b93431c44ac4dc5b3c8eaa | 7.20 | 液冷计算柜设备上电 | 2 | 5711bf7d585084aa21011f8708cc8f26 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-07至2026-03-08进行液冷计算柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-16 00:00:00 | 2026-03-17 00:00:00 | 2026-03-21 00:00:00 |  | 进行中 | 30% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-23 00:00:00 | 23 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49836 |  | 6e28d6bc3eb7edcd1cb23804107d9184 | 12.1 | 客户集群验收 | 2 | fae29171999e359cf40c83e23c9da541 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-10至2026-02-19进行客户集群验收活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-01 00:00:00 | 2026-02-01 00:00:00 | 2026-02-06 00:00:00 | 2026-02-06 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 09:58:50 |  | { "device_list": [] } |  | B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04 |  | 100%
49846 |  | 6f86ea2a1bb59bb7a25593c93692f9b4 | 9.8 | 集群性能调优 | 2 | f9ac2503e56fa2240efefcc3aba5828a | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-13至2026-02-15进行集群性能调优活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-01-31 00:00:00 | 2026-01-31 00:00:00 | 2026-02-02 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-02-03 00:00:00 |  | { "device_list": [] } |  | B2DH403-POD09 |  | 100%
49555 |  | 7074a3e4bffb251414ec557c173e4b8d | 6.11 | 转运与设备静置 | 2 | f52853c9677b1938411df3cedf812acc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-11至2026-01-11进行转运与设备静置活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-11 00:00:00 | 2026-01-11 00:00:00 | 2026-01-13 00:00:00 | 2026-01-13 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-01-13 00:00:00 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49622 |  | 70967e75c9e2a8701970de106bca4001 | 8.6 | 智算硬件压测 | 2 | b5f402b29414deadb16f17861def8194 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-28 00:00:00 | 2026-01-27 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 08:35:31 | 11 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49792 |  | 70b58027cf54704623ee64cbdb6b9684 | 8.1 | 基础网络配置 | 2 | 7a21404db97a2a7184547a95c4f4a28c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-09进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-08 00:00:00 | 2026-03-09 00:00:00 | 2026-03-12 00:00:00 | 2026-03-13 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-19 18:41:08 | 33 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49543 |  | 7126fe6a4a6e2a1f5df92c8a64a6b459 | 5.3 | 网络子系统LLD设计 | 2 | 9d902ce7baa85aa0b3573c7dc4634011 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-28至2026-01-01进行网络子系统LLD设计活动，确保低阶设计顺利进行。 | { "device_list": [] } | manage_agent | design_agent | 2025-12-28 00:00:00 | 2026-01-01 00:00:00 | 2025-12-30 00:00:00 | 2026-01-03 00:00:00 | 已完成 | 100% | 网络专家 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:46:44 |  | { "device_list": [] } |  |  |  | 100%
49724 |  | 714e1651f888edc8d5efe7114bba7fb5 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 150290f605b7b9c11fb814eb2fa4cb3f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-25 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-04-02 19:14:50 | 24 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49537 |  | 729aec4da0f04e5d7b18ff17fd97ab15 | 4.1 | 信息分析与确认 | 2 | 2866389ea55269ba184f0b54b2386005 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-20至2025-12-20进行信息分析与确认活动，确保建模仿真顺利进行。 | { "device_list": [] } | manage_agent | simulation_agent | 2025-12-20 00:00:00 | 2025-12-20 00:00:00 | 2025-12-22 00:00:00 | 2025-12-22 00:00:00 | 已完成 | 100% | 李佳蒴 60094644 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:46:17 |  | { "device_list": [] } |  |  |  | 100%
49625 |  | 739c9761e2ca52ad9a6a4ec2c9112e93 | 9.1 | 计算管理系统对接 | 2 | 097cb011d565cd09f42c3de80111c703 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-01-30 00:00:00 | 2026-01-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:35:47 | 11 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49830 |  | 73d96cba6457786cbce5761f7f3edabc | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-29至2026-01-31进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-25 00:00:00 | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 09:58:18 |  | { "device_list": [] } |  | B2DH403-POD09 |  | 100%
49748 |  | 74346242d7286003721306bc87feb26f | 8.12 | 计算子系统验证-智算服务器 | 2 | 00213f32bd359e146829c8b6e81e054d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-01-31 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 09:52:29 | 27 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49628 |  | 757e3a125477be2ad052e719f60aee72 | 7.23 | 总线设备柜设备上电 | 2 | 39f755adca700a886f962ce3bac181bc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-19进行总线设备柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-21 00:00:00 | 2026-01-23 00:00:00 | 2026-01-24 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-01-27 00:00:00 | 12 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49807 |  | 75b233293d99467906f2b85ff509fabb | 8.2 | 设备硬装初始化-智算服务器 | 2 | dc4fd9bf53efce590628780fd29f44a8 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-23至2026-01-24进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-25 00:00:00 | 2026-01-25 00:00:00 | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 08:43:02 | 35 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49604 |  | 76efc370947c862edfd3f93549ec7fc9 | 7.14 | 网络设备上电 | 2 | 92d8f9e053e5c6293b513d9bfef0b492 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-13进行网络设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-13 00:00:00 | 2026-01-17 00:00:00 | 2026-01-18 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-01-29 00:00:00 | 9 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49808 |  | 77af99b5dea8df474c421f6009de1fc7 | 8.6 | 智算硬件压测 | 2 | dc4fd9bf53efce590628780fd29f44a8 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-25至2026-01-29进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-26 00:00:00 | 2026-01-26 00:00:00 | 2026-01-28 00:00:00 | 2026-01-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 09:58:08 | 35 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49603 |  | 783c1f7942646b722d6139ced3f9a252 | 7.13 | 网络设备安装 | 2 | 92d8f9e053e5c6293b513d9bfef0b492 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-11至2026-01-11进行网络设备安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-11 00:00:00 | 2026-01-11 00:00:00 | 2026-01-16 00:00:00 | 2026-01-16 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:42:44 | 9 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49723 |  | 789d2dc89696764bb4a4e616bb66026e | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 150290f605b7b9c11fb814eb2fa4cb3f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-10进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 2026-03-23 00:00:00 | 2026-03-24 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-22 23:51:27 | 24 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49774 |  | 79a56237e61bb08ddbba7dc8ad5393c5 | 7.20 | 液冷计算柜设备上电 | 2 | 0d2365c84de5c6fbd95cb5b915b11daf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-07至2026-03-08进行液冷计算柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-16 00:00:00 | 2026-03-17 00:00:00 | 2026-03-20 00:00:00 | 2026-03-21 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-22 00:00:00 | 31 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49798 |  | 7a21404db97a2a7184547a95c4f4a28c | 8.0 | 单机调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-18进行单机调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-08 00:00:00 | 2026-03-27 00:00:00 | 2026-03-12 00:00:00 | 2026-03-31 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-04-02 19:14:23 |  | { "device_list": [] } |  | B2DH402-POD07 |  | 100%
49754 |  | 7a95eb4f2d730425089b58d02befd60d | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 00213f32bd359e146829c8b6e81e054d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 2026-01-26 00:00:00 | 2026-01-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 09:52:05 | 28 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49796 |  | 7b49cc45f3121c22f06324dce60e6c64 | 6.0 | 到货 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-03-05进行到货活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-03-05 00:00:00 | 2026-01-09 00:00:00 | 2026-03-09 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 10:10:55 |  | { "device_list": [] } |  | B2DH402-POD07
49694 |  | 7c9bbd3f67355dfb3e206e60bdfdb2da | 8.13 | 计算子系统验证-灵衢网络 | 2 | 0f8cc620095af38d62109166a5af7bc4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-18进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-27 00:00:00 | 2026-03-27 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-04-02 19:12:25 | 20 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49760 |  | 7e16bce9c98ba2d01f38724bf3932593 | 7.15 | 网络设备硬件验收 | 2 | d6c4fa9c7e400667870077b23e88f967 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-14进行网络设备硬件验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 2026-01-18 00:00:00 | 2026-01-18 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 08:36:44 | 29 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49552 |  | 7f7578f0e84e25ebb234f4b5fc6e2a0b | 7.1 | 机房洁净度测试 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-02至2025-12-06进行机房洁净度测试活动，确保工程安装顺利进行。 | { "device_list": [] } | manage_agent | installation_agent | 2025-12-02 00:00:00 | 2025-12-06 00:00:00 | 2025-12-04 00:00:00 | 2025-12-08 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:47:24 |  | { "device_list": [] } |  | B2DH401-POD01 |  | 100%
49639 |  | 7f91baeabf840f9bc785a620cf6f50f5 | 8.15 | 网络子系统验证 | 2 | b5f402b29414deadb16f17861def8194 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-23进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-23 00:00:00 | 2026-01-24 00:00:00 | 2026-01-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:35:02 | 13 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49858 |  | 7fa986a000a50959bd1d8fe06e916da0 | 12.1 | 客户集群验收 | 2 | 9f85b7d5cb45132378d790a0cf6120cf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-30至2026-04-08进行客户集群验收活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-01 00:00:00 | 2026-04-01 00:00:00 | 2026-04-06 00:00:00 | 2026-04-06 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-07 08:27:43 |  | { "device_list": [] } |  | B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08 |  | 100%
49662 |  | 7fddf8f1d7b9ab5c523eeaf67ec484a1 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | fe360f4b58153382f33ce7e61e7e0db5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-23 00:00:00 | 2026-03-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-04-02 19:13:14 | 16 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49667 |  | 8151ce7876edeec4956e628730c1104a | 7.15 | 网络设备硬件验收 | 2 | 0a42ee3f371d80abc73b66a46d67254f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-08进行网络设备硬件验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 2026-03-11 00:00:00 | 2026-03-11 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-15 20:44:12 | 17 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49659 |  | 82cb114b898394a62e5d8d8500a3b01d | 7.23 | 总线设备柜设备上电 | 2 | 0a42ee3f371d80abc73b66a46d67254f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-07至2026-03-08进行总线设备柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-16 00:00:00 | 2026-03-17 00:00:00 |  |  | 未开始 | 0% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-21 00:00:00 | 16 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49725 |  | 82edbd94fb9583582135bbdf6902beca | 8.13 | 计算子系统验证-灵衢网络 | 2 | 150290f605b7b9c11fb814eb2fa4cb3f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-18进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-27 00:00:00 | 2026-03-30 00:00:00 | 2026-04-01 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-04-02 19:15:01 | 24 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49855 |  | 83915923ef721ebea2841de97a5b6fee | 9.6 | 集群通信配置测试 | 2 | 101a6de57d32e63d5bb5c737a2136aa5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-23至2026-03-24进行集群通信配置测试活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 48, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-30 00:00:00 | 2026-03-30 00:00:00 | 2026-04-04 00:00:00 | 2026-04-04 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-02 19:16:14 |  | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 192, "unit": "台" } ] } |  | B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08 |  | 100%
49683 |  | 840ab0e335f69fde86efb42c8bf01e05 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 0f8cc620095af38d62109166a5af7bc4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-10进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 2026-03-20 00:00:00 | 2026-03-21 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-22 23:51:40 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49559 |  | 869e976efd4cdaeb8e04c60f5caa07dd | 8.2 | 设备硬装初始化-智算服务器 | 2 | d67315c919da4515dcd27f7f8cee0fd4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 2026-01-24 00:00:00 | 2026-01-25 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 08:33:03 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49783 |  | 86d61e89cba3456a5134d88afae7386d | 7.23 | 总线设备柜设备上电 | 2 | 0d2365c84de5c6fbd95cb5b915b11daf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-07至2026-03-08进行总线设备柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-16 00:00:00 | 2026-03-17 00:00:00 | 2026-03-20 00:00:00 | 2026-03-21 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-22 00:00:00 | 32 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49686 |  | 883f0765a49da5c34a5fe141b487e14f | 8.12 | 计算子系统验证-智算服务器 | 2 | 0f8cc620095af38d62109166a5af7bc4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-18进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-27 00:00:00 | 2026-03-27 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-04-02 19:12:43 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49540 |  | 889dd9e848c9eb0e62d3b43f61523be2 | 4.4 | 建模仿真终稿输出 | 2 | 2866389ea55269ba184f0b54b2386005 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-27至2025-12-27进行建模仿真终稿输出活动，确保建模仿真顺利进行。 | { "device_list": [] } | manage_agent | simulation_agent | 2025-12-27 00:00:00 | 2025-12-27 00:00:00 | 2025-12-29 00:00:00 | 2025-12-29 00:00:00 | 已完成 | 100% | 李佳蒴 60094644 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:46:30 |  | { "device_list": [] } |  |  |  | 100%
49800 |  | 891c1fe6e9943446b403d45c3add9ad5 | 6.5 | 灵衢线缆到货（含开箱验货） | 2 | 4f1622107208a82e5379e84235c8076b | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-05进行灵衢线缆到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-05 00:00:00 | 2026-01-07 00:00:00 | 2026-01-07 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 08:40:21 | 34 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH403-POD09 |  | 100%
49687 |  | 89d515672eeac8dc823810fd8b046d5c | 9.1 | 计算管理系统对接 | 2 | ed8aa2bb2319bb51c9f0f6c340ce306b | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-17进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-26 00:00:00 | 2026-03-27 00:00:00 | 2026-03-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-04-02 19:13:03 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49562 |  | 8bad19ed6e3ba85547dcf0f78704f60f | 8.12 | 计算子系统验证-智算服务器 | 2 | d67315c919da4515dcd27f7f8cee0fd4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 2026-01-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 08:33:17 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49616 |  | 8cd93541e9b96aa254b488bf2f4f0d89 | 6.2 | 计算柜到货（含开箱验货） | 2 | a1cfb4ec8e18404017fa40df1bca7ddd | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行计算柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-13 00:00:00 | 2026-01-13 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 08:33:43 | 11 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49669 |  | 8d96ce7901895dd0a3b370471c6ac84b | 8.7 | 网络子系统部署调测 | 2 | fe360f4b58153382f33ce7e61e7e0db5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-10至2026-03-14进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-10 00:00:00 | 2026-03-14 00:00:00 | 2026-03-13 00:00:00 | 2026-03-17 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-22 23:56:22 | 17 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49751 |  | 8eebd3ac42e5a7c3a5530e4d4de195c0 | 7.22 | 总线设备柜安装 | 2 | d6c4fa9c7e400667870077b23e88f967 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-12进行总线设备柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 2026-01-16 00:00:00 | 2026-01-16 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 08:36:49 | 28 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49780 |  | 8f05f3cca9e3562e11f1ebf6d5f2ef93 | 9.1 | 计算管理系统对接 | 2 | 1a7cd43a16f5a52df8b8948fed1de43b | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-17进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-26 00:00:00 | 2026-03-29 00:00:00 | 2026-03-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-04-02 19:14:40 | 31 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49763 |  | 91cda9da58b7760cf6fd8d5ad249732c | 8.15 | 网络子系统验证 | 2 | 00213f32bd359e146829c8b6e81e054d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-23进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-23 00:00:00 | 2026-01-25 00:00:00 | 2026-01-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 09:51:59 | 29 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49611 |  | 92d8f9e053e5c6293b513d9bfef0b492 | 7.0 | 工程安装 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-02至2026-01-26进行工程安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2025-12-02 00:00:00 | 2026-01-28 00:00:00 | 2025-12-07 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:42:43 |  | { "device_list": [] } |  | B2DH401-POD04 |  | 100%
49574 |  | 947ba88e66419cdaced694e985ad5224 | 7.15 | 网络设备硬件验收 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-14进行网络设备硬件验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 2026-01-16 00:00:00 | 2026-01-16 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 00:47:38 | 5 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49771 |  | 95d7408c861a049531d4e97947bb9f69 | 6.2 | 计算柜到货（含开箱验货） | 2 | 7b49cc45f3121c22f06324dce60e6c64 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行计算柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 10:10:48 | 31 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49676 |  | 95da955ea3c44bb9044c7e5323cfc096 | 6.5 | 灵衢线缆到货（含开箱验货） | 2 | 49933100b7bbf12f6eafe81922f0875d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-05进行灵衢线缆到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-05 00:00:00 | 2026-01-07 00:00:00 | 2026-01-07 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-10 09:43:50 | 18 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH402-POD05 |  | 100%
49617 |  | 963c0f437af617e97d1893b20870f87b | 6.11 | 转运与设备静置 | 2 | a1cfb4ec8e18404017fa40df1bca7ddd | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-11至2026-01-11进行转运与设备静置活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-11 00:00:00 | 2026-01-11 00:00:00 | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-01-14 00:00:00 | 11 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49697 |  | 96ff5c06eeda5661fd3000a8f82b3cd2 | 7.14 | 网络设备上电 | 2 | 130bd396a173514f6052d60408189852 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-07进行网络设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-07 00:00:00 | 2026-03-08 00:00:00 | 2026-03-09 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-20 00:00:00 | 21 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49734 |  | 974f1dbc336d0a548d8c0446ef1588c7 | 6.0 | 到货 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-03-05进行到货活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-03-05 00:00:00 | 2026-01-10 00:00:00 | 2026-03-10 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 09:57:19 |  | { "device_list": [] } |  | B2DH402-POD08
49556 |  | 97e76ad827bb998b73ddd1b591eccccd | 7.19 | 液冷计算柜安装 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-12进行液冷计算柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:47:54 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49553 |  | 990c8d5f0f5df07ecf3aedb0b0935a32 | 7.3 | 综合布线与成端-灵衢线缆 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-06至2026-01-17进行综合布线与成端-灵衢线缆活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2026-01-06 00:00:00 | 2026-01-19 00:00:00 | 2026-01-08 00:00:00 | 2026-01-21 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-01-22 00:00:00 | 2 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH401-POD01 |  | 100%
49820 |  | 9b55545abad65cf5555597110150ed39 | 7.13 | 网络设备安装 | 2 | 668de380b2c306cc4b6644ee75fe4ef9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-19至2026-01-19进行网络设备安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-19 00:00:00 | 2026-01-19 00:00:00 | 2026-01-21 00:00:00 | 2026-01-21 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:41:06 | 37 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49606 |  | 9b65125e5931941e69d596afb81d63ba | 8.1 | 基础网络配置 | 2 | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-15进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-14 00:00:00 | 2026-01-15 00:00:00 | 2026-01-19 00:00:00 | 2026-01-20 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:53:20 | 9 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49593 |  | 9bfad7d412e5989a6d0c610f8f40d95e | 8.12 | 计算子系统验证-智算服务器 | 2 | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-02-01 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:54:07 | 7 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49651 |  | 9cd1fd92c9a7204cc6fe13d327696590 | 7.21 | 液冷计算柜验收 | 2 | 0a42ee3f371d80abc73b66a46d67254f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-15进行液冷计算柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-18 00:00:00 | 2026-03-24 00:00:00 | 2026-03-21 00:00:00 | 2026-03-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-15 20:44:33 | 15 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49648 |  | 9d1e82970b382c1fd43de5761c31dd8a | 6.11 | 转运与设备静置 | 2 | 15225ba7ad316e6a0f70b2424fcabe1c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-05至2026-03-05进行转运与设备静置活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-05 00:00:00 | 2026-03-05 00:00:00 | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-08 00:00:00 | 15 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49550 |  | 9d902ce7baa85aa0b3573c7dc4634011 | 5.0 | 低阶设计 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-28至2026-01-04进行低阶设计活动，确保低阶设计顺利进行。 | { "device_list": [] } | manage_agent | design_agent | 2025-12-28 00:00:00 | 2026-01-04 00:00:00 | 2025-12-30 00:00:00 | 2026-01-06 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:46:59 |  | { "device_list": [] }
49624 |  | 9dc88dc03e7b82a8cceefb8c2a5d7f30 | 8.12 | 计算子系统验证-智算服务器 | 2 | b5f402b29414deadb16f17861def8194 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-29进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-01-30 00:00:00 | 2026-01-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 08:35:36 | 11 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49560 |  | 9e572786bb2ed387fb5b279ebbcdbdfe | 8.6 | 智算硬件压测 | 2 | d67315c919da4515dcd27f7f8cee0fd4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-28 00:00:00 | 2026-01-26 00:00:00 | 2026-01-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 08:33:12 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49626 |  | 9f2832fe6e57c7f1b2a86b2beec79192 | 6.3 | 总线设备柜到货（含开箱验货） | 2 | a1cfb4ec8e18404017fa40df1bca7ddd | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行总线设备柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-13 00:00:00 | 2026-01-13 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:33:38 | 12 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49863 |  | 9f85b7d5cb45132378d790a0cf6120cf | 12.0 | 验收测试 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-30至2026-04-18进行验收测试活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-01 00:00:00 | 2026-04-04 00:00:00 | 2026-04-06 00:00:00 | 2026-04-09 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-07 08:28:22 |  | { "device_list": [] } |  | B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08
49742 |  | a02a541f55d0ddc335acb18f28572131 | 7.19 | 液冷计算柜安装 | 2 | d6c4fa9c7e400667870077b23e88f967 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-12进行液冷计算柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 2026-01-16 00:00:00 | 2026-01-16 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 08:37:05 | 27 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49627 |  | a0aebb5ca83c8724889bd982b5d283fc | 7.22 | 总线设备柜安装 | 2 | 39f755adca700a886f962ce3bac181bc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-12进行总线设备柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 2026-01-15 00:00:00 | 2026-01-15 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:34:21 | 12 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49547 |  | a0dbd5ad0477b318aad9cea926d954d3 | 2.0 | L1机房准备 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-01至2025-12-01进行L1机房准备活动，确保L1机房准备顺利进行。 | { "device_list": [] } | manage_agent | other_assistant | 2025-12-01 00:00:00 | 2025-12-01 00:00:00 | 2025-12-03 00:00:00 | 2025-12-03 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 08:30:43 |  | { "device_list": [] } |  |  |  | 100%
49641 |  | a1cfb4ec8e18404017fa40df1bca7ddd | 6.0 | 到货 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-11进行到货活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-11 00:00:00 | 2026-01-08 00:00:00 | 2026-01-14 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:33:54 |  | { "device_list": [] } |  | B2DH401-POD02
49813 |  | a2150c8c4713b189a5d224e33a63b24b | 7.22 | 总线设备柜安装 | 2 | 668de380b2c306cc4b6644ee75fe4ef9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-20进行总线设备柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-20 00:00:00 | 2026-01-22 00:00:00 | 2026-01-22 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 08:41:23 | 36 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49693 |  | a2a382c53d9f0c26dec1a5c0347e2e38 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 0f8cc620095af38d62109166a5af7bc4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-22 00:00:00 | 2026-03-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-04-02 19:12:19 | 20 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49695 |  | a2d19dee27506d296bfea5fd23a8509e | 6.9 | 网络到货（含开箱验货） | 2 | 49933100b7bbf12f6eafe81922f0875d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行网络到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-10 09:43:50 | 21 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49633 |  | a2e5b09dbb0b5f9ae908fe7437c6fc5d | 6.9 | 网络到货（含开箱验货） | 2 | a1cfb4ec8e18404017fa40df1bca7ddd | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行网络到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-13 00:00:00 | 2026-01-13 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:33:54 | 13 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49853 |  | a30c8cdf5b2353e6c48ba8ec5e84b396 | 9.4 | 线序及光链路质量排查 | 2 | 101a6de57d32e63d5bb5c737a2136aa5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-18进行线序及光链路质量排查活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-26 00:00:00 | 2026-03-30 00:00:00 | 2026-03-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-02 19:15:46 |  | { "device_list": [] } |  | B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08 |  | 100%
49678 |  | a38bee2dca0e5845a82f682d61ab984b | 6.2 | 计算柜到货（含开箱验货） | 2 | 49933100b7bbf12f6eafe81922f0875d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行计算柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-10 09:43:50 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49685 |  | a41c351f1d77a1865440fa61f72ed499 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 0f8cc620095af38d62109166a5af7bc4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-22 00:00:00 | 2026-03-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-04-02 19:12:36 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49548 |  | a5509dbfc0ddd88c2b793fbec3a55cbe | 3.0 | 工程勘测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-17至2025-12-27进行工程勘测活动，确保工程勘测顺利进行。 | { "device_list": [] } | manage_agent | survey_agent | 2025-12-17 00:00:00 | 2025-12-27 00:00:00 | 2025-12-19 00:00:00 | 2025-12-29 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:45:36 |  | { "device_list": [] }
49708 |  | a56aa08b3751388294278c3eeaa99751 | 7.3 | 综合布线与成端-灵衢线缆 | 2 | 5711bf7d585084aa21011f8708cc8f26 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-06至2026-01-17进行综合布线与成端-灵衢线缆活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2026-01-06 00:00:00 | 2026-03-15 00:00:00 | 2026-01-11 00:00:00 | 2026-03-20 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-20 00:00:00 | 22 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH402-POD08 |  | 100%
49600 |  | a662a0bb4a9c160f668318b7ef332825 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-26 00:00:00 | 2026-01-29 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:53:36 | 8 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49690 |  | a6a62289c68ba2d72d24512289138381 | 7.23 | 总线设备柜设备上电 | 2 | 130bd396a173514f6052d60408189852 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-07至2026-03-08进行总线设备柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-16 00:00:00 | 2026-03-17 00:00:00 | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-20 00:00:00 | 20 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49825 |  | a75d34592138b7696c60078a8dd00820 | 8.15 | 网络子系统验证 | 2 | dc4fd9bf53efce590628780fd29f44a8 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-29至2026-01-31进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-25 00:00:00 | 2026-01-25 00:00:00 | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:42:29 | 37 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49666 |  | aa81557117d1255026a65273b69be936 | 7.14 | 网络设备上电 | 2 | 0a42ee3f371d80abc73b66a46d67254f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-07进行网络设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-07 00:00:00 |  |  | 未开始 | 0% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-21 00:00:00 | 17 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49819 |  | abdd99391d90464afef903496858d666 | 6.9 | 网络到货（含开箱验货） | 2 | 4f1622107208a82e5379e84235c8076b | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-18进行网络到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | other_assistant | 2026-01-18 00:00:00 | 2026-01-18 00:00:00 | 2026-01-20 00:00:00 | 2026-01-20 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:40:44 | 37 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49580 |  | ad4cc73ce79dc239794414b964a1ccee | 7.0 | 工程安装 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-02至2026-01-26进行工程安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2025-12-02 00:00:00 | 2026-01-28 00:00:00 | 2025-12-04 00:00:00 | 2026-01-30 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 00:48:02 |  | { "device_list": [] } |  | B2DH401-POD01
49573 |  | ad7dcc3b38079670b30fe66523f32f81 | 7.14 | 网络设备上电 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-13进行网络设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-13 00:00:00 | 2026-01-14 00:00:00 | 2026-01-15 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-01-25 00:00:00 | 5 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49655 |  | ae7b89afee87414fbacfd95cdbda72c7 | 8.12 | 计算子系统验证-智算服务器 | 2 | fe360f4b58153382f33ce7e61e7e0db5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-18进行计算子系统验证-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-27 00:00:00 | 2026-03-28 00:00:00 | 2026-03-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-04-02 19:13:37 | 15 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49607 |  | ae9d8cb472ef2d8ff07ca763fa1f2bd4 | 8.7 | 网络子系统部署调测 | 2 | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-16至2026-01-20进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-16 00:00:00 | 2026-01-20 00:00:00 | 2026-01-21 00:00:00 | 2026-01-25 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:53:24 | 9 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49746 |  | af4336b71ffa2a93a6395ece6354be5d | 8.6 | 智算硬件压测 | 2 | 00213f32bd359e146829c8b6e81e054d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-28 00:00:00 | 2026-01-28 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 09:52:21 | 27 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49536 |  | b02d99d4db04de8250d6810cf063f0d4 | 3.4 | 工程勘测报告评审 | 2 | a5509dbfc0ddd88c2b793fbec3a55cbe | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-25至2025-12-27进行工程勘测报告评审活动，确保工程勘测顺利进行。 | { "device_list": [] } | manage_agent | survey_agent | 2025-12-25 00:00:00 | 2025-12-27 00:00:00 | 2025-12-27 00:00:00 | 2025-12-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:45:36 |  | { "device_list": [] } |  |  |  | 100%
49620 |  | b094d5269f06624e69986959a741b3c8 | 7.21 | 液冷计算柜验收 | 2 | 39f755adca700a886f962ce3bac181bc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-26进行液冷计算柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-22 00:00:00 | 2026-01-28 00:00:00 | 2026-01-25 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 08:34:45 | 11 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49532 |  | b0c54fb744d19fe7db99fce7b4d38803 | 2.3 | 机房改造实施 | 2 | a0dbd5ad0477b318aad9cea926d954d3 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-01至2025-12-01进行机房改造实施活动，确保L1机房准备顺利进行。 | { "device_list": [] } | manage_agent | other_assistant | 2025-12-01 00:00:00 | 2025-12-01 00:00:00 | 2025-12-03 00:00:00 | 2025-12-03 00:00:00 | 已完成 | 100% | 严浩丁 00635652 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 08:30:43 |  | { "device_list": [] } |  |  |  | 100%
49745 |  | b0cfaf3991d660fd90982b09093f6739 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 00213f32bd359e146829c8b6e81e054d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 2026-01-26 00:00:00 | 2026-01-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 09:52:17 | 27 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49713 |  | b2e9195387db68382e85ba2af72017b2 | 7.21 | 液冷计算柜验收 | 2 | 5711bf7d585084aa21011f8708cc8f26 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-15进行液冷计算柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-18 00:00:00 | 2026-03-24 00:00:00 | 2026-03-23 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-15 20:46:35 | 23 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49610 |  | b42abb2c92f1b1889620005fbc34448d | 6.0 | 到货 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-11进行到货活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-11 00:00:00 | 2026-01-10 00:00:00 | 2026-01-16 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:53:06 |  | { "device_list": [] } |  | B2DH401-POD04
49665 |  | b4fe0dd545526e7160fccf87dfb280a1 | 7.13 | 网络设备安装 | 2 | 0a42ee3f371d80abc73b66a46d67254f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-05至2026-03-05进行网络设备安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-05 00:00:00 | 2026-03-05 00:00:00 | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-10 09:55:40 | 17 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49768 |  | b54bba420a74d18a9f17858c109c828e | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-28进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-27 00:00:00 | 2026-01-25 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 09:52:43 |  | { "device_list": [] } |  | B2DH401-POD03 |  | 100%
49718 |  | b55e557d17de51fc650d098584c928af | 9.1 | 计算管理系统对接 | 2 | da48302d975b092db03c9e1966a610eb | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-17进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-25 00:00:00 | 2026-03-30 00:00:00 | 2026-03-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-04-02 19:15:24 | 23 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49643 |  | b5f402b29414deadb16f17861def8194 | 8.0 | 单机调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-29进行单机调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-14 00:00:00 | 2026-01-29 00:00:00 | 2026-01-17 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:35:36 |  | { "device_list": [] } |  | B2DH401-POD02
49577 |  | b640ce99d351e4ed2c83d6b149050d42 | 8.15 | 网络子系统验证 | 2 | d67315c919da4515dcd27f7f8cee0fd4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-23进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-23 00:00:00 | 2026-01-23 00:00:00 | 2026-01-25 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 08:31:20 | 5 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49802 |  | b6591410b8e3236f5d7c9f36749aab27 | 6.2 | 计算柜到货（含开箱验货） | 2 | 4f1622107208a82e5379e84235c8076b | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-18进行计算柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-18 00:00:00 | 2026-01-18 00:00:00 | 2026-01-20 00:00:00 | 2026-01-20 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 08:40:32 | 35 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49753 |  | b6cb935da339d798180ba6147fde9788 | 7.24 | 总线设备柜验收 | 2 | d6c4fa9c7e400667870077b23e88f967 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-26进行总线设备柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-22 00:00:00 | 2026-01-28 00:00:00 | 2026-01-26 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 08:37:00 | 28 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49842 |  | b782d872685360e1a587f4ad725d26ae | 9.4 | 线序及光链路质量排查 | 2 | f9ac2503e56fa2240efefcc3aba5828a | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-30至2026-02-01进行线序及光链路质量排查活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 2026-01-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 09:59:25 |  | { "device_list": [] } |  | B2DH403-POD09 |  | 100%
49608 |  | b7934605b06fa10a4c6c6a61733f9116 | 8.15 | 网络子系统验证 | 2 | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-23进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-23 00:00:00 | 2026-01-26 00:00:00 | 2026-01-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:53:28 | 9 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49572 |  | b90f83ca8bf9672f3336cfe971778dcb | 7.13 | 网络设备安装 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-11至2026-01-11进行网络设备安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-11 00:00:00 | 2026-01-11 00:00:00 | 2026-01-13 00:00:00 | 2026-01-13 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 00:47:31 | 5 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49744 |  | ba6797ace09105884e3ec4e0fd64bcf2 | 7.21 | 液冷计算柜验收 | 2 | d6c4fa9c7e400667870077b23e88f967 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-26进行液冷计算柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-22 00:00:00 | 2026-01-28 00:00:00 | 2026-01-26 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 08:37:16 | 27 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49733 |  | bb732f39d7fa092d3e3a8c1418f58f86 | 9.2 | 网络管理系统对接 | 2 | da48302d975b092db03c9e1966a610eb | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-16进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-15 00:00:00 | 2026-03-20 00:00:00 | 2026-03-20 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-04-02 19:15:19 | 25 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49710 |  | bbaf6e211ab6cc6610ef80ca128de7d3 | 6.11 | 转运与设备静置 | 2 | 974f1dbc336d0a548d8c0446ef1588c7 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-05至2026-03-05进行转运与设备静置活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-05 00:00:00 | 2026-03-05 00:00:00 | 2026-03-10 00:00:00 | 2026-03-10 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-10 00:00:00 | 23 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49844 |  | bc1e42d03d744e36d0d09341c1c9fe1c | 9.6 | 集群通信配置测试 | 2 | f9ac2503e56fa2240efefcc3aba5828a | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-06至2026-02-07进行集群通信配置测试活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-29 00:00:00 | 2026-01-29 00:00:00 | 2026-01-31 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-03-10 09:59:38 |  | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49762 |  | bd41eab07818814111503639b7f56d3d | 8.7 | 网络子系统部署调测 | 2 | 00213f32bd359e146829c8b6e81e054d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-16至2026-01-20进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-16 00:00:00 | 2026-01-20 00:00:00 | 2026-01-20 00:00:00 | 2026-01-24 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 09:51:55 | 29 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49869 |  | bd449a75f8efbcaabaa38a7f494228c6-B2DH401-POD02 | 12.4-B2DH401-POD02 | 移交 | 2 | fae29171999e359cf40c83e23c9da541 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-28至2026-03-01进行移交活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-04 00:00:00 | 2026-02-04 00:00:00 | 2026-02-07 00:00:00 | 2026-02-07 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-02-08 00:00:00 |  | { "device_list": [] } |  | B2DH401-POD02 |  | 100%
49870 |  | bd449a75f8efbcaabaa38a7f494228c6-B2DH401-POD03 | 12.4-B2DH401-POD03 | 移交 | 2 | fae29171999e359cf40c83e23c9da541 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-28至2026-03-01进行移交活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-04 00:00:00 | 2026-02-04 00:00:00 | 2026-02-08 00:00:00 | 2026-02-08 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-02-09 00:00:00 |  | { "device_list": [] } |  | B2DH401-POD03 |  | 100%
49871 |  | bd449a75f8efbcaabaa38a7f494228c6-B2DH401-POD04 | 12.4-B2DH401-POD04 | 移交 | 2 | fae29171999e359cf40c83e23c9da541 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-28至2026-03-01进行移交活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-04 00:00:00 | 2026-02-04 00:00:00 | 2026-02-09 00:00:00 | 2026-02-09 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-02-10 00:00:00 |  | { "device_list": [] } |  | B2DH401-POD04 |  | 100%
49702 |  | bfa119ccc5f4e15bad5c403f47040b9a | 9.2 | 网络管理系统对接 | 2 | ed8aa2bb2319bb51c9f0f6c340ce306b | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-16进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-16 00:00:00 | 2026-03-17 00:00:00 | 2026-03-18 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-04-02 19:12:55 | 21 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49602 |  | bfc0050d630dc09d57e98f374e25c350 | 6.9 | 网络到货（含开箱验货） | 2 | b42abb2c92f1b1889620005fbc34448d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行网络到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-15 00:00:00 | 2026-01-15 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:53:06 | 9 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49535 |  | bffd65ee0410b5ccedb944b3c3abec48 | 3.3 | 输出工勘报告 | 2 | a5509dbfc0ddd88c2b793fbec3a55cbe | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-20至2025-12-24进行输出工勘报告活动，确保工程勘测顺利进行。 | { "device_list": [] } | manage_agent | survey_agent | 2025-12-20 00:00:00 | 2025-12-24 00:00:00 | 2025-12-22 00:00:00 | 2025-12-26 00:00:00 | 已完成 | 100% | 侯克照 00578443 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:45:32 |  | { "device_list": [] } |  |  |  | 100%
49698 |  | c00e2290b1b8185beafa1f1bf4f5b57b | 7.15 | 网络设备硬件验收 | 2 | 130bd396a173514f6052d60408189852 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-08进行网络设备硬件验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 2026-03-10 00:00:00 | 2026-03-10 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-15 20:43:08 | 21 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49570 |  | c0113ee3e287b8c18d94e0121c11beb9 | 8.13 | 计算子系统验证-灵衢网络 | 2 | d67315c919da4515dcd27f7f8cee0fd4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-29进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 2026-01-29 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 08:31:40 | 4 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49557 |  | c0b66ae2dd5cce71576c3b653d25adc0 | 7.20 | 液冷计算柜设备上电 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-19进行液冷计算柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-21 00:00:00 | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-01-25 00:00:00 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49634 |  | c0dcc0c3971cd6cd9d412933876cb3be | 7.13 | 网络设备安装 | 2 | 39f755adca700a886f962ce3bac181bc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-11至2026-01-11进行网络设备安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-11 00:00:00 | 2026-01-11 00:00:00 | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:34:07 | 13 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49732 |  | c19c4835b1fa460cdbe84d222feb25f4 | 8.15 | 网络子系统验证 | 2 | 150290f605b7b9c11fb814eb2fa4cb3f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-17进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-17 00:00:00 | 2026-03-20 00:00:00 | 2026-03-22 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-22 23:54:44 | 25 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49605 |  | c21d3cacb2cd9dfe231108e703e37307 | 7.15 | 网络设备硬件验收 | 2 | 92d8f9e053e5c6293b513d9bfef0b492 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-14进行网络设备硬件验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 2026-01-19 00:00:00 | 2026-01-19 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:42:44 | 9 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49646 |  | c366bd5250ba57540bd0a45d5076c7fe | 7.3 | 综合布线与成端-灵衢线缆 | 2 | 0a42ee3f371d80abc73b66a46d67254f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-06至2026-01-17进行综合布线与成端-灵衢线缆活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2026-01-06 00:00:00 | 2026-03-15 00:00:00 | 2026-01-09 00:00:00 |  | 进行中 | 45% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-18 00:00:00 | 14 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH402-POD06 |  | 100%
49789 |  | c443211f5334c21f12e5da9ed6a7caff | 7.13 | 网络设备安装 | 2 | 0d2365c84de5c6fbd95cb5b915b11daf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-05至2026-03-05进行网络设备安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-05 00:00:00 | 2026-03-05 00:00:00 | 2026-03-09 00:00:00 | 2026-03-09 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 09:56:25 | 33 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49832 |  | c4f33ed122e7e250c360994d8b409b26 | 9.5 | 综合布线整改 | 2 | f502cd626d2334d82791f460952855ff | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-30至2026-02-02进行综合布线整改活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-01-28 00:00:00 | 2026-01-28 00:00:00 | 2026-02-02 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-11 09:00:56 |  | { "device_list": [] } |  | B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04 |  | 100%
49872 |  | c61eaff3cda9bbdf089094797c43b0c0-B2DH402-POD05 | 9.8-B2DH402-POD05 | 集群性能调优 | 2 | 101a6de57d32e63d5bb5c737a2136aa5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-30至2026-04-01进行集群性能调优活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-01 00:00:00 | 2026-04-01 00:00:00 | 2026-04-03 00:00:00 | 2026-04-03 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-03 00:00:00 |  | { "device_list": [] } |  | B2DH402-POD05 |  | 100%
49873 |  | c61eaff3cda9bbdf089094797c43b0c0-B2DH402-POD06 | 9.8-B2DH402-POD06 | 集群性能调优 | 2 | 101a6de57d32e63d5bb5c737a2136aa5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-30至2026-04-01进行集群性能调优活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-01 00:00:00 | 2026-04-01 00:00:00 |  |  | 未开始 | 0% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-04 00:00:00 |  | { "device_list": [] } |  | B2DH402-POD06 |  | 100%
49874 |  | c61eaff3cda9bbdf089094797c43b0c0-B2DH402-POD07 | 9.8-B2DH402-POD07 | 集群性能调优 | 2 | 101a6de57d32e63d5bb5c737a2136aa5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-30至2026-04-01进行集群性能调优活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-01 00:00:00 | 2026-04-01 00:00:00 | 2026-04-05 00:00:00 | 2026-04-05 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-05 00:00:00 |  | { "device_list": [] } |  | B2DH402-POD07 |  | 100%
49875 |  | c61eaff3cda9bbdf089094797c43b0c0-B2DH402-POD08 | 9.8-B2DH402-POD08 | 集群性能调优 | 2 | 101a6de57d32e63d5bb5c737a2136aa5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-30至2026-04-01进行集群性能调优活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-01 00:00:00 | 2026-04-01 00:00:00 |  |  | 未开始 | 0% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-06 00:00:00 |  | { "device_list": [] } |  | B2DH402-POD08 |  | 100%
49761 |  | c79de657454717e0d77a812b702abb22 | 8.1 | 基础网络配置 | 2 | 00213f32bd359e146829c8b6e81e054d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-15进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-14 00:00:00 | 2026-01-15 00:00:00 | 2026-01-18 00:00:00 | 2026-01-19 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 09:51:50 | 29 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49582 |  | c7f11a1dd31dbdf48ee2751e8335e861 | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-28进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-27 00:00:00 | 2026-01-23 00:00:00 | 2026-01-29 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 08:33:28 |  | { "device_list": [] } |  | B2DH401-POD01
49741 |  | c99cd977e6d30863e62a271905edc1e3 | 6.11 | 转运与设备静置 | 2 | e4ce39e2aff0d3dd2cfa93d47331d18e | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-11至2026-01-11进行转运与设备静置活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-11 00:00:00 | 2026-01-11 00:00:00 | 2026-01-15 00:00:00 | 2026-01-15 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-01-15 00:00:00 | 27 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49590 |  | cb9ad2f65d546efae7982ab24299cd79 | 8.2 | 设备硬装初始化-智算服务器 | 2 | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 2026-01-27 00:00:00 | 2026-01-28 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:53:44 | 7 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49682 |  | cbf62e265301809c2a8fa3bbaf9110e5 | 7.21 | 液冷计算柜验收 | 2 | 130bd396a173514f6052d60408189852 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-15进行液冷计算柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-18 00:00:00 | 2026-03-24 00:00:00 | 2026-03-20 00:00:00 | 2026-03-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-15 20:43:41 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49831 |  | cc7949f165cbeb9a1a4e71e343e3aa24 | 9.4 | 线序及光链路质量排查 | 2 | f502cd626d2334d82791f460952855ff | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-29进行线序及光链路质量排查活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-02-01 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-11 09:02:26 |  | { "device_list": [] } |  | B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04 |  | 100%
49743 |  | cfe686ef45fb83f615c2287b258d1ccf | 7.20 | 液冷计算柜设备上电 | 2 | d6c4fa9c7e400667870077b23e88f967 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-18至2026-01-19进行液冷计算柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-21 00:00:00 | 2026-01-24 00:00:00 | 2026-01-25 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-01-28 00:00:00 | 27 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49586 |  | d004703e5c3df9f8e649f15e952dc59e | 6.11 | 转运与设备静置 | 2 | b42abb2c92f1b1889620005fbc34448d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-11至2026-01-11进行转运与设备静置活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-11 00:00:00 | 2026-01-11 00:00:00 | 2026-01-16 00:00:00 | 2026-01-16 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-01-16 00:00:00 | 7 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49845 |  | d0586f5b6dddc1c6a430b31b38a66b78 | 9.7 | 集群系统集成测试 | 2 | f9ac2503e56fa2240efefcc3aba5828a | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-08至2026-02-12进行集群系统集成测试活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-30 00:00:00 | 2026-01-30 00:00:00 | 2026-02-01 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-03-10 09:59:42 |  | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49629 |  | d10989f7fd7ded8aeb4814bd989c78db | 7.24 | 总线设备柜验收 | 2 | 39f755adca700a886f962ce3bac181bc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-26进行总线设备柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-22 00:00:00 | 2026-01-28 00:00:00 | 2026-01-25 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:34:30 | 12 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49551 |  | d1bc999d07dada5c5291b6808e344f84 | 6.5 | 灵衢线缆到货（含开箱验货） | 2 | f52853c9677b1938411df3cedf812acc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-05进行灵衢线缆到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-05 00:00:00 | 2026-01-07 00:00:00 | 2026-01-07 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:47:03 | 2 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH401-POD01 |  | 100%
49769 |  | d3a7341a88d24ef284d0781f30253d46 | 6.5 | 灵衢线缆到货（含开箱验货） | 2 | 7b49cc45f3121c22f06324dce60e6c64 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-05进行灵衢线缆到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-05 00:00:00 | 2026-01-09 00:00:00 | 2026-01-09 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 10:10:37 | 30 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH402-POD07 |  | 100%
49567 |  | d3a8b00f2775beb76bdff75cdc597206 | 7.24 | 总线设备柜验收 | 2 | ad4cc73ce79dc239794414b964a1ccee | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-26进行总线设备柜验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-22 00:00:00 | 2026-01-28 00:00:00 | 2026-01-24 00:00:00 | 2026-01-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:47:51 | 4 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49729 |  | d3c6e655c26af8c10ab120192c117d67 | 7.15 | 网络设备硬件验收 | 2 | 5711bf7d585084aa21011f8708cc8f26 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-08进行网络设备硬件验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 2026-03-13 00:00:00 | 2026-03-13 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-15 20:46:08 | 25 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49592 |  | d5546b006ae368ad9395159acdf67664 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 39b4df4d06a5dfe67bc7db7f22d7e6c9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-26 00:00:00 | 2026-01-29 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:53:52 | 7 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49640 |  | d5d71bdf42f508c5ecf6ba3a53b0858c | 9.2 | 网络管理系统对接 | 2 | 097cb011d565cd09f42c3de80111c703 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-22进行网络管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-21 00:00:00 | 2026-01-24 00:00:00 | 2026-01-24 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:35:43 | 13 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49581 |  | d67315c919da4515dcd27f7f8cee0fd4 | 8.0 | 单机调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-29进行单机调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-14 00:00:00 | 2026-01-29 00:00:00 | 2026-01-16 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 08:33:17 |  | { "device_list": [] } |  | B2DH401-POD01
49766 |  | d6c4fa9c7e400667870077b23e88f967 | 7.0 | 工程安装 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-02至2026-01-26进行工程安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2025-12-02 00:00:00 | 2026-01-28 00:00:00 | 2025-12-06 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 08:37:16 |  | { "device_list": [] } |  | B2DH401-POD03
49773 |  | d7f8738bb0b1611f19f25064eef6b828 | 7.19 | 液冷计算柜安装 | 2 | 0d2365c84de5c6fbd95cb5b915b11daf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-06进行液冷计算柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 2026-03-10 00:00:00 | 2026-03-10 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-11 08:54:34 | 31 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49621 |  | d866e8ed5f47ed2ab4aad74f9b5cb634 | 8.2 | 设备硬装初始化-智算服务器 | 2 | b5f402b29414deadb16f17861def8194 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-21进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 2026-01-25 00:00:00 | 2026-01-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 08:35:21 | 11 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49692 |  | d99077850b80ecfa008f68d52b281a89 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | 0f8cc620095af38d62109166a5af7bc4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-10进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 2026-03-20 00:00:00 | 2026-03-21 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-22 23:51:12 | 20 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49740 |  | d9ca893fe7040acbaf36eb6515e493ce | 6.2 | 计算柜到货（含开箱验货） | 2 | e4ce39e2aff0d3dd2cfa93d47331d18e | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行计算柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 08:36:06 | 27 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49737 |  | da48302d975b092db03c9e1966a610eb | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-17进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-25 00:00:00 | 2026-03-20 00:00:00 | 2026-03-30 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-04-02 19:15:24 |  | { "device_list": [] } |  | B2DH402-POD08
49829 |  | dc4fd9bf53efce590628780fd29f44a8 | 8.0 | 单机调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-02-01进行单机调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-22 00:00:00 | 2026-01-27 00:00:00 | 2026-01-24 00:00:00 | 2026-01-29 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 09:58:12 |  | { "device_list": [] } |  | B2DH403-POD09
49823 |  | dd0a8ca78bbf47f874fc0c90901eba19 | 8.1 | 基础网络配置 | 2 | dc4fd9bf53efce590628780fd29f44a8 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-23进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 2026-01-24 00:00:00 | 2026-01-25 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 08:42:16 | 37 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49852 |  | dd183b97366f3e6338d7bcdc1464d2ea | 12.0 | 验收测试 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-13至2026-03-04进行验收测试活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-01-31 00:00:00 | 2026-02-04 00:00:00 | 2026-02-02 00:00:00 | 2026-02-06 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-03-10 10:00:10 |  | { "device_list": [] } |  | B2DH403-POD09 |  | 100%
49711 |  | ddcde316d2ad9e687664230c65f30c17 | 7.19 | 液冷计算柜安装 | 2 | 5711bf7d585084aa21011f8708cc8f26 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-06进行液冷计算柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 2026-03-11 00:00:00 | 2026-03-11 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-11 08:54:39 | 23 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49544 |  | def04905cc6ecfecc33b01ca7d7bb1db | 5.4 | 存储子系统LLD设计 | 2 | 9d902ce7baa85aa0b3573c7dc4634011 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-28至2026-01-01进行存储子系统LLD设计活动，确保低阶设计顺利进行。 | { "device_list": [] } | manage_agent | design_agent | 2025-12-28 00:00:00 | 2026-01-01 00:00:00 | 2025-12-30 00:00:00 | 2026-01-03 00:00:00 | 已完成 | 100% | 张杨 00543862 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:46:48 |  | { "device_list": [] } |  |  |  | 100%
49747 |  | df8c04144166943812a92e45efa936c2 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 00213f32bd359e146829c8b6e81e054d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-26 00:00:00 | 2026-01-28 00:00:00 | 2026-01-30 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 09:52:25 | 27 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49638 |  | dfa753ed56be297a2b2bfbc9266b872c | 8.7 | 网络子系统部署调测 | 2 | b5f402b29414deadb16f17861def8194 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-16至2026-01-20进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-16 00:00:00 | 2026-01-20 00:00:00 | 2026-01-19 00:00:00 | 2026-01-23 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:34:56 | 13 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49684 |  | e00878eb9bafd279d0457c1f5de4ecc7 | 8.6 | 智算硬件压测 | 2 | 0f8cc620095af38d62109166a5af7bc4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-22 00:00:00 | 2026-03-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-22 23:50:17 | 19 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49613 |  | e0f5b7502c728cdf7af677ef58bdf1d0 | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-21至2026-01-28进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-21 00:00:00 | 2026-01-27 00:00:00 | 2026-01-26 00:00:00 | 2026-02-01 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 09:54:15 |  | { "device_list": [] } |  | B2DH401-POD04 |  | 100%
49541 |  | e3f6918109e8d6f2e3ea5cc13a02cdf1 | 5.1 | 集群LLD设计 | 2 | 9d902ce7baa85aa0b3573c7dc4634011 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2025-12-28至2026-01-01进行集群LLD设计活动，确保低阶设计顺利进行。 | { "device_list": [] } | manage_agent | design_agent | 2025-12-28 00:00:00 | 2026-01-01 00:00:00 | 2025-12-30 00:00:00 | 2026-01-03 00:00:00 | 已完成 | 100% | 张杨 00543862 | 华为 |  | l00880586 | 2026-03-09 23:40:40 | l00880586 | 2026-03-10 00:46:54 |  | { "device_list": [] } |  |  |  | 100%
49765 |  | e4ce39e2aff0d3dd2cfa93d47331d18e | 6.0 | 到货 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-11进行到货活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-11 00:00:00 | 2026-01-09 00:00:00 | 2026-01-15 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 08:36:18 |  | { "device_list": [] } |  | B2DH401-POD03
49653 |  | e4e7e8af27b9afbfc5a0f3cbce28bb8f | 8.6 | 智算硬件压测 | 2 | fe360f4b58153382f33ce7e61e7e0db5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行智算硬件压测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-23 00:00:00 | 2026-03-27 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-22 23:50:24 | 15 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49631 |  | e72933f178dc98e290c67c385d695702 | 8.10 | 计算子系统部署调测-灵衢网络 | 2 | b5f402b29414deadb16f17861def8194 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-22至2026-01-26进行计算子系统部署调测-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-24 00:00:00 | 2026-01-26 00:00:00 | 2026-01-27 00:00:00 | 2026-01-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:35:11 | 12 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49652 |  | e78226e836e03524cbf62093e03e94ca | 8.2 | 设备硬装初始化-智算服务器 | 2 | fe360f4b58153382f33ce7e61e7e0db5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-09至2026-03-10进行设备硬装初始化-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-18 00:00:00 | 2026-03-19 00:00:00 | 2026-03-21 00:00:00 | 2026-03-22 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-22 23:51:48 | 15 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49688 |  | e7ccc372665d7833851344424c5fa7b7 | 6.3 | 总线设备柜到货（含开箱验货） | 2 | 49933100b7bbf12f6eafe81922f0875d | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行总线设备柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-06 00:00:00 | 2026-03-06 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-10 09:43:50 | 20 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49770 |  | e86576ebd63c3c633a74365f238dec65 | 7.3 | 综合布线与成端-灵衢线缆 | 2 | 0d2365c84de5c6fbd95cb5b915b11daf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-06至2026-01-17进行综合布线与成端-灵衢线缆活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2026-01-06 00:00:00 | 2026-03-15 00:00:00 | 2026-01-10 00:00:00 | 2026-03-19 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-19 00:00:00 | 30 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH402-POD07 |  | 100%
49657 |  | e9ba510af24819ef664cd08361804894 | 6.3 | 总线设备柜到货（含开箱验货） | 2 | 15225ba7ad316e6a0f70b2424fcabe1c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行总线设备柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-07 00:00:00 | 2026-03-07 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-10 10:10:11 | 16 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49850 |  | ea290e51e9731d060dd7870bd7ce4b62 | 12.4 | 移交 | 2 | dd183b97366f3e6338d7bcdc1464d2ea | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-03至2026-03-04进行移交活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-03 00:00:00 | 2026-02-04 00:00:00 | 2026-02-05 00:00:00 | 2026-02-06 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-02-06 00:00:00 |  | { "device_list": [] } |  | B2DH403-POD09 |  | 100%
49781 |  | ea4a6f4e188aebddfc84d4c586e50327 | 6.3 | 总线设备柜到货（含开箱验货） | 2 | 7b49cc45f3121c22f06324dce60e6c64 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-04至2026-03-04进行总线设备柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-03-04 00:00:00 | 2026-03-04 00:00:00 | 2026-03-08 00:00:00 | 2026-03-08 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 10:10:41 | 32 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49706 |  | ed8aa2bb2319bb51c9f0f6c340ce306b | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-17进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-26 00:00:00 | 2026-03-17 00:00:00 | 2026-03-28 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-04-02 19:13:03 |  | { "device_list": [] } |  | B2DH402-POD05
49876 |  | ee914e09bbe701a12a53d7f534422a0d-B2DH402-POD05 | 12.4-B2DH402-POD05 | 移交 | 2 | 9f85b7d5cb45132378d790a0cf6120cf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-04-17至2026-04-18进行移交活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-04 00:00:00 | 2026-04-04 00:00:00 | 2026-04-06 00:00:00 | 2026-04-06 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-06 00:00:00 |  | { "device_list": [] } |  | B2DH402-POD05 |  | 100%
49877 |  | ee914e09bbe701a12a53d7f534422a0d-B2DH402-POD06 | 12.4-B2DH402-POD06 | 移交 | 2 | 9f85b7d5cb45132378d790a0cf6120cf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-04-17至2026-04-18进行移交活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-04 00:00:00 | 2026-04-04 00:00:00 |  |  | 未开始 | 0% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-07 00:00:00 |  | { "device_list": [] } |  | B2DH402-POD06 |  | 100%
49878 |  | ee914e09bbe701a12a53d7f534422a0d-B2DH402-POD07 | 12.4-B2DH402-POD07 | 移交 | 2 | 9f85b7d5cb45132378d790a0cf6120cf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-04-17至2026-04-18进行移交活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-04 00:00:00 | 2026-04-04 00:00:00 | 2026-04-08 00:00:00 | 2026-04-08 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-08 00:00:00 |  | { "device_list": [] } |  | B2DH402-POD07 |  | 100%
49879 |  | ee914e09bbe701a12a53d7f534422a0d-B2DH402-POD08 | 12.4-B2DH402-POD08 | 移交 | 2 | 9f85b7d5cb45132378d790a0cf6120cf | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-04-17至2026-04-18进行移交活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-04-04 00:00:00 | 2026-04-04 00:00:00 |  |  | 未开始 | 0% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-09 00:00:00 |  | { "device_list": [] } |  | B2DH402-POD08 |  | 100%
49576 |  | ef24a08c1071192ce5463f304eb4c63e | 8.7 | 网络子系统部署调测 | 2 | d67315c919da4515dcd27f7f8cee0fd4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-16至2026-01-20进行网络子系统部署调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-16 00:00:00 | 2026-01-20 00:00:00 | 2026-01-18 00:00:00 | 2026-01-22 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 08:31:05 | 5 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49636 |  | ef298d30e1c87748671248665c466ed9 | 7.15 | 网络设备硬件验收 | 2 | 39f755adca700a886f962ce3bac181bc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-14进行网络设备硬件验收活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 2026-01-17 00:00:00 | 2026-01-17 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:34:15 | 13 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49575 |  | ef8fc1c3be87b126f48ff45d19fa2340 | 8.1 | 基础网络配置 | 2 | d67315c919da4515dcd27f7f8cee0fd4 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-14至2026-01-15进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-01-14 00:00:00 | 2026-01-15 00:00:00 | 2026-01-16 00:00:00 | 2026-01-17 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 00:48:10 | 5 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49794 |  | f0170d59e49060a96433657bc21f602e | 8.15 | 网络子系统验证 | 2 | 7a21404db97a2a7184547a95c4f4a28c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-15至2026-03-17进行网络子系统验证活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-15 00:00:00 | 2026-03-17 00:00:00 | 2026-03-19 00:00:00 | 2026-03-21 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-22 23:54:40 | 33 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49614 |  | f1753b5f61a587b8d735f041e47c11a3 | 6.5 | 灵衢线缆到货（含开箱验货） | 2 | a1cfb4ec8e18404017fa40df1bca7ddd | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-05进行灵衢线缆到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-05 00:00:00 | 2026-01-08 00:00:00 | 2026-01-08 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:43 | l00880586 | 2026-03-10 08:33:32 | 10 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH401-POD02 |  | 100%
49696 |  | f275d17e50428e4961dcd237780a2aea | 7.13 | 网络设备安装 | 2 | 130bd396a173514f6052d60408189852 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-05至2026-03-05进行网络设备安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-05 00:00:00 | 2026-03-05 00:00:00 | 2026-03-07 00:00:00 | 2026-03-07 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:46 | l00880586 | 2026-03-10 09:54:45 | 21 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD05 |  | 100%
49630 |  | f2ae0903f800bd7c94804250994b0367 | 8.5 | 设备硬装初始化-灵衢网络 | 2 | b5f402b29414deadb16f17861def8194 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-21进行设备硬装初始化-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-22 00:00:00 | 2026-01-23 00:00:00 | 2026-01-25 00:00:00 | 2026-01-26 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:44 | l00880586 | 2026-03-10 08:35:06 | 12 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD02 |  | 100%
49758 |  | f2ec812a70d77043f94d3b8f3a0a0724 | 7.13 | 网络设备安装 | 2 | d6c4fa9c7e400667870077b23e88f967 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-11至2026-01-11进行网络设备安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-01-11 00:00:00 | 2026-01-11 00:00:00 | 2026-01-15 00:00:00 | 2026-01-15 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:49 | l00880586 | 2026-03-10 08:36:34 | 29 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49656 |  | f38ca32fcfc00a772ffc0eddec40bc7c | 9.1 | 计算管理系统对接 | 2 | 30007f6ecaa7d88df89066d8ba4b0173 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-17进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-26 00:00:00 | 2026-03-28 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-04-02 19:13:51 | 15 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD06 |  | 100%
49840 |  | f502cd626d2334d82791f460952855ff | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-02-12进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-02-01 00:00:00 | 2026-02-01 00:00:00 | 2026-02-06 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-11 09:02:26 |  | { "device_list": [] } |  | B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04 |  | 100%
49579 |  | f52853c9677b1938411df3cedf812acc | 6.0 | 到货 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-05至2026-01-11进行到货活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" }, { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | other_assistant | 2026-01-05 00:00:00 | 2026-01-11 00:00:00 | 2026-01-07 00:00:00 | 2026-01-13 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 00:47:19 |  | { "device_list": [] } |  | B2DH401-POD01
49854 |  | f699e3baaab73e2344ac140032a2e73e | 9.5 | 综合布线整改 | 2 | 101a6de57d32e63d5bb5c737a2136aa5 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-19至2026-03-22进行综合布线整改活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-03-27 00:00:00 | 2026-03-29 00:00:00 | 2026-04-01 00:00:00 | 2026-04-03 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-04-02 19:15:53 |  | { "device_list": [] } |  | B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08 |  | 100%
49838 |  | f6dba523fc57621812c83fb427c0cb61 | 12.3 | 验收报告沟通 | 2 | fae29171999e359cf40c83e23c9da541 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-25至2026-02-27进行验收报告沟通活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-03 00:00:00 | 2026-02-03 00:00:00 | 2026-02-08 00:00:00 | 2026-02-08 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 09:59:00 |  | { "device_list": [] } |  | B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04 |  | 100%
49596 |  | f7550740505a2df7c3b571d120d83b0a | 7.22 | 总线设备柜安装 | 2 | 92d8f9e053e5c6293b513d9bfef0b492 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-12至2026-01-12进行总线设备柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 2026-01-17 00:00:00 | 2026-01-17 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:42 | l00880586 | 2026-03-10 09:42:44 | 8 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH401-POD04 |  | 100%
49757 |  | f96cda32cb3bb810541455b9d0cffdef | 6.9 | 网络到货（含开箱验货） | 2 | e4ce39e2aff0d3dd2cfa93d47331d18e | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行网络到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-14 00:00:00 | 2026-01-14 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 08:36:18 | 29 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49851 |  | f9ac2503e56fa2240efefcc3aba5828a | 9.0 | 集群调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-30至2026-02-15进行集群调测活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-31 00:00:00 | 2026-01-29 00:00:00 | 2026-02-02 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:52 | l00880586 | 2026-03-10 09:59:42 |  | { "device_list": [] } |  | B2DH403-POD09
49554 |  | fa4d23fc19b6531b1572e9dfe96c3a4a | 6.2 | 计算柜到货（含开箱验货） | 2 | f52853c9677b1938411df3cedf812acc | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-10至2026-01-10进行计算柜到货（含开箱验货）活动，确保到货顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | other_assistant | 2026-01-10 00:00:00 | 2026-01-10 00:00:00 | 2026-01-12 00:00:00 | 2026-01-12 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:41 | l00880586 | 2026-03-10 00:47:11 | 3 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD01 |  | 100%
49841 |  | fae29171999e359cf40c83e23c9da541 | 12.0 | 验收测试 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-10至2026-03-01进行验收测试活动，确保验收测试顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-01 00:00:00 | 2026-02-04 00:00:00 | 2026-02-06 00:00:00 | 2026-02-09 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-10 09:59:03 |  | { "device_list": [] } |  | B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04 |  | 100%
49716 |  | faef7c9ffa8d8520b5a51e24229bce94 | 8.8 | 计算子系统部署调测-智算服务器 | 2 | 150290f605b7b9c11fb814eb2fa4cb3f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-11至2026-03-15进行计算子系统部署调测-智算服务器活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-20 00:00:00 | 2026-03-24 00:00:00 | 2026-03-25 00:00:00 | 2026-03-29 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-04-02 19:15:08 | 23 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49787 |  | fb06cb014e170e5b220f6a88bcf56658 | 8.13 | 计算子系统验证-灵衢网络 | 2 | 7a21404db97a2a7184547a95c4f4a28c | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-16至2026-03-18进行计算子系统验证-灵衢网络活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-25 00:00:00 | 2026-03-27 00:00:00 | 2026-03-29 00:00:00 | 2026-03-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-04-02 19:14:10 | 32 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD07 |  | 100%
49721 |  | fc589d6855f97ed3098aa4c6ffaf045e | 7.23 | 总线设备柜设备上电 | 2 | 5711bf7d585084aa21011f8708cc8f26 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-07至2026-03-08进行总线设备柜设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-03-16 00:00:00 | 2026-03-17 00:00:00 | 2026-03-21 00:00:00 |  | 进行中 | 30% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-23 00:00:00 | 24 | { "device_list": [ { "device_model": "LingQu 630 V1", "quantity": 56, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49677 |  | fcf31e56b07e41a2ab6693622da25134 | 7.3 | 综合布线与成端-灵衢线缆 | 2 | 130bd396a173514f6052d60408189852 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-06至2026-01-17进行综合布线与成端-灵衢线缆活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } | manage_agent | installation_agent | 2026-01-06 00:00:00 | 2026-03-15 00:00:00 | 2026-01-08 00:00:00 | 2026-03-17 00:00:00 | 已完成 | 100% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-03-17 00:00:00 | 18 | { "device_list": [ { "device_model": "400G MPO线缆", "quantity": 2688, "unit": "根" } ] } |  | B2DH402-POD05 |  | 100%
49674 |  | fe360f4b58153382f33ce7e61e7e0db5 | 8.0 | 单机调测 | 1 | -1 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-18进行单机调测活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" }, { "device_model": "Atlas 900 A3 SuperPoD总线设备柜", "quantity": 4, "unit": "柜" }, { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-03-08 00:00:00 | 2026-03-27 00:00:00 | 2026-03-11 00:00:00 | 2026-03-30 00:00:00 | 已完成 | 100.00% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:45 | l00880586 | 2026-04-02 19:13:37 |  | { "device_list": [] } |  | B2DH402-POD06 |  | 100%
49730 |  | fe9ecfb7b6dc4ec9a94c91f1f3e31671 | 8.1 | 基础网络配置 | 2 | 150290f605b7b9c11fb814eb2fa4cb3f | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-08至2026-03-09进行基础网络配置活动，确保单机调测顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | deployment_agent | 2026-03-08 00:00:00 | 2026-03-09 00:00:00 | 2026-03-13 00:00:00 | 2026-03-14 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-19 18:41:13 | 25 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49728 |  | feddbb9ad4bb084c0787c6dda61daf52 | 7.14 | 网络设备上电 | 2 | 5711bf7d585084aa21011f8708cc8f26 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-03-06至2026-03-07进行网络设备上电活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } | manage_agent | installation_agent | 2026-03-06 00:00:00 | 2026-03-07 00:00:00 | 2026-03-11 00:00:00 |  | 进行中 | 30% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:47 | l00880586 | 2026-03-23 00:00:00 | 25 | { "device_list": [ { "device_model": "CE9866-128DQ", "quantity": 6, "unit": "台" } ] } |  | B2DH402-POD08 |  | 100%
49749 |  | ff0db7b6c27831d0f78bf241d476644b | 9.1 | 计算管理系统对接 | 2 | b54bba420a74d18a9f17858c109c828e | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-27至2026-01-28进行计算管理系统对接活动，确保集群调测顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | deployment_agent | 2026-01-27 00:00:00 | 2026-01-27 00:00:00 | 2026-01-31 00:00:00 | 2026-01-31 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:48 | l00880586 | 2026-03-10 09:52:43 | 27 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH401-POD03 |  | 100%
49804 |  | ff2fcfd67796a7446ecfaf9e6101f075 | 7.19 | 液冷计算柜安装 | 2 | 668de380b2c306cc4b6644ee75fe4ef9 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-01-20至2026-01-20进行液冷计算柜安装活动，确保工程安装顺利进行。 | { "device_list": [ { "device_model": "Atlas 900 A3 SuperPoD计算柜", "quantity": 12, "unit": "柜" } ] } | manage_agent | installation_agent | 2026-01-20 00:00:00 | 2026-01-22 00:00:00 | 2026-01-22 00:00:00 | 2026-01-24 00:00:00 | 已完成 | 100% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:50 | l00880586 | 2026-03-10 08:41:40 | 35 | { "device_list": [ { "device_model": "Atlas 900 A3", "quantity": 48, "unit": "台" } ] } |  | B2DH403-POD09 |  | 100%
49864 |  | 1a5f9192fb74861bc06e54102c144d9f | 9.8 | 集群性能调优 | 2 | f502cd626d2334d82791f460952855ff | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目，请从2026-02-10至2026-02-12进行集群性能调优活动，确保集群调测顺利进行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-02-01 00:00:00 | 2026-06-08 00:00:00 | 2026-02-03 00:00:00 |  | 进行中 | 65% | 张志宏 00464948 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-11 09:01:23 |  | { "device_list": [] } |  | B2DH401-POD01 |  | 65%
49865 |  | pod01-handover-pending-20260615 | 12.4-POD01 | 移交 | 2 | fae29171999e359cf40c83e23c9da541 | 6336ff05cffc4144aa6d96a87e66a36e | 项目编码 56A0TXN，项目名称 OTT10 2026年昇腾A3超节点9POD交付项目；POD01 上线尚未完成，移交顺延至上线完成后执行。 | { "device_list": [] } | manage_agent | deployment_agent | 2026-06-15 00:00:00 | 2026-06-15 00:00:00 |  |  | 未开始 | 0% | 徐宏斌 00908848 | 华为 |  | l00880586 | 2026-03-09 23:40:51 | l00880586 | 2026-03-12 00:00:00 |  | { "device_list": [] } | 因集群性能调优未完成，移交不得提前完成 | B2DH401-POD01 |  | 0%