## sheet0
REL_ID | SLA_VERSION | STAGE | VERSION | PROJECT_ID | PROJECT_SCENE | PRODUCT_FORM | COOLING_METHOD | ARRIVAL_FILE | MANAGEMENT_UNIT | SCHEDULE_DATA | STATUS | CREATED_AT | CREATED_BY
844 | 0 | 1 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  |  | [{"schedule_list": [{"activity": "机房改造实施", "end_at": "2025-12-01", "start_at": "2025-12-01", "primary_activity": "L1机房准备", "primary_activity_id": 2, "activity_id": "2.3"}, {"activity": "现场勘测", "start_at": "2025-12-17", "end_at": "2025-12-19", "primary_activity": "工程勘测", "primary_activity_id": 3, "activity_id": "3.1"}, {"activity": "远程视频辅助", "start_at": "2025-12-18", "end_at": "2025-12-19", "primary_activity": "工程勘测", "primary_activity_id": 3, "activity_id": "3.2"}, {"activity": "输出工勘报告", "start_at": "2025-12-20", "end_at": "2025-12-24", "primary_activity": "工程勘测", "primary_activity_id": 3, "activity_id": "3.3"}, {"activity": "工程勘测报告评审", "start_at": "2025-12-25", "end_at": "2025-12-27", "primary_activity": "工程勘测", "primary_activity_id": 3, "activity_id": "3.4"}, {"activity": "信息分析与确认", "start_at": "2025-12-20", "end_at": "2025-12-20", "primary_activity": "建模仿真", "primary_activity_id": 4, "activity_id": "4.1"}, {"activity": "建模仿真设计", "start_at": "2025-12-21", "end_at": "2025-12-25", "primary_activity": "建模仿真", "primary_activity_id": 4, "activity_id": "4.2"}, {"activity": "建模仿真初稿评审", "start_at": "2025-12-26", "end_at": "2025-12-26", "primary_activity": "建模仿真", "primary_activity_id": 4, "activity_id": "4.3"}, {"activity": "建模仿真终稿输出", "start_at": "2025-12-27", "end_at": "2025-12-27", "primary_activity": "建模仿真", "primary_activity_id": 4, "activity_id": "4.4"}, {"activity": "集群LLD设计", "start_at": "2025-12-28", "end_at": "2026-01-01", "primary_activity": "低阶设计", "primary_activity_id": 5, "activity_id": "5.1"}, {"activity": "计算子系统LLD设计", "start_at": "2025-12-28", "end_at": "2026-01-01", "primary_activity": "低阶设计", "primary_activity_id": 5, "activity_id": "5.2"}, {"activity": "网络子系统LLD设计", "start_at": "2025-12-28", "end_at": "2026-01-01", "primary_activity": "低阶设计", "primary_activity_id": 5, "activity_id": "5.3"}, {"activity": "存储子系统LLD设计", "start_at": "2025-12-28", "end_at": "2026-01-01", "primary_activity": "低阶设计", "primary_activity_id": 5, "activity_id": "5.4"}, {"activity": "集群验收方案设计", "start_at": "2025-12-28", "end_at": "2026-01-01", "primary_activity": "低阶设计", "primary_activity_id": 5, "activity_id": "5.6"}, {"activity": "低阶设计评审", "start_at": "2026-01-02", "end_at": "2026-01-04", "primary_activity": "低阶设计", "primary_activity_id": 5, "activity_id": "5.7"}]}] | 1 | 2026-03-09 21:54:53 | l00880586
845 | 0 | 2 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH401-POD01 | [{"management_unit": "B2DH401-POD01", "product_group_name": "灵衢线缆", "arrival_date": "2026-01-05", "end_date": "2026-01-17", "device_list": "400G MPO线缆 2688根", "schedule_list": [{"activity": "灵衢线缆到货（含开箱验货）", "activity_id": "6.5", "end_at": "2026-01-05", "start_at": "2026-01-05", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "机房洁净度测试", "start_at": "2025-12-02", "end_at": "2025-12-06", "activity_id": "7.1", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "综合布线与成端-灵衢线缆", "start_at": "2026-01-06", "end_at": "2026-01-17", "activity_id": "7.3", "primary_activity": "工程安装", "primary_activity_id": 7}]}, {"management_unit": "B2DH401-POD01", "product_group_name": "计算柜", "arrival_date": "2026-01-10", "end_date": "2026-01-29", "device_list": "Atlas 900 A3 SuperPoD计算柜 12柜", "schedule_list": [{"activity": "计算柜到货（含开箱验货）", "activity_id": "6.2", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "转运与设备静置", "start_at": "2026-01-11", "end_at": "2026-01-11", "activity_id": "6.11", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "液冷计算柜安装", "start_at": "2026-01-12", "end_at": "2026-01-12", "activity_id": "7.19", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜设备上电", "start_at": "2026-01-18", "end_at": "2026-01-19", "activity_id": "7.20", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜验收", "start_at": "2026-01-20", "end_at": "2026-01-26", "activity_id": "7.21", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-智算服务器", "start_at": "2026-01-20", "end_at": "2026-01-21", "activity_id": "8.2", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "智算硬件压测", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.6", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-智算服务器", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.8", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-智算服务器", "start_at": "2026-01-27", "end_at": "2026-01-29", "activity_id": "8.12", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算管理系统对接", "start_at": "2026-01-27", "end_at": "2026-01-28", "activity_id": "9.1", "primary_activity": "集群调测", "primary_activity_id": 9}]}, {"management_unit": "B2DH401-POD01", "product_group_name": "总线设备柜", "arrival_date": "2026-01-10", "end_date": "2026-01-29", "device_list": "Atlas 900 A3 SuperPoD总线设备柜 4柜", "schedule_list": [{"activity": "总线设备柜到货（含开箱验货）", "activity_id": "6.3", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "总线设备柜安装", "start_at": "2026-01-12", "end_at": "2026-01-12", "activity_id": "7.22", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜设备上电", "start_at": "2026-01-18", "end_at": "2026-01-19", "activity_id": "7.23", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜验收", "start_at": "2026-01-20", "end_at": "2026-01-26", "activity_id": "7.24", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-灵衢网络", "start_at": "2026-01-20", "end_at": "2026-01-21", "activity_id": "8.5", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-灵衢网络", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.10", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-灵衢网络", "start_at": "2026-01-27", "end_at": "2026-01-29", "activity_id": "8.13", "primary_activity": "单机调测", "primary_activity_id": 8}]}, {"management_unit": "B2DH401-POD01", "product_group_name": "网络", "arrival_date": "2026-01-10", "end_date": "2026-01-23", "device_list": "CE9866-128DQ 6台", "schedule_list": [{"activity": "网络到货（含开箱验货）", "activity_id": "6.9", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "网络设备安装", "star | 1 | 2026-03-09 22:43:43 | l00880586
846 | 0 | 2 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH401-POD04 | [{"management_unit": "B2DH401-POD04", "product_group_name": "灵衢线缆", "arrival_date": "2026-01-05", "end_date": "2026-01-17", "device_list": "400G MPO线缆 2688根", "schedule_list": [{"activity": "灵衢线缆到货（含开箱验货）", "activity_id": "6.5", "end_at": "2026-01-05", "start_at": "2026-01-05", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "机房洁净度测试", "start_at": "2025-12-02", "end_at": "2025-12-06", "activity_id": "7.1", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "综合布线与成端-灵衢线缆", "start_at": "2026-01-06", "end_at": "2026-01-17", "activity_id": "7.3", "primary_activity": "工程安装", "primary_activity_id": 7}]}, {"management_unit": "B2DH401-POD04", "product_group_name": "计算柜", "arrival_date": "2026-01-10", "end_date": "2026-01-29", "device_list": "Atlas 900 A3 SuperPoD计算柜 12柜", "schedule_list": [{"activity": "计算柜到货（含开箱验货）", "activity_id": "6.2", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "转运与设备静置", "start_at": "2026-01-11", "end_at": "2026-01-11", "activity_id": "6.11", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "液冷计算柜安装", "start_at": "2026-01-12", "end_at": "2026-01-12", "activity_id": "7.19", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜设备上电", "start_at": "2026-01-18", "end_at": "2026-01-19", "activity_id": "7.20", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜验收", "start_at": "2026-01-20", "end_at": "2026-01-26", "activity_id": "7.21", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-智算服务器", "start_at": "2026-01-20", "end_at": "2026-01-21", "activity_id": "8.2", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "智算硬件压测", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.6", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-智算服务器", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.8", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-智算服务器", "start_at": "2026-01-27", "end_at": "2026-01-29", "activity_id": "8.12", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算管理系统对接", "start_at": "2026-01-27", "end_at": "2026-01-28", "activity_id": "9.1", "primary_activity": "集群调测", "primary_activity_id": 9}]}, {"management_unit": "B2DH401-POD04", "product_group_name": "总线设备柜", "arrival_date": "2026-01-10", "end_date": "2026-01-29", "device_list": "Atlas 900 A3 SuperPoD总线设备柜 4柜", "schedule_list": [{"activity": "总线设备柜到货（含开箱验货）", "activity_id": "6.3", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "总线设备柜安装", "start_at": "2026-01-12", "end_at": "2026-01-12", "activity_id": "7.22", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜设备上电", "start_at": "2026-01-18", "end_at": "2026-01-19", "activity_id": "7.23", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜验收", "start_at": "2026-01-20", "end_at": "2026-01-26", "activity_id": "7.24", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-灵衢网络", "start_at": "2026-01-20", "end_at": "2026-01-21", "activity_id": "8.5", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-灵衢网络", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.10", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-灵衢网络", "start_at": "2026-01-27", "end_at": "2026-01-29", "activity_id": "8.13", "primary_activity": "单机调测", "primary_activity_id": 8}]}, {"management_unit": "B2DH401-POD04", "product_group_name": "网络", "arrival_date": "2026-01-10", "end_date": "2026-01-23", "device_list": "CE9866-128DQ 6台", "schedule_list": [{"activity": "网络到货（含开箱验货）", "activity_id": "6.9", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "网络设备安装", "star | 1 | 2026-03-09 22:43:43 | l00880586
847 | 0 | 2 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH401-POD02 | [{"management_unit": "B2DH401-POD02", "product_group_name": "灵衢线缆", "arrival_date": "2026-01-05", "end_date": "2026-01-17", "device_list": "400G MPO线缆 2688根", "schedule_list": [{"activity": "灵衢线缆到货（含开箱验货）", "activity_id": "6.5", "end_at": "2026-01-05", "start_at": "2026-01-05", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "机房洁净度测试", "start_at": "2025-12-02", "end_at": "2025-12-06", "activity_id": "7.1", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "综合布线与成端-灵衢线缆", "start_at": "2026-01-06", "end_at": "2026-01-17", "activity_id": "7.3", "primary_activity": "工程安装", "primary_activity_id": 7}]}, {"management_unit": "B2DH401-POD02", "product_group_name": "计算柜", "arrival_date": "2026-01-10", "end_date": "2026-01-29", "device_list": "Atlas 900 A3 SuperPoD计算柜 12柜", "schedule_list": [{"activity": "计算柜到货（含开箱验货）", "activity_id": "6.2", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "转运与设备静置", "start_at": "2026-01-11", "end_at": "2026-01-11", "activity_id": "6.11", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "液冷计算柜安装", "start_at": "2026-01-12", "end_at": "2026-01-12", "activity_id": "7.19", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜设备上电", "start_at": "2026-01-18", "end_at": "2026-01-19", "activity_id": "7.20", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜验收", "start_at": "2026-01-20", "end_at": "2026-01-26", "activity_id": "7.21", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-智算服务器", "start_at": "2026-01-20", "end_at": "2026-01-21", "activity_id": "8.2", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "智算硬件压测", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.6", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-智算服务器", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.8", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-智算服务器", "start_at": "2026-01-27", "end_at": "2026-01-29", "activity_id": "8.12", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算管理系统对接", "start_at": "2026-01-27", "end_at": "2026-01-28", "activity_id": "9.1", "primary_activity": "集群调测", "primary_activity_id": 9}]}, {"management_unit": "B2DH401-POD02", "product_group_name": "总线设备柜", "arrival_date": "2026-01-10", "end_date": "2026-01-29", "device_list": "Atlas 900 A3 SuperPoD总线设备柜 4柜", "schedule_list": [{"activity": "总线设备柜到货（含开箱验货）", "activity_id": "6.3", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "总线设备柜安装", "start_at": "2026-01-12", "end_at": "2026-01-12", "activity_id": "7.22", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜设备上电", "start_at": "2026-01-18", "end_at": "2026-01-19", "activity_id": "7.23", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜验收", "start_at": "2026-01-20", "end_at": "2026-01-26", "activity_id": "7.24", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-灵衢网络", "start_at": "2026-01-20", "end_at": "2026-01-21", "activity_id": "8.5", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-灵衢网络", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.10", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-灵衢网络", "start_at": "2026-01-27", "end_at": "2026-01-29", "activity_id": "8.13", "primary_activity": "单机调测", "primary_activity_id": 8}]}, {"management_unit": "B2DH401-POD02", "product_group_name": "网络", "arrival_date": "2026-01-10", "end_date": "2026-01-23", "device_list": "CE9866-128DQ 6台", "schedule_list": [{"activity": "网络到货（含开箱验货）", "activity_id": "6.9", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "网络设备安装", "star | 1 | 2026-03-09 22:43:43 | l00880586
848 | 0 | 2 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH402-POD06 | [{"management_unit": "B2DH402-POD06", "product_group_name": "灵衢线缆", "arrival_date": "2026-01-05", "end_date": "2026-01-17", "device_list": "400G MPO线缆 2688根", "schedule_list": [{"activity": "灵衢线缆到货（含开箱验货）", "activity_id": "6.5", "end_at": "2026-01-05", "start_at": "2026-01-05", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "机房洁净度测试", "start_at": "2025-12-02", "end_at": "2025-12-06", "activity_id": "7.1", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "综合布线与成端-灵衢线缆", "start_at": "2026-01-06", "end_at": "2026-01-17", "activity_id": "7.3", "primary_activity": "工程安装", "primary_activity_id": 7}]}, {"management_unit": "B2DH402-POD06", "product_group_name": "计算柜", "arrival_date": "2026-03-04", "end_date": "2026-03-18", "device_list": "Atlas 900 A3 SuperPoD计算柜 12柜", "schedule_list": [{"activity": "计算柜到货（含开箱验货）", "activity_id": "6.2", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "转运与设备静置", "start_at": "2026-03-05", "end_at": "2026-03-05", "activity_id": "6.11", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "液冷计算柜安装", "start_at": "2026-03-06", "end_at": "2026-03-06", "activity_id": "7.19", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜设备上电", "start_at": "2026-03-07", "end_at": "2026-03-08", "activity_id": "7.20", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜验收", "start_at": "2026-03-09", "end_at": "2026-03-15", "activity_id": "7.21", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-智算服务器", "start_at": "2026-03-09", "end_at": "2026-03-10", "activity_id": "8.2", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "智算硬件压测", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.6", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-智算服务器", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.8", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-智算服务器", "start_at": "2026-03-16", "end_at": "2026-03-18", "activity_id": "8.12", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算管理系统对接", "start_at": "2026-03-16", "end_at": "2026-03-17", "activity_id": "9.1", "primary_activity": "集群调测", "primary_activity_id": 9}]}, {"management_unit": "B2DH402-POD06", "product_group_name": "总线设备柜", "arrival_date": "2026-03-04", "end_date": "2026-03-18", "device_list": "Atlas 900 A3 SuperPoD总线设备柜 4柜", "schedule_list": [{"activity": "总线设备柜到货（含开箱验货）", "activity_id": "6.3", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "总线设备柜安装", "start_at": "2026-03-06", "end_at": "2026-03-06", "activity_id": "7.22", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜设备上电", "start_at": "2026-03-07", "end_at": "2026-03-08", "activity_id": "7.23", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜验收", "start_at": "2026-03-09", "end_at": "2026-03-15", "activity_id": "7.24", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-灵衢网络", "start_at": "2026-03-09", "end_at": "2026-03-10", "activity_id": "8.5", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-灵衢网络", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.10", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-灵衢网络", "start_at": "2026-03-16", "end_at": "2026-03-18", "activity_id": "8.13", "primary_activity": "单机调测", "primary_activity_id": 8}]}, {"management_unit": "B2DH402-POD06", "product_group_name": "网络", "arrival_date": "2026-03-04", "end_date": "2026-03-17", "device_list": "CE9866-128DQ 6台", "schedule_list": [{"activity": "网络到货（含开箱验货）", "activity_id": "6.9", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "网络设备安装", "star | 1 | 2026-03-09 22:43:43 | l00880586
849 | 0 | 2 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH402-POD05 | [{"management_unit": "B2DH402-POD05", "product_group_name": "灵衢线缆", "arrival_date": "2026-01-05", "end_date": "2026-01-17", "device_list": "400G MPO线缆 2688根", "schedule_list": [{"activity": "灵衢线缆到货（含开箱验货）", "activity_id": "6.5", "end_at": "2026-01-05", "start_at": "2026-01-05", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "机房洁净度测试", "start_at": "2025-12-02", "end_at": "2025-12-06", "activity_id": "7.1", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "综合布线与成端-灵衢线缆", "start_at": "2026-01-06", "end_at": "2026-01-17", "activity_id": "7.3", "primary_activity": "工程安装", "primary_activity_id": 7}]}, {"management_unit": "B2DH402-POD05", "product_group_name": "计算柜", "arrival_date": "2026-03-04", "end_date": "2026-03-18", "device_list": "Atlas 900 A3 SuperPoD计算柜 12柜", "schedule_list": [{"activity": "计算柜到货（含开箱验货）", "activity_id": "6.2", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "转运与设备静置", "start_at": "2026-03-05", "end_at": "2026-03-05", "activity_id": "6.11", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "液冷计算柜安装", "start_at": "2026-03-06", "end_at": "2026-03-06", "activity_id": "7.19", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜设备上电", "start_at": "2026-03-07", "end_at": "2026-03-08", "activity_id": "7.20", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜验收", "start_at": "2026-03-09", "end_at": "2026-03-15", "activity_id": "7.21", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-智算服务器", "start_at": "2026-03-09", "end_at": "2026-03-10", "activity_id": "8.2", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "智算硬件压测", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.6", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-智算服务器", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.8", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-智算服务器", "start_at": "2026-03-16", "end_at": "2026-03-18", "activity_id": "8.12", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算管理系统对接", "start_at": "2026-03-16", "end_at": "2026-03-17", "activity_id": "9.1", "primary_activity": "集群调测", "primary_activity_id": 9}]}, {"management_unit": "B2DH402-POD05", "product_group_name": "总线设备柜", "arrival_date": "2026-03-04", "end_date": "2026-03-18", "device_list": "Atlas 900 A3 SuperPoD总线设备柜 4柜", "schedule_list": [{"activity": "总线设备柜到货（含开箱验货）", "activity_id": "6.3", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "总线设备柜安装", "start_at": "2026-03-06", "end_at": "2026-03-06", "activity_id": "7.22", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜设备上电", "start_at": "2026-03-07", "end_at": "2026-03-08", "activity_id": "7.23", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜验收", "start_at": "2026-03-09", "end_at": "2026-03-15", "activity_id": "7.24", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-灵衢网络", "start_at": "2026-03-09", "end_at": "2026-03-10", "activity_id": "8.5", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-灵衢网络", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.10", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-灵衢网络", "start_at": "2026-03-16", "end_at": "2026-03-18", "activity_id": "8.13", "primary_activity": "单机调测", "primary_activity_id": 8}]}, {"management_unit": "B2DH402-POD05", "product_group_name": "网络", "arrival_date": "2026-03-04", "end_date": "2026-03-17", "device_list": "CE9866-128DQ 6台", "schedule_list": [{"activity": "网络到货（含开箱验货）", "activity_id": "6.9", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "网络设备安装", "star | 1 | 2026-03-09 22:43:43 | l00880586
850 | 0 | 2 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH402-POD08 | [{"management_unit": "B2DH402-POD08", "product_group_name": "灵衢线缆", "arrival_date": "2026-01-05", "end_date": "2026-01-17", "device_list": "400G MPO线缆 2688根", "schedule_list": [{"activity": "灵衢线缆到货（含开箱验货）", "activity_id": "6.5", "end_at": "2026-01-05", "start_at": "2026-01-05", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "机房洁净度测试", "start_at": "2025-12-02", "end_at": "2025-12-06", "activity_id": "7.1", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "综合布线与成端-灵衢线缆", "start_at": "2026-01-06", "end_at": "2026-01-17", "activity_id": "7.3", "primary_activity": "工程安装", "primary_activity_id": 7}]}, {"management_unit": "B2DH402-POD08", "product_group_name": "计算柜", "arrival_date": "2026-03-04", "end_date": "2026-03-18", "device_list": "Atlas 900 A3 SuperPoD计算柜 12柜", "schedule_list": [{"activity": "计算柜到货（含开箱验货）", "activity_id": "6.2", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "转运与设备静置", "start_at": "2026-03-05", "end_at": "2026-03-05", "activity_id": "6.11", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "液冷计算柜安装", "start_at": "2026-03-06", "end_at": "2026-03-06", "activity_id": "7.19", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜设备上电", "start_at": "2026-03-07", "end_at": "2026-03-08", "activity_id": "7.20", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜验收", "start_at": "2026-03-09", "end_at": "2026-03-15", "activity_id": "7.21", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-智算服务器", "start_at": "2026-03-09", "end_at": "2026-03-10", "activity_id": "8.2", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "智算硬件压测", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.6", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-智算服务器", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.8", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-智算服务器", "start_at": "2026-03-16", "end_at": "2026-03-18", "activity_id": "8.12", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算管理系统对接", "start_at": "2026-03-16", "end_at": "2026-03-17", "activity_id": "9.1", "primary_activity": "集群调测", "primary_activity_id": 9}]}, {"management_unit": "B2DH402-POD08", "product_group_name": "总线设备柜", "arrival_date": "2026-03-04", "end_date": "2026-03-18", "device_list": "Atlas 900 A3 SuperPoD总线设备柜 4柜", "schedule_list": [{"activity": "总线设备柜到货（含开箱验货）", "activity_id": "6.3", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "总线设备柜安装", "start_at": "2026-03-06", "end_at": "2026-03-06", "activity_id": "7.22", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜设备上电", "start_at": "2026-03-07", "end_at": "2026-03-08", "activity_id": "7.23", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜验收", "start_at": "2026-03-09", "end_at": "2026-03-15", "activity_id": "7.24", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-灵衢网络", "start_at": "2026-03-09", "end_at": "2026-03-10", "activity_id": "8.5", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-灵衢网络", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.10", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-灵衢网络", "start_at": "2026-03-16", "end_at": "2026-03-18", "activity_id": "8.13", "primary_activity": "单机调测", "primary_activity_id": 8}]}, {"management_unit": "B2DH402-POD08", "product_group_name": "网络", "arrival_date": "2026-03-04", "end_date": "2026-03-17", "device_list": "CE9866-128DQ 6台", "schedule_list": [{"activity": "网络到货（含开箱验货）", "activity_id": "6.9", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "网络设备安装", "star | 1 | 2026-03-09 22:43:43 | l00880586
851 | 0 | 2 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH401-POD03 | [{"management_unit": "B2DH401-POD03", "product_group_name": "灵衢线缆", "arrival_date": "2026-01-05", "end_date": "2026-01-17", "device_list": "400G MPO线缆 2688根", "schedule_list": [{"activity": "灵衢线缆到货（含开箱验货）", "activity_id": "6.5", "end_at": "2026-01-05", "start_at": "2026-01-05", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "机房洁净度测试", "start_at": "2025-12-02", "end_at": "2025-12-06", "activity_id": "7.1", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "综合布线与成端-灵衢线缆", "start_at": "2026-01-06", "end_at": "2026-01-17", "activity_id": "7.3", "primary_activity": "工程安装", "primary_activity_id": 7}]}, {"management_unit": "B2DH401-POD03", "product_group_name": "计算柜", "arrival_date": "2026-01-10", "end_date": "2026-01-29", "device_list": "Atlas 900 A3 SuperPoD计算柜 12柜", "schedule_list": [{"activity": "计算柜到货（含开箱验货）", "activity_id": "6.2", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "转运与设备静置", "start_at": "2026-01-11", "end_at": "2026-01-11", "activity_id": "6.11", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "液冷计算柜安装", "start_at": "2026-01-12", "end_at": "2026-01-12", "activity_id": "7.19", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜设备上电", "start_at": "2026-01-18", "end_at": "2026-01-19", "activity_id": "7.20", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜验收", "start_at": "2026-01-20", "end_at": "2026-01-26", "activity_id": "7.21", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-智算服务器", "start_at": "2026-01-20", "end_at": "2026-01-21", "activity_id": "8.2", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "智算硬件压测", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.6", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-智算服务器", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.8", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-智算服务器", "start_at": "2026-01-27", "end_at": "2026-01-29", "activity_id": "8.12", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算管理系统对接", "start_at": "2026-01-27", "end_at": "2026-01-28", "activity_id": "9.1", "primary_activity": "集群调测", "primary_activity_id": 9}]}, {"management_unit": "B2DH401-POD03", "product_group_name": "总线设备柜", "arrival_date": "2026-01-10", "end_date": "2026-01-29", "device_list": "Atlas 900 A3 SuperPoD总线设备柜 4柜", "schedule_list": [{"activity": "总线设备柜到货（含开箱验货）", "activity_id": "6.3", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "总线设备柜安装", "start_at": "2026-01-12", "end_at": "2026-01-12", "activity_id": "7.22", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜设备上电", "start_at": "2026-01-18", "end_at": "2026-01-19", "activity_id": "7.23", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜验收", "start_at": "2026-01-20", "end_at": "2026-01-26", "activity_id": "7.24", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-灵衢网络", "start_at": "2026-01-20", "end_at": "2026-01-21", "activity_id": "8.5", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-灵衢网络", "start_at": "2026-01-22", "end_at": "2026-01-26", "activity_id": "8.10", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-灵衢网络", "start_at": "2026-01-27", "end_at": "2026-01-29", "activity_id": "8.13", "primary_activity": "单机调测", "primary_activity_id": 8}]}, {"management_unit": "B2DH401-POD03", "product_group_name": "网络", "arrival_date": "2026-01-10", "end_date": "2026-01-23", "device_list": "CE9866-128DQ 6台", "schedule_list": [{"activity": "网络到货（含开箱验货）", "activity_id": "6.9", "end_at": "2026-01-10", "start_at": "2026-01-10", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "网络设备安装", "star | 1 | 2026-03-09 22:43:43 | l00880586
852 | 0 | 2 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH402-POD07 | [{"management_unit": "B2DH402-POD07", "product_group_name": "灵衢线缆", "arrival_date": "2026-01-05", "end_date": "2026-01-17", "device_list": "400G MPO线缆 2688根", "schedule_list": [{"activity": "灵衢线缆到货（含开箱验货）", "activity_id": "6.5", "end_at": "2026-01-05", "start_at": "2026-01-05", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "机房洁净度测试", "start_at": "2025-12-02", "end_at": "2025-12-06", "activity_id": "7.1", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "综合布线与成端-灵衢线缆", "start_at": "2026-01-06", "end_at": "2026-01-17", "activity_id": "7.3", "primary_activity": "工程安装", "primary_activity_id": 7}]}, {"management_unit": "B2DH402-POD07", "product_group_name": "计算柜", "arrival_date": "2026-03-04", "end_date": "2026-03-18", "device_list": "Atlas 900 A3 SuperPoD计算柜 12柜", "schedule_list": [{"activity": "计算柜到货（含开箱验货）", "activity_id": "6.2", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "转运与设备静置", "start_at": "2026-03-05", "end_at": "2026-03-05", "activity_id": "6.11", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "液冷计算柜安装", "start_at": "2026-03-06", "end_at": "2026-03-06", "activity_id": "7.19", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜设备上电", "start_at": "2026-03-07", "end_at": "2026-03-08", "activity_id": "7.20", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜验收", "start_at": "2026-03-09", "end_at": "2026-03-15", "activity_id": "7.21", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-智算服务器", "start_at": "2026-03-09", "end_at": "2026-03-10", "activity_id": "8.2", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "智算硬件压测", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.6", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-智算服务器", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.8", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-智算服务器", "start_at": "2026-03-16", "end_at": "2026-03-18", "activity_id": "8.12", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算管理系统对接", "start_at": "2026-03-16", "end_at": "2026-03-17", "activity_id": "9.1", "primary_activity": "集群调测", "primary_activity_id": 9}]}, {"management_unit": "B2DH402-POD07", "product_group_name": "总线设备柜", "arrival_date": "2026-03-04", "end_date": "2026-03-18", "device_list": "Atlas 900 A3 SuperPoD总线设备柜 4柜", "schedule_list": [{"activity": "总线设备柜到货（含开箱验货）", "activity_id": "6.3", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "总线设备柜安装", "start_at": "2026-03-06", "end_at": "2026-03-06", "activity_id": "7.22", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜设备上电", "start_at": "2026-03-07", "end_at": "2026-03-08", "activity_id": "7.23", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜验收", "start_at": "2026-03-09", "end_at": "2026-03-15", "activity_id": "7.24", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-灵衢网络", "start_at": "2026-03-09", "end_at": "2026-03-10", "activity_id": "8.5", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-灵衢网络", "start_at": "2026-03-11", "end_at": "2026-03-15", "activity_id": "8.10", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-灵衢网络", "start_at": "2026-03-16", "end_at": "2026-03-18", "activity_id": "8.13", "primary_activity": "单机调测", "primary_activity_id": 8}]}, {"management_unit": "B2DH402-POD07", "product_group_name": "网络", "arrival_date": "2026-03-04", "end_date": "2026-03-17", "device_list": "CE9866-128DQ 6台", "schedule_list": [{"activity": "网络到货（含开箱验货）", "activity_id": "6.9", "end_at": "2026-03-04", "start_at": "2026-03-04", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "网络设备安装", "star | 1 | 2026-03-09 22:43:43 | l00880586
853 | 0 | 2 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH403-POD09 | [{"management_unit": "B2DH403-POD09", "product_group_name": "灵衢线缆", "arrival_date": "2026-01-05", "end_date": "2026-01-17", "device_list": "400G MPO线缆 2688根", "schedule_list": [{"activity": "灵衢线缆到货（含开箱验货）", "activity_id": "6.5", "end_at": "2026-01-05", "start_at": "2026-01-05", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "机房洁净度测试", "start_at": "2025-12-02", "end_at": "2025-12-06", "activity_id": "7.1", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "综合布线与成端-灵衢线缆", "start_at": "2026-01-06", "end_at": "2026-01-17", "activity_id": "7.3", "primary_activity": "工程安装", "primary_activity_id": 7}]}, {"management_unit": "B2DH403-POD09", "product_group_name": "计算柜", "arrival_date": "2026-01-18", "end_date": "2026-02-01", "device_list": "Atlas 900 A3 SuperPoD计算柜 12柜", "schedule_list": [{"activity": "计算柜到货（含开箱验货）", "activity_id": "6.2", "end_at": "2026-01-18", "start_at": "2026-01-18", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "转运与设备静置", "start_at": "2026-01-19", "end_at": "2026-01-19", "activity_id": "6.11", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "液冷计算柜安装", "start_at": "2026-01-20", "end_at": "2026-01-20", "activity_id": "7.19", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜设备上电", "start_at": "2026-01-21", "end_at": "2026-01-22", "activity_id": "7.20", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "液冷计算柜验收", "start_at": "2026-01-23", "end_at": "2026-01-29", "activity_id": "7.21", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-智算服务器", "start_at": "2026-01-23", "end_at": "2026-01-24", "activity_id": "8.2", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "智算硬件压测", "start_at": "2026-01-25", "end_at": "2026-01-29", "activity_id": "8.6", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-智算服务器", "start_at": "2026-01-25", "end_at": "2026-01-29", "activity_id": "8.8", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-智算服务器", "start_at": "2026-01-30", "end_at": "2026-02-01", "activity_id": "8.12", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算管理系统对接", "start_at": "2026-01-30", "end_at": "2026-01-31", "activity_id": "9.1", "primary_activity": "集群调测", "primary_activity_id": 9}]}, {"management_unit": "B2DH403-POD09", "product_group_name": "总线设备柜", "arrival_date": "2026-01-18", "end_date": "2026-02-01", "device_list": "Atlas 900 A3 SuperPoD总线设备柜 4柜", "schedule_list": [{"activity": "总线设备柜到货（含开箱验货）", "activity_id": "6.3", "end_at": "2026-01-18", "start_at": "2026-01-18", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "总线设备柜安装", "start_at": "2026-01-20", "end_at": "2026-01-20", "activity_id": "7.22", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜设备上电", "start_at": "2026-01-21", "end_at": "2026-01-22", "activity_id": "7.23", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "总线设备柜验收", "start_at": "2026-01-23", "end_at": "2026-01-29", "activity_id": "7.24", "primary_activity": "工程安装", "primary_activity_id": 7}, {"activity": "设备硬装初始化-灵衢网络", "start_at": "2026-01-23", "end_at": "2026-01-24", "activity_id": "8.5", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统部署调测-灵衢网络", "start_at": "2026-01-25", "end_at": "2026-01-29", "activity_id": "8.10", "primary_activity": "单机调测", "primary_activity_id": 8}, {"activity": "计算子系统验证-灵衢网络", "start_at": "2026-01-30", "end_at": "2026-02-01", "activity_id": "8.13", "primary_activity": "单机调测", "primary_activity_id": 8}]}, {"management_unit": "B2DH403-POD09", "product_group_name": "网络", "arrival_date": "2026-01-18", "end_date": "2026-01-31", "device_list": "CE9866-128DQ 6台", "schedule_list": [{"activity": "网络到货（含开箱验货）", "activity_id": "6.9", "end_at": "2026-01-18", "start_at": "2026-01-18", "primary_activity": "到货", "primary_activity_id": 6}, {"activity": "网络设备安装", "star | 1 | 2026-03-09 22:43:43 | l00880586
854 | 0 | 3 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04 | [{"management_unit": "B2DH401-POD01,B2DH401-POD02,B2DH401-POD03,B2DH401-POD04", "schedule_list": [{"activity": "线序及光链路质量排查", "start_at": "2026-01-27", "end_at": "2026-01-29", "activity_id": "9.4", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "综合布线整改", "start_at": "2026-01-30", "end_at": "2026-02-02", "activity_id": "9.5", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "集群通信配置测试", "start_at": "2026-02-03", "end_at": "2026-02-04", "activity_id": "9.6", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "集群系统集成测试", "start_at": "2026-02-05", "end_at": "2026-02-09", "activity_id": "9.7", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "集群性能调优", "start_at": "2026-02-10", "end_at": "2026-02-12", "activity_id": "9.8", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "客户集群验收", "start_at": "2026-02-10", "end_at": "2026-02-19", "activity_id": "12.1", "primary_activity": "验收测试", "primary_activity_id": 12}, {"activity": "输出验收报告", "start_at": "2026-02-20", "end_at": "2026-02-24", "activity_id": "12.2", "primary_activity": "验收测试", "primary_activity_id": 12}, {"activity": "验收报告沟通", "start_at": "2026-02-25", "end_at": "2026-02-27", "activity_id": "12.3", "primary_activity": "验收测试", "primary_activity_id": 12}, {"activity": "移交", "start_at": "2026-02-28", "end_at": "2026-03-01", "activity_id": "12.4", "primary_activity": "验收测试", "primary_activity_id": 12}]}] | 1 | 2026-03-09 23:28:12 | l00880586
855 | 0 | 3 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH403-POD09 | [{"management_unit": "B2DH403-POD09", "schedule_list": [{"activity": "线序及光链路质量排查", "start_at": "2026-01-30", "end_at": "2026-02-01", "activity_id": "9.4", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "综合布线整改", "start_at": "2026-02-02", "end_at": "2026-02-05", "activity_id": "9.5", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "集群通信配置测试", "start_at": "2026-02-06", "end_at": "2026-02-07", "activity_id": "9.6", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "集群系统集成测试", "start_at": "2026-02-08", "end_at": "2026-02-12", "activity_id": "9.7", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "集群性能调优", "start_at": "2026-02-13", "end_at": "2026-02-15", "activity_id": "9.8", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "客户集群验收", "start_at": "2026-02-13", "end_at": "2026-02-22", "activity_id": "12.1", "primary_activity": "验收测试", "primary_activity_id": 12}, {"activity": "输出验收报告", "start_at": "2026-02-23", "end_at": "2026-02-27", "activity_id": "12.2", "primary_activity": "验收测试", "primary_activity_id": 12}, {"activity": "验收报告沟通", "start_at": "2026-02-28", "end_at": "2026-03-02", "activity_id": "12.3", "primary_activity": "验收测试", "primary_activity_id": 12}, {"activity": "移交", "start_at": "2026-03-03", "end_at": "2026-03-04", "activity_id": "12.4", "primary_activity": "验收测试", "primary_activity_id": 12}]}] | 1 | 2026-03-09 23:28:12 | l00880586
856 | 0 | 3 | 5 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling |  | B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08 | [{"management_unit": "B2DH402-POD05,B2DH402-POD06,B2DH402-POD07,B2DH402-POD08", "schedule_list": [{"activity": "线序及光链路质量排查", "start_at": "2026-03-16", "end_at": "2026-03-18", "activity_id": "9.4", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "综合布线整改", "start_at": "2026-03-19", "end_at": "2026-03-22", "activity_id": "9.5", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "集群通信配置测试", "start_at": "2026-03-23", "end_at": "2026-03-24", "activity_id": "9.6", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "集群系统集成测试", "start_at": "2026-03-25", "end_at": "2026-03-29", "activity_id": "9.7", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "集群性能调优", "start_at": "2026-03-30", "end_at": "2026-04-01", "activity_id": "9.8", "primary_activity": "集群调测", "primary_activity_id": 9}, {"activity": "客户集群验收", "start_at": "2026-03-30", "end_at": "2026-04-08", "activity_id": "12.1", "primary_activity": "验收测试", "primary_activity_id": 12}, {"activity": "输出验收报告", "start_at": "2026-04-09", "end_at": "2026-04-13", "activity_id": "12.2", "primary_activity": "验收测试", "primary_activity_id": 12}, {"activity": "验收报告沟通", "start_at": "2026-04-14", "end_at": "2026-04-16", "activity_id": "12.3", "primary_activity": "验收测试", "primary_activity_id": 12}, {"activity": "移交", "start_at": "2026-04-17", "end_at": "2026-04-18", "activity_id": "12.4", "primary_activity": "验收测试", "primary_activity_id": 12}]}] | 1 | 2026-03-09 23:28:12 | l00880586