## sheet0
REL_ID | STAGE | FROM_STAGE | DEST_STAGE | VERSION | PROJECT_ID | PROJECT_SCENE | PRODUCT_FORM | COOLING_METHOD | CATEGORY | PRODUCT_GROUP | FROM_ACTIVITY_ID | FROM_ACTIVITY_NAME | DEST_ACTIVITY_ID | DEST_ACTIVITY_NAME | STATUS | CREATED_AT | CREATED_BY | UPDATED_AT | UPDATED_BY | PROJECT_SCALE
769 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 3.1 | 现场勘测 | 3.3 | 输出工勘报告 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
770 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 3.2 | 远程视频辅助 | 3.3 | 输出工勘报告 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
771 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 3.3 | 输出工勘报告 | 3.4 | 工程勘测报告评审 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
772 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 3.4 | 工程勘测报告评审 | 5.2 | 计算子系统LLD设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
773 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 3.4 | 工程勘测报告评审 | 5.6 | 集群验收方案设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
774 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 3.4 | 工程勘测报告评审 | 5.1 | 集群LLD设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
775 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 3.4 | 工程勘测报告评审 | 5.3 | 网络子系统LLD设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
776 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 3.4 | 工程勘测报告评审 | 5.4 | 存储子系统LLD设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
777 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 4.1 | 信息分析与确认 | 4.2 | 建模仿真设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
778 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 4.2 | 建模仿真设计 | 4.3 | 建模仿真初稿评审 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
779 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 4.3 | 建模仿真初稿评审 | 4.4 | 建模仿真终稿输出 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
780 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 4.4 | 建模仿真终稿输出 | 5.2 | 计算子系统LLD设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
781 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 4.4 | 建模仿真终稿输出 | 5.3 | 网络子系统LLD设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
782 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 4.4 | 建模仿真终稿输出 | 5.4 | 存储子系统LLD设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
783 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 4.4 | 建模仿真终稿输出 | 5.1 | 集群LLD设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
784 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 4.4 | 建模仿真终稿输出 | 5.6 | 集群验收方案设计 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
785 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 5.1 | 集群LLD设计 | 5.7 | 低阶设计评审 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
786 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 5.2 | 计算子系统LLD设计 | 5.7 | 低阶设计评审 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
787 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 5.3 | 网络子系统LLD设计 | 5.7 | 低阶设计评审 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
788 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 5.4 | 存储子系统LLD设计 | 5.7 | 低阶设计评审 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
789 | 1 | 1 | 1 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 规划与设计阶段 |  | 5.6 | 集群验收方案设计 | 5.7 | 低阶设计评审 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
790 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 存储 |  | 2.3 | 机房改造实施 | 7.10 | 存储设备安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
791 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 存储 |  | 5.7 | 低阶设计评审 | 7.10 | 存储设备安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
792 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 存储 |  | 6.8 | 存储到货（含开箱验货） | 7.10 | 存储设备安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
793 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 存储 |  | 7.10 | 存储设备安装 | 7.11 | 存储设备上电 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
794 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 存储 |  | 7.11 | 存储设备上电 | 7.12 | 存储设备硬件验收 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
795 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 存储 |  | 7.11 | 存储设备上电 | 8.4 | 设备硬装初始化-存储服务器 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
796 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 存储 |  | 7.2 | 综合布线与成端-通用线缆 | 7.11 | 存储设备上电 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
797 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 存储 |  | 8.11 | 存储子系统部署调测 | 8.14 | 存储子系统验证 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
798 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 存储 |  | 8.11 | 存储子系统部署调测 | 9.3 | 存储管理系统对接 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
799 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 存储 |  | 8.4 | 设备硬装初始化-存储服务器 | 8.11 | 存储子系统部署调测 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
800 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 总线设备柜 |  | 2.3 | 机房改造实施 | 7.22 | 总线设备柜安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
801 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 总线设备柜 |  | 5.7 | 低阶设计评审 | 7.22 | 总线设备柜安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
802 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 总线设备柜 |  | 6.11 | 转运与设备静置 | 7.22 | 总线设备柜安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
803 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 总线设备柜 |  | 6.3 | 总线设备柜到货（含开箱验货） | 6.11 | 转运与设备静置 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
804 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 总线设备柜 |  | 7.22 | 总线设备柜安装 | 7.23 | 总线设备柜设备上电 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
805 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 总线设备柜 |  | 7.23 | 总线设备柜设备上电 | 8.5 | 设备硬装初始化-灵衢网络 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
806 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 总线设备柜 |  | 7.23 | 总线设备柜设备上电 | 7.24 | 总线设备柜验收 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
807 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 总线设备柜 |  | 7.3 | 综合布线与成端-灵衢线缆 | 7.23 | 总线设备柜设备上电 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
808 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 总线设备柜 |  | 8.10 | 计算子系统部署调测-灵衢网络 | 8.13 | 计算子系统验证-灵衢网络 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
809 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 总线设备柜 |  | 8.5 | 设备硬装初始化-灵衢网络 | 8.10 | 计算子系统部署调测-灵衢网络 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
810 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 机房 |  | 2.3 | 机房改造实施 | 7.1 | 机房洁净度测试 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
811 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 2.3 | 机房改造实施 | 7.19 | 液冷计算柜安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
812 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 5.7 | 低阶设计评审 | 7.19 | 液冷计算柜安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
813 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 6.11 | 转运与设备静置 | 7.19 | 液冷计算柜安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
814 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 6.2 | 计算柜到货（含开箱验货） | 6.11 | 转运与设备静置 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
815 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 7.19 | 液冷计算柜安装 | 7.20 | 液冷计算柜设备上电 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
816 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 7.20 | 液冷计算柜设备上电 | 7.21 | 液冷计算柜验收 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
817 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 7.20 | 液冷计算柜设备上电 | 8.2 | 设备硬装初始化-智算服务器 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
818 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 7.3 | 综合布线与成端-灵衢线缆 | 7.20 | 液冷计算柜设备上电 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
819 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 8.2 | 设备硬装初始化-智算服务器 | 8.6 | 智算硬件压测 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
820 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 8.2 | 设备硬装初始化-智算服务器 | 8.8 | 计算子系统部署调测-智算服务器 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
821 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 8.8 | 计算子系统部署调测-智算服务器 | 8.12 | 计算子系统验证-智算服务器 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
822 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 计算柜 |  | 8.8 | 计算子系统部署调测-智算服务器 | 9.1 | 计算管理系统对接 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
823 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 灵衢线缆 |  | 5.7 | 低阶设计评审 | 7.3 | 综合布线与成端-灵衢线缆 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
824 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 灵衢线缆 |  | 6.5 | 灵衢线缆到货（含开箱验货） | 7.3 | 综合布线与成端-灵衢线缆 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
825 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 灵衢线缆 |  | 7.1 | 机房洁净度测试 | 7.3 | 综合布线与成端-灵衢线缆 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
826 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 网络 |  | 2.3 | 机房改造实施 | 7.13 | 网络设备安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
827 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 网络 |  | 5.7 | 低阶设计评审 | 7.13 | 网络设备安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
828 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 网络 |  | 6.9 | 网络到货（含开箱验货） | 7.13 | 网络设备安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
829 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 网络 |  | 7.13 | 网络设备安装 | 7.14 | 网络设备上电 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
830 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 网络 |  | 7.14 | 网络设备上电 | 8.1 | 基础网络配置 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
831 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 网络 |  | 7.14 | 网络设备上电 | 7.15 | 网络设备硬件验收 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
832 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 网络 |  | 7.2 | 综合布线与成端-通用线缆 | 7.14 | 网络设备上电 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
833 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 网络 |  | 8.1 | 基础网络配置 | 8.7 | 网络子系统部署调测 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
834 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 网络 |  | 8.7 | 网络子系统部署调测 | 8.15 | 网络子系统验证 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
835 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 网络 |  | 8.7 | 网络子系统部署调测 | 9.2 | 网络管理系统对接 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
836 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通用线缆 |  | 5.7 | 低阶设计评审 | 7.2 | 综合布线与成端-通用线缆 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
837 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通用线缆 |  | 6.4 | 通用线缆到货（含开箱验货） | 7.2 | 综合布线与成端-通用线缆 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
838 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通用线缆 |  | 7.1 | 机房洁净度测试 | 7.2 | 综合布线与成端-通用线缆 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
839 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通算 |  | 2.3 | 机房改造实施 | 7.7 | 通算服务器安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
840 | 2 | 1 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通算 |  | 5.7 | 低阶设计评审 | 7.7 | 通算服务器安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
841 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通算 |  | 6.7 | 通算到货（含开箱验货） | 7.7 | 通算服务器安装 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
842 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通算 |  | 7.2 | 综合布线与成端-通用线缆 | 7.8 | 通算设备上电 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
843 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通算 |  | 7.7 | 通算服务器安装 | 7.8 | 通算设备上电 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
844 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通算 |  | 7.8 | 通算设备上电 | 7.9 | 通算设备硬件验收 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
845 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通算 |  | 7.8 | 通算设备上电 | 8.3 | 设备硬装初始化-通算服务器 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
846 | 2 | 2 | 2 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 通算 |  | 8.3 | 设备硬装初始化-通算服务器 | 8.9 | 计算子系统部署调测-通算服务器 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
847 | 3 | 3 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 12.1 | 客户集群验收 | 12.2 | 输出验收报告 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
848 | 3 | 3 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 12.2 | 输出验收报告 | 12.3 | 验收报告沟通 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
849 | 3 | 3 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 12.3 | 验收报告沟通 | 12.4 | 移交 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
850 | 3 | 2 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 8.10 | 计算子系统部署调测-灵衢网络 | 9.4 | 线序及光链路质量排查 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
851 | 3 | 2 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 8.11 | 存储子系统部署调测 | 9.4 | 线序及光链路质量排查 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
852 | 3 | 2 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 8.12 | 计算子系统验证-智算服务器 | 9.6 | 集群通信配置测试 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
853 | 3 | 2 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 8.13 | 计算子系统验证-灵衢网络 | 9.6 | 集群通信配置测试 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
854 | 3 | 2 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 8.14 | 存储子系统验证 | 9.6 | 集群通信配置测试 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
855 | 3 | 2 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 8.15 | 网络子系统验证 | 9.6 | 集群通信配置测试 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
856 | 3 | 2 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 8.16 | 计算子系统验证-通算服务器 | 9.6 | 集群通信配置测试 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
857 | 3 | 2 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 8.7 | 网络子系统部署调测 | 9.4 | 线序及光链路质量排查 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
858 | 3 | 2 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 8.8 | 计算子系统部署调测-智算服务器 | 9.4 | 线序及光链路质量排查 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
859 | 3 | 2 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 8.9 | 计算子系统部署调测-通算服务器 | 9.4 | 线序及光链路质量排查 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
860 | 3 | 3 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 9.4 | 线序及光链路质量排查 | 9.5 | 综合布线整改 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
861 | 3 | 3 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 9.5 | 综合布线整改 | 9.6 | 集群通信配置测试 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
862 | 3 | 3 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 9.6 | 集群通信配置测试 | 9.7 | 集群系统集成测试 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
863 | 3 | 3 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 9.7 | 集群系统集成测试 | 9.8 | 集群性能调优 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目
864 | 3 | 3 | 3 | 1 | 6336ff05cffc4144aa6d96a87e66a36e | 集群集成 | A3 | liquid_cooling | 集群调测与验收阶段 |  | 9.7 | 集群系统集成测试 | 12.1 | 客户集群验收 | 1 | 2025-12-24 16:01:07 | system | 2025-12-24 16:01:07 | system | 标准项目